## 1_2_Jobs
Question | Date Asked | Asked By | Answer | Answered On | Answered By | Status
AEM currently requires additional work to map property names coming from Workday into another CMS module and then associate each property with an image path from DAM. What we’ve seen so far does not account for the hundreds of existing locations we have today.
Are all job-related components production-ready, or are any still considered MVP or interim solutions? |  | @Mayte Eme |  |  |  | deferred
Are Careers authors restricted to Careers-specific components only |  | @Mayte Eme | No |  | @Daniela Khuanghlawn | Pending
Are configuration options role-based (author vs. admin)? |  | @Mayte Eme |  |  |  | deferred
Are deep links supported so we can link users directly to filtered search results (using filter parameters in the URL)? We need the ability to add parameters to the URL string and deep-link users, rather than relying on parameters appended only after a user applies filters. |  | @Gonzalo A. Calasich Ferreyra , @Mayte Eme | You can do deep-link using URL filter parameter, based on the DATA available in stage please find the sample URL: https://aem.careers.stage.hardrock.com/jobs?jobCategory=Security&jobProperty=Hard%20Rock%20Hotel%20%26%20Casino%20Ottawa&jobType=Full%20time&jobLocationCity=Ottawa @Mayte Eme : Can you clarify whether filter selections append parameters to the URL (from user interaction). If so, how do we prevent creating thousands of URL variations that could impact analytics, reporting, or SEO? Also, can you provide the format adobe accepts? must the parameter value be encoded? |  | @Vinay S A | Clarification Needed
Are default search behaviors configurable (e.g., location-first, keyword-first)? |  | @Mayte Eme |  |  |  | deferred
Are filters driven dynamically from Workday data or statically configured? |  | @Mayte Eme |  |  |  | deferred
Are filters interdependent? |  | @Mayte Eme |  |  |  | Pending
Are Job City, State or Country used in any other place than filters and location in card? |  | @Mayte Eme | Job City, state, country is used for the Jobs CF DAM Folder structure |  | @Daniela Khuanghlawn | Pending
Are manually added jobs required to be manually deleted (no scheduling with start/end date/time like Sitecore)? |  | @Mayte Eme | During our discussions with SHRSS IT team they had mentioned they would do a sync b/w AEM and Workday data, if there is additional jobs present in the in AEM, an API is already provisioned for them to DELETE jobs in the AEM. @Shoaib Danish / @Taranjeet Loh Can you please add you insights on data sync and deletion of jobs @Shoaib Danish: The integration process relies on the Job IDs retrurned from Adobe API. So if the IDs of the manually created jobs is not returned then these jobs will not be impacted, if they are then they will be deleted as they dont exist in Workday and the integration process deletes all those jobs from AEM which are not in Workday. @Mayte Eme : for manually created jobs, how does AEM treat manually created jobs in lifecycle and scheduling logic? |  | @Vinay S A @Shoaib Danish | Clarification Needed
Based on demo, seems we can use job components on other sites. is that correct? |  | @Mayte Eme |  |  |  | deferred
Can a job listing query include more than one location? |  | @Mayte Eme | Yes it can include more than one location, Please find the sample stage link where we have 2 locations listed. https://aem.careers.stage.hardrock.com/jobs?jobLocationCity=Ottawa%2CBarcelona%2CLondon%2CEdinburgh @Mayte Eme : There appears to be conflicting information. For clarity, can you confirm whether the current temporary solution supports selecting all locations (any location, any grouping of locations), or if there are limitations? |  | @Vinay S A | Clarification Needed
Can Awards be reused across multiple pages without duplication? |  | @Mayte Eme | Yes by using an experience fragment |  | @Daniela Khuanghlawn | Pending
Can Awards be scheduled (go live on a specific date and automatically expire)? |  | @Mayte Eme |  |  |  | Pending
Can category ordering and visibility be controlled by content authors? |  | @Mayte Eme |  |  |  | deferred
Can Hot Jobs be pinned only on the first page or across all pages? |  | @Angelika Akopyan | Its pinned only on the First page. |  | @Vinay S A | ANSWERED
Can hot jobs be scheduled like in sitecore (using promo cards) |  | @Mayte Eme |  |  |  | deferred
Can I choose which categories are displayed in category cards? |  | @Mayte Eme |  |  |  | deferred
Can Product configure sorting, filtering, or query logic for Hiring Events (e.g., upcoming first, region filter)? |  | @Mayte Eme |  |  |  | Pending
Can the page template used to build this site support additional content blocks below or between? |  | @Mayte Eme |  |  |  | deferred
Can the Workday API sync be triggered on demand? |  | @Angelika Akopyan | @Shoaib Danish / @Taranjeet Loh Can you answer this? @Shoaib Danish: Yes but we don't have any interface, services team can initiate the process on demand |  | @Shoaib Danish | ANSWERED
Can we default the Search Page path to the existing search page so authors don’t have to select it every time? |  | @Mayte Eme |  |  |  | deferred
Can we share external preview links with stakeholders who do not have AEM credentials for this site? |  | @Lisa Cardia | This can be done using the preview feature. This is can setup based on the fully defined requirements @Mayte Eme :For clarity, please confirm whether an out-of-the-box internal preview capability does not exist. I thought this was demonstrated earlier, but it now seems that may not be the case. |  | @Vinay S A | Clarification Needed
Can we use the filtering component that has been developed for Casino Promotions on Careers site so we don’t lose that functionality? |  | @Lisa Cardia @Mayte Eme |  |  |  | deferred
Do hiring events and job fairs automatically show and drop off based on start/end date/time? Is timezone respected per property? |  | @Mayte Eme |  |  |  | Pending
Do Hot Jobs automatically drop off based on end date/time? Is timezone respected per property? |  | @Mayte Eme |  |  |  | Pending
Do we have the option to add short description to Hot Job card if necessary? |  | @Lisa Cardia | Hot Jobs are driven from the Jobs CF, and as per the initial requirements defined there was not data field requested for description, hence you will not be able to show descriptions, https://shrss.atlassian.net/browse/AAEMDAM-1173 @Mayte Eme : who answered this question and when? Also, can you point us to the requirement artifact where Short Description was explicitly out of scope? We need to track this as either a missed requirement or a new enhancement request. |  | @Vinay S A | answered
Does filter state persist across navigation? |  | @Mayte Eme |  |  |  | Pending
Does the Job Card support personalization rules (e.g., geo-targeted jobs)? |  | @Mayte Eme |  |  |  | Pending
For Job Portal Url, Is this URL automatically assigned as the default CTA link on job listing cards? |  | @Mayte Eme |  |  |  | Pending
Has load testing been done at scale? |  | @Mayte Eme |  |  |  | deferred
How are Benefits managed across pages (Home and Benefits page)? shared? |  | @Mayte Eme | Currently cards on separate pages. |  | @Daniela Khuanghlawn | Pending
How are dynamic queries built to reuse components across pages? |  | @Mayte Eme |  |  |  | Pending
How are Hiring Events implemented in AEM? |  | @Mayte Eme | Hiring Events are currently using the Promotions CF Model and displayed with the CF Card component |  | @Daniela Khuanghlawn | Pending
How are image cropping, scaling, and focal points controlled to prevent distortion? |  | @Mayte Eme |  |  |  | deferred
How are long job titles truncated — CSS only or server-side logic? |  | @Mayte Eme |  |  |  | Pending
How are testimonials modeled in AEM? |  | @Mayte Eme | Testimonials use the video card component |  | @Daniela Khuanghlawn | deferred
How does search behave with no results or partial matches? |  | @Mayte Eme |  |  |  | deferred
How does the Job Listing Card component handle incomplete or missing data? |  | @Mayte Eme |  |  |  | deferred
How is search relevance and ranking determined? |  | @Mayte Eme |  |  |  | deferred
How long does a full sync take (we currently have 800+ jobs in PROD)? |  | @Angelika Akopyan | Once the data is pushed, reflecting on end user should not take more than 15-20mins(Apart from any unforeseen error, which we have not seen till date), Also question here is will the sync happen for all 800+ jobs every time? @Shoaib Danish / @Taranjeet Loh @Shoaib Danish: We dont have that kind of data in source (Workday), so we are not sure how much time it will take. Ideally it should not take more than 10 minutes. @Mayte Eme : has any testing been done to ensure will handle all jobs? |  | @Vinay S A @Shoaib Danish | Clarification Needed
How long does a job remain flagged as “Hot”? |  | @Mayte Eme | Until a content author turns off the Hot Job toggle in the Job CF. |  | @Daniela Khuanghlawn | deferred
How often does the Workday API job sync run? |  | @Mayte Eme | The SHRSS system can perform multiple data pushes for job data as required(This API is push based approch). For more detailed information on the frequency of these data pushes, please reach out to @Shoaib Danish / @Taranjeet Loh , as they can provide the most accurate details. @Shoaib Danish After every 30 minutes @Mayte Eme : If there’s a force sync, does that change the 30-min schedule or does it reset? |  | @Vinay S A @Shoaib Danish | Clarification Needed
How will property/location data and images be fully mapped and maintained in AEM for Careers? ETR? |  | @Mayte Eme |  |  |  | deferred
If “Is API Data” is unchecked that’s the next sync checks it? Assume not but would like confirmation |  | @Mayte Eme |  |  |  | Pending
If a user overrides a Hot Job image, will this override the image displayed in WorkDay listings? |  | @Lisa Cardia | The reverse sync is not available, data updated on the AEM will not be synced in the workday, Workday data is always the source of truth. @Mayte Eme If a user overrides the image for a job within the Hot Jobs component/field/section/item, is that override scoped only to that instance, or does it update the underlying job model used by other components such as the Job Listing page? |  | @Vinay S A | Clarification Needed
If an asset reference is moved, does the image break or is the reference preserved? (This was answered in the session but can we verify that there would be no situation where a referenced asset could break if the asset is moved/renamed?) |  | @Don Middlebrook |  |  |  | deferred
If DPLT updates a property, does it automatically update both Brand and Careers? |  | @Mayte Eme |  |  |  | Pending
If needed to hide a job coming from Workday API, can we do that? (until Workdays does the manual update and syncs)? |  | @Mayte Eme | un-publish the Job CF will hide the jobs from listing, but in the next subsequent sync if the same job is updated and pushed to AEM, this will republish the job cf as part of sync process |  | @Vinay S A | answered
If we update Benefits in one place, does it update everywhere automatically? |  | @Mayte Eme | The benefits cards can be moved to an experience fragment. |  | @Daniela Khuanghlawn | Pending
If we use an experiment fragment for shared cards across pages, can we modify the fragment to exclude the card of the page we are on? |  | @Lisa Cardia | All the cards in the experience fragment renders wherever the experience fragment is referenced, so there is no provision of some content of experience fragment getting hidden based on the page we are in. This can be achieved based on custom implementation, if we have the requirements fully defined @Mayte Eme: Before we consider custom implementation, can you confirm whether there is a standard AEM pattern (e.g., query-based component, conditional rendering rule, policy-level configuration) that would support this use case? |  | @Vinay S A | Clarification Needed
Is the layout responsive and optimized for all breakpoints (desktop, tablet, mobile)? |  | @Mayte Eme |  |  |  | deferred
Is the locations page using DPLT? |  | @Mayte Eme | No |  | @Daniela Khuanghlawn | deferred
Is there a custom 404 for expired jobs? |  | @Mayte Eme |  |  |  | Pending
Is there a limit to how many Hot Jobs display? |  | @Mayte Eme | Limit is set by author in the component |  | @Daniela Khuanghlawn | Pending
Is there built-in logic to maintain equal row heights across dynamic content? |  | @Mayte Eme |  |  |  | Pending
Is there version history for job overrides? |  | @Mayte Eme |  |  |  | Pending
Is this site built using shared, reusable component? |  | @Mayte Eme | All of the component are shared across the LOB. @Mayte Eme : Just to confirm: Are all Careers components shared and reusable, so that updating content in one place updates it everywhere it appears within the site and other sites? |  | @Vinay S A | Clarification Needed
Need to get a walk us through a live authoring example of creating a Hiring Event from start to publish and scheduled drop off. including feeds/queries on other pages/sites. |  | @Mayte Eme |  |  |  | Pending
Several images currently appear cropped incorrectly, distorted, or oversized, which negatively impacts brand perception.
The address from API, where is that used? |  | @Mayte Eme |  |  |  | Pending
The Inclusion page uses shared components—how are those configured? |  | @Mayte Eme |  |  |  | Pending
There are noticeable differences in typography, spacing, and visual treatments compared to the existing site. We need clarity on when these styling inconsistencies will be resolved to ensure visual consistency and brand alignment prior to go-live.
To help us provide accurate feedback, can you please include direct links to each component reviewed during these sessions so we can easily reference them afterward? |  | @Mayte Eme |  |  |  | Pending
Told tags are internal metadata to categorize content but can they be used to query content? |  | @Mayte Eme |  |  |  | Pending
We understand LD JSON is not used but why is it there and what does it do if used? |  | @Mayte Eme |  |  |  | Pending
What are the exact sorting rules? (e.g., Job Title → Country → City?) |  | @Mayte Eme , @Charles Baugh |  |  |  | Pending
What are the image specs for career components? |  | @Mayte Eme , @Lisa Cardia |  |  |  | deferred
What are the user roles created for this website? |  | @Mayte Eme |  |  |  | deferred
What component is used for Testimonials on Careers? |  | @Mayte Eme | Video Card |  | @Daniela Khuanghlawn | Pending
What component is used for the Awards accordion? |  | @Mayte Eme | Awards is using the card carousel component |  | @Daniela Khuanghlawn | Pending
What component is used for the pre-footer form CTA? |  | @Mayte Eme | Please clarify what pre-footer form you are referring to. |  |  | Pending
What components are used to render Benefits modules? |  | @Mayte Eme | Card Component |  | @Daniela Khuanghlawn | Pending
What data is sent to the data layer on job click? |  | @Mayte Eme |  |  |  | deferred
What does a Hiring Event detail page template look like? |  | @Mayte Eme |  |  |  | Pending
What does the Hiring Events listing page use to render events? |  | @Mayte Eme | The HE Listing page is currently using the CF Card component. |  | @Daniela Khuanghlawn | Pending
What does type do? |  | @Mayte Eme |  |  |  | Pending
What happens if a category/location/property/type has no jobs in filters? |  | @Mayte Eme |  |  |  | deferred
What happens if a job detail page URL exists but job no longer exists in Workday? |  | @Mayte Eme |  |  |  | Pending
What happens if the Workday integration fails? Is there an error state or fallback page? |  | @Mayte Eme | Error response is sent for based on the error type, and Adobe is hoping based on error type SHRSS workday team can re-push the data. @Shoaib Danish / @Taranjeet Loh Please share your additional inputs. @Shoaib Danish: If the integration fails, then it does not send any update to AEM. @Mayte Eme : What happens in the UI ? for the customer? |  | @Vinay S A @Shoaib Danish | Clarification Needed
What happens if Workday data is missing, delayed, or malformed? |  | @Mayte Eme | Error response is sent back to SHRSS workday system, this should identify the error type and re-push the data accordingly. @Mayte Eme : What happens in the UI ? for the customer? |  | @Vinay S A | Clarification Needed
What image renditions are generated, and are aspect ratios enforced |  | @Mayte Eme |  |  |  | deferred
What is the element ID or tracking event for job card clicks? |  | @Mayte Eme |  |  |  | deferred
What is the finalized DAM folder structure for job-related images? |  | @Mayte Eme |  |  |  | deferred
What is the page template careers site uses? |  | @Lisa Cardia |  |  |  | Pending
What is the recommended number of job listings per page? |  | @Mayte Eme | This is a authoring configuration kept on the component, and we have configured the same number(50 Jobs per page) in stage, SHRSS team can reduce the same based on the requirements. @Mayte Eme : Can SHRSS IT confirm what the intended number of job listings per page should be? Since this implementation does not smart/infinite scrolling and must rely on pagination, the number we choose directly impacts performance, UX, and API load. |  | @Vinay S A | Clarification Needed
What message displays if there are not Hot Jobs during a period of time? What message displays if there no Hiring Events during a period of time? |  | @Lisa Cardia |  |  |  | pending
What templates are used for returning applicants, team members? |  | @Mayte Eme |  |  |  | Pending
What would be the proper process to remove some of the jobs imported from Workday to schedule them for later display? Re-sync from Workday? can a manual update work? |  | @Charles Baugh | un-publish the Job CF will hide the jobs from listing, but in the next subsequent sync if the same job is updated and pushed to AEM, this will republish the job cf as part of sync process @Mayte Eme This confirms that unpublishing is not a viable scheduling solution, since the next sync will republish the job. Does the current implementation support any mechanism to : Suppress specific Workday jobs from display in AEM Schedule imported jobs for future visibility Override publish state independently of Workday sync |  | @Vinay S A | Clarification Needed
When a grid is configured for 3 cards per row and the final row contains only 1 or 2 cards, how is alignment and layout behavior configured (e.g., left-aligned, centered, stretched, or balanced)? |  | @Lisa Cardia |  |  |  | deferred
When job cards don’t fill a full row, should they be centered instead of left-aligned? |  | @Lisa Cardia |  |  |  | Pending
When we create a page (any template) does it inherit header/footer? |  | @Mayte Eme |  |  |  | deferred
When will image issues be addressed and resolved? |  | @Mayte Eme |  |  |  | deferred
When will the style inconsistencies compared to the current site be addressed? |  | @Mayte Eme |  |  |  | deferred
Where are the filters for hot jobs listing page? |  | @Mayte Eme |  |  |  | Pending
Where is Job Zip Code used? |  | @Mayte Eme |  |  |  | Pending
Which fields are not overwritten during Workday job sync? |  | @Mayte Eme , @Lisa Cardia | Image and isHotJob filed is not overwritten, @Mayte Eme : Daniella mentioned 3 fields. are you sure? |  | @Vinay S A | Clarification Needed
Which items on this list are shared enterprise components vs. Careers-only implementations? |  | @Mayte Eme | The components above can be used on any site and the author configures the data source/specific folder on the page. The Job Images component is used in the configuration page shown during the session. |  | @Daniela Khuanghlawn | deferred
While it makes sense to allow selection if multiple search pages exist, in practice there is only one. Requiring authors to manually set this value each time adds unnecessary friction.
Who has access to configuration pages for job components? |  | @Mayte Eme |  |  |  | deferred
Why are logos the same height as navigation links? Is that intentional from a design system perspective? |  | @Mayte Eme |  |  |  | Pending
Why do Hot Jobs cards have standard height and widths (dependent on # of cards displayed), but Event Cards do not have standard heights or widths? |  | @Lisa Cardia |  |  |  | Pending
Why is there no organization to Careers Media Assets in the DAM and why did most assets inherit incorrect naming? |  | @Lisa Cardia , @Don Middlebrook |  |  |  | Pending
Will other page templates work in careers website or will they break? |  | @Mayte Eme | Other template will work. @Mayte Eme : This contradicts earlier information. Please confirm that this is correct and that no CSS conflicts or functional issues will impact the Careers components. |  | @Vinay S A | Clarification Needed

## 3_4_Events
Question | Date Asked | Asked By | Answer | Answered On | Answered By | Status
Is there an override date and override location field for Event Content Fragments? |  | @Lisa Cardia |  |  |  | Pending
Will selecting a Banner Image override the default Banner image on Event Detail Page? |  | @Lisa Cardia |  |  |  | Pending
What asset dimensions work best for Event Content Fragment card, Event Detail Page and Event Calendar components? |  | @Lisa Cardia , @Don Middlebrook |  |  |  | Pending
Why does the image field allow for multiple images on Event Content Fragment Card if only one image can be applied? What happens if multiple images are added? |  | @Lisa Cardia , @Don Middlebrook |  |  |  | Pending
Is there logic applied to Status Labels? Can an author configure multiple statuses at once? Ex: Set the Announce, On-Sale and Pre-sale dates and expect the card and detail page to appear in different states with different CTAs. |  | @Lisa Cardia |  |  |  | Pending
What if we want to hide CTA Label? Leaving blank autopopulates ‘More Info>’ |  | @Lisa Cardia |  |  |  | Pending
How can we avoid properties accidentally selecting incorrect Location Reference # since they do not have Friendly Name? |  | @Lisa Cardia |  |  |  | Pending
Are timezones and languages supported? |  | @Lisa Cardia , @Mayte Eme |  |  |  | Pending
Is it possible for a default image to display for Event Content Fragment card if author does not specifically select an image? |  | @Lisa Cardia |  |  |  | Pending
What does Second CTA Label button do on Event Calendar configuration? |  | @Lisa Cardia |  |  |  | Pending
How do we configure a friendly URL for event detail pages, not auto-generated with a string of unique numbers and letters? |  | @Lisa Cardia |  |  |  | Pending
When creating an Event Content Fragment initially, what is Title and Description associated with before clicking Create? |  | @Lisa Cardia |  |  |  | Pending
Are there Meta Title and Meta Description fields necessary for Events? |  | @Lisa Cardia |  |  |  | Pending
How can we see changes to an Event Content Fragment without publishing? |  | @Lisa Cardia |  |  |  | Pending
What fields in the card and detail page are managed by status values? |  | @Mayte Eme |  |  |  | Pending
How do we schedule events to automatically publish and unpublish based on start and end date/time without manual intervention? |  | @Mayte Eme |  |  |  | Pending
How do we ensure events automatically drop off the Event Calendar after the end date/time without requiring manual unpublishing? |  | @Mayte Eme |  |  |  | Pending
How do we configure property-level timezones so event times always display in the venue’s local timezone instead of the user’s browser timezone? |  | @Mayte Eme |  |  |  | Pending
How do we restrict Location Reference selections by user role or property access to prevent cross-property publishing errors? |  | @Mayte Eme |  |  |  | Pending
How do we configure custom tags (ex: “Dinner & Show,” “21+,” “Free Event”) beyond predefined categories and use them for filtering/display? |  | @Mayte Eme |  |  |  | Pending
How do we dynamically query and display events in other components (carousel, grid, homepage modules) outside of the Event Calendar component? |  | @Mayte Eme |  |  |  | Pending
How do we build event listings using queries (tags/metadata) instead of a single folder path, especially for cross-LOB “featured events” scenarios? |  | @Mayte Eme |  |  |  | Pending
How do we exclude specific categories or tags when pulling events into a listing component? |  | @Mayte Eme |  |  |  | Pending
How do we control sorting behavior when two events share identical start dates and times? |  | @Mayte Eme |  |  |  | Pending
How do we manually reorder featured events within the same month beyond the default “Featured” checkbox logic? |  | @Mayte Eme |  |  |  | Pending
How do we temporarily hide an event without fully unpublishing the Content Fragment? |  | @Mayte Eme |  |  |  | Pending
How do we customize Event Detail Page layouts per property instead of using one global template? |  | @Mayte Eme |  |  |  | Pending
How do we add structured modules to the Event Detail Page (ex: venue info, parking, FAQs, disclaimers) without embedding everything in the Description field? |  | @Mayte Eme |  |  |  | Pending
How do we preview Event Detail pages in author mode without publishing to Stage or Production? |  | @Mayte Eme |  |  |  | Pending
How do we configure ticket prices? |  | @Mayte Eme |  |  |  | Pending
How do we preview Event Listing page in author mode without publishing to Stage or Production? |  | @Mayte Eme |  |  |  | Pending
How do we configure recurring events (weekly, monthly) without creating separate Content Fragments for each occurrence? |  | @Mayte Eme |  |  |  | Pending
How do I group events? |  | @Mayte Eme |  |  |  | Pending
How do we conditionally display different CTAs (Buy Tickets, RSVP, Learn More) based on event type or status? |  | @Mayte Eme |  |  |  | Pending
How do we manage event-specific SEO fields (Meta Title, Meta Description, Open Graph, Schema Event markup)? |  | @Mayte Eme |  |  |  | Pending
How do we display venue name separately from full address instead of relying solely on the Location Reference field? |  | @Mayte Eme |  |  |  | Pending
How do we add structured compliance disclaimers (ex: 21+, ID required) as dedicated fields instead of manual RTE content? |  | @Mayte Eme |  |  |  | Pending
How do we duplicate or clone events efficiently for repeat use cases? |  | @Mayte Eme |  |  |  | Pending
How do we report on which Event Content Fragments are live, unpublished, expired, or scheduled? |  | @Mayte Eme |  |  |  | Pending
How do we prioritize certain events globally (pinning logic) beyond chronological sorting? |  | @Mayte Eme |  |  |  | Pending
How do we integrate event status dynamically with ticketing systems? |  | @Mayte Eme |  |  |  | Pending
How do we configure different event card layout variations (horizontal, vertical, large hero, compact)? |  | @Mayte Eme |  |  |  | Pending
How do we configure default filters for specific properties (ex: default to “Concerts” category)? |  | @Mayte Eme |  |  |  | Pending
How do we configure the filters: venues, categories, date presets and custom date range, properties? |  | @Mayte Eme |  |  |  | Pending
How do we query events to be displayed within site in other pages? |  | @Mayte Eme |  |  |  | Pending
How do we query events from multiple sites or all sites to be displayed in other site? (i.e. entertainment site) |  | @Mayte Eme |  |  |  | Pending
How do we configure event lifecycle states (Announcement/Presale/On-Sale/Post-Event/Cancelled/Rescheduled) so the badge, CTA, and messaging change automatically without manual republish? |  | @Mayte Eme |  |  |  | Pending
How do we define the timing rules for each state (announce time, presale window, on-sale time) so transitions execute at the exact moment and are logged for audit? |  | @Mayte Eme |  |  |  | Pending
How do we handle multi-date events (one event with multiple showtimes) so cards/detail pages display correctly and listings sort predictably? |  | @Mayte Eme |  |  |  | Pending
How do we support multi-venue events (touring performer) without duplicating content fragments or losing consistency? |  | @Mayte Eme |  |  |  | Pending
How do we ensure cross-site event reuse renders with the consuming site’s format while still showing the correct timezone label? |  | @Mayte Eme |  |  |  | Pending
How do we ensure scheduling works for reused content across sites (schedule once, updates everywhere it is displayed)? |  | @Mayte Eme |  |  |  | Pending
How do we prevent layout breakage when scheduled items expire (collapse module or show fallback message, keep row styling patterns intact)? |  | @Mayte Eme |  |  |  | Pending
How do we standardize the tagging taxonomy so filtering logic works (and isn’t ad-hoc per site/component)? |  | @Mayte Eme |  |  |  | Pending
How do we support “badge/bubble text” on event cards (e.g., “21+”, “Free”, “Phone-free”), including cases where properties intentionally leave it blank today (often using )—without forcing awkward author workarounds? (aligns to lifecycle + UI rules) |  | @Mayte Eme |  |  |  | Pending
How do we preview “future state” scheduled content (e.g., “what the page will look like when presale starts”) ? |  | @Mayte Eme |  |  |  | Pending
How do we guarantee event updates reflect within an acceptable caching window on Stage/Prod (and what is the target SLA)? |  | @Mayte Eme |  |  |  | Pending
How do we ensure dynamic queries stay performant (e.g., 200ms server-side target) as events scale across properties? |  | @Mayte Eme |  |  |  | Pending
How do we prevent expired events from appearing in search results, filtered grids, and cross-promotional components? |  | @Mayte Eme |  |  |  | Pending
How do we support soft-deactivation (temporarily hide from UI but retain data and URL)? |  | @Mayte Eme |  |  |  | Pending
How do we restore an archived or expired event without rebuilding the Content Fragment? |  | @Mayte Eme |  |  |  | Pending
How do we configure dynamic filtering logic that adapts based on available content (only show filters that apply)? |  | @Mayte Eme |  |  |  | Pending
How do we exclude certain categories from filters while still allowing them to display in grids? |  | @Mayte Eme |  |  |  | Pending
How do we prevent filter pollution when incorrect Location References are selected? |  | @Mayte Eme |  |  |  | Pending
How do we support conditional display rules for badges? |  | @Mayte Eme |  |  |  | Pending
How do we control display limits (e.g., show only 3 upcoming events)? |  | @Mayte Eme |  |  |  | Pending
How do we control fallback behavior if no events match the query? |  | @Mayte Eme |  |  |  | Pending
How do we configure search indexing rules for events? |  | @Mayte Eme |  |  |  | Pending
How do we configure canonical URLs for event detail pages? |  | @Mayte Eme |  |  |  | Pending
How do event cards adapt across breakpoints (mobile, tablet, desktop)? (they looked weird in the demo) |  | @Mayte Eme |  |  |  | Pending
How do we prevent layout shift when images are missing or delayed? |  | @Mayte Eme |  |  |  | Pending
How do we enforce max character limits on titles to protect grid layout? |  | @Mayte Eme |  |  |  | Pending
How do we implement friendly name display instead of numeric Location IDs? |  | @Mayte Eme |  |  |  | Pending
How do we prevent authors from publishing events without required governance fields? |  | @Mayte Eme |  |  |  | Pending
How do we validate that required lifecycle dates are logically sequenced? |  | @Mayte Eme |  |  |  | Pending
How do we implement role-based author permissions per property? |  | @Mayte Eme |  |  |  | Pending
How do we configure the number of event cards per row per breakpoint (desktop, tablet, mobile), and is this configurable per page template? |  | @Mayte Eme |  |  |  | Pending
How do orphaned cards behave in the final row (e.g., 1–2 cards when layout is set to 3 per row)? Can alignment be configured (left, centered, stretched)? |  | @Mayte Eme |  |  |  | Pending
How do we control card height consistency when titles, statuses, or metadata vary in length? |  | @Mayte Eme |  |  |  | Pending
How does the Smart Event Grid determine priority when multiple events are marked Featured? |  | @Mayte Eme |  |  |  | Pending
How do we define maximum events displayed before pagination or load-more is triggered? |  | @Mayte Eme |  |  |  | Pending
How do we configure pagination vs. “Load More” vs. infinite scroll for event listings? |  | @Mayte Eme |  |  |  | Pending
How does pagination behave when filters are applied — does it reset, persist, or re-query dynamically? |  | @Mayte Eme |  |  |  | Pending
Are filtered results URL-driven (query parameters) to support sharable filtered views? |  | @Mayte Eme |  |  |  | Pending
How do we configure on-page search scope for events — title only, description, venue, tags, status? |  | @Mayte Eme |  |  |  | Pending
How does the Events Filter component support multi-select filters (e.g., Venue + Category + Date Range)? |  | @Mayte Eme |  |  |  | Pending
How are filter states handled in browser history (back button behavior)? |  | @Mayte Eme |  |  |  | Pending
How do we prevent empty filter states (no results) from degrading UX? |  | @Mayte Eme |  |  |  | Pending
How does filtering interact with event lifecycle (Announced, On Sale, Sold Out)? |  | @Mayte Eme |  |  |  | Pending
Is there version history specific to Content Fragments for event rollback? |  | @Mayte Eme |  |  |  | Pending
How do we prevent properties from editing enterprise-managed events? |  | @Mayte Eme |  |  |  | Pending
How are Event Detail Pages structured for SEO (schema markup: Event, Venue, Offer)? |  | @Mayte Eme |  |  |  | Pending
Is sitemap updated instantly upon event publish/unpublish? |  | @Mayte Eme |  |  |  | Pending
How do we aggregate events from multiple properties without duplicating CFs? |  | @Mayte Eme |  |  |  | Pending
Should Events remain a Content Fragment model, or should they be modeled using Experience Fragments or a hybrid architecture for cross-site rendering control? |  | @Mayte Eme |  |  |  | Pending
What is the recommended AEM pattern for separating “event data” from “event presentation” to avoid template duplication across properties? |  | @Mayte Eme |  |  |  | Pending
Does AEM support inheritance or composition patterns for Content Fragments to allow enterprise-managed fields and property-managed overrides? |  | @Mayte Eme |  |  |  | Pending
What is Adobe’s recommended modeling approach for multi-venue or touring events to prevent duplication? |  | @Mayte Eme |  |  |  | Pending
Can filtering logic be centrally managed or does each component require independent configuration? |  | @Mayte Eme |  |  |  | Pending
Can a single Content Fragment be rendered across multiple site themes without duplication? |  | @Mayte Eme |  |  |  | Pending
Does AEM automatically generate structured data for Event schema, or must it be custom implemented? |  | @Mayte Eme |  |  |  | Pending
Are any fields hardcoded in component logic but not exposed in the CF model |  | @Mayte Eme |  |  |  | Pending
Which fields are display-only vs logic-driving (e.g., status, badges, visibility)? |  | @Mayte Eme |  |  |  | Pending
Can fields be conditionally required based on event type? |  | @Mayte Eme |  |  |  | Pending
Does a new property automatically inherit tag taxonomy? |  | @Mayte Eme |  |  |  | Pending
What breaks if a property is added but event configuration is incomplete? |  | @Mayte Eme |  |  |  | Pending
Are renditions automatically generated per event component use? |  | @Mayte Eme |  |  |  | Pending
What happens if an asset is deleted or moved? |  | @Mayte Eme |  |  |  | Pending
How do we configure the default fallback image per site per event type? |  | @Mayte Eme |  |  |  | Pending
Which CF fields map to which component elements (card, detail, calendar)? |  | @Mayte Eme |  |  |  | Pending
Does the card and detail page share the same image source? |  | @Mayte Eme |  |  |  | Pending
How do we configure the mobile image? |  | @Mayte Eme |  |  |  | Pending
Where is the master event taxonomy managed? |  | @Mayte Eme |  |  |  | Pending
Are tags property-specific or global? |  | @Mayte Eme |  |  |  | Pending
How are retired tags handled in existing events? |  | @Mayte Eme |  |  |  | Pending
Does template enforce accessibility standards? (noticed a few issues) |  | @Mayte Eme |  |  |  | Pending
Does URL generation follow naming convention rules? |  | @Mayte Eme |  |  |  | Pending
Can URL be edited after creation without breaking references? |  | @Mayte Eme |  |  |  | Pending
Is there version rollback at page level? |  | @Mayte Eme |  |  |  | Pending
Need to demonstrate cross-property/site reuse |  | @Mayte Eme |  |  |  | Pending

## 5_Careers
Question | Asked By | Date Asked | Answer | Answered On | Answered By | Status
Are accessibility controls (captions, ARIA labels) supported? | @Mayte Eme |  |  |  |  | Pending
Are all fields translatable, or are some hard-coded? | @Mayte Eme |  |  |  |  | Pending
Are field values dynamically inherited or copied per language? | @Mayte Eme |  |  |  |  | Pending
Can alignment rules differ per breakpoint? | @Mayte Eme |  |  |  |  | Pending
Can location-based components fall back to manual text if DPLT record is missing? | @Mayte Eme |  |  |  |  | Pending
Can multiple templates render the same Promotion Fragment? | @Mayte Eme |  |  |  |  | Pending
Can Promotion Content Fragments be decoupled from Casino-specific fields (e.g., Loyalty, Slot) if reused for non-casino use cases like Hiring Events? | @Mayte Eme |  |  |  |  | Pending
Can promotions be syndicated across sites dynamically? | @Mayte Eme |  |  |  |  | Pending
Can we store content on the page level (such as in the Content Tree) without using the Hide feature? The Hide Feature still displays the content in the HTML which may flag to Google and crawlers we are misleading users. | @Lisa Cardia |  |  |  |  | Pending
Do translations require full manual duplication of every field? | @Mayte Eme |  |  |  |  | Pending
Do we need development to add, remove or change including translate labels such as FILTERS and FILTERS CTA button for Promotions Search? (Languages / i18n) | @Lisa Cardia , @Mayte Eme |  |  |  |  | Pending
Does Hide remove components server-side or apply client-side CSS only? | @Mayte Eme |  |  |  |  | Pending
Has load testing been performed? | @Mayte Eme |  |  |  |  | Pending
How are autoplay, mute, and looping governed at component level and browser policy level? | @Mayte Eme |  |  |  |  | Pending
How are Promotion Fragments translated? | @Mayte Eme |  |  |  |  | Pending
How are responsive renditions generated — Dynamic Media, Adaptive Image Servlet, or static crops? | @Mayte Eme |  |  |  |  | Pending
How do we allow authors to toggle between carousel and grid layouts at component level? | @Mayte Eme |  |  |  |  | Pending
How do we configure an SEO-safe, UX-optimized empty-state behavior when no results match filters? | @Mayte Eme |  |  |  |  | Pending
How do we configure compound Query Builder logic (path + tag + metadata) for precise Promotion retrieval? | @Mayte Eme |  |  |  |  | Pending
How do we configure fallback thumbnail behavior if video fails to load? | @Mayte Eme |  |  |  |  | Pending
How do we configure grid alignment logic so incomplete rows center-align? | @Lisa Cardia |  |  |  |  | Pending
How do we configure site-specific filter sets while reusing a global Promotions component? | @Mayte Eme |  |  |  |  | Pending
How do we configure the Promotions component to query multiple CF root paths to support cross-property rendering? | @Lisa Cardia |  |  |  |  | Pending
How do we eliminate manual breakpoint resizing through template-level grid policies? | @Mayte Eme |  |  |  |  | Pending
How do we enable author-controlled filter display order without requiring code changes? | @Mayte Eme |  |  |  |  | Pending
How do we enable controlled extensibility of Promotion Detail pages without breaking structure? | @Mayte Eme |  |  |  |  | Pending
How do we enforce DAM-level asset validation and compression policies? | @Don Middlebrook |  |  |  |  | Pending
How do we exclude specific CFs from query results without restructuring the DAM hierarchy? | @Mayte Eme |  |  |  |  | Pending
How do we implement mobile-specific image overrides for Promotions? | @Mayte Eme |  |  |  |  | Pending
How do we implement start/end lifecycle logic for Promotion visibility beyond page activation? | @Mayte Eme |  |  |  |  | Pending
How do we implement workflow-driven Promotion states (Active, Expired, Archived)? | @Mayte Eme |  |  |  |  | Pending
How do we improve author experience by enabling searchable CF references instead of manual ID entry? | @Mayte Eme |  |  |  |  | Pending
How do we leverage metadata-driven queries instead of hard-coded ID references? | @Mayte Eme |  |  |  |  | Pending
How do we structure taxonomy governance so new tags automatically surface in filter UI across sites? | @Mayte Eme |  |  |  |  | Pending
How do we support layout variation per Promotion while maintaining template governance? | @Mayte Eme |  |  |  |  | Pending
How do we suppress specific filter values in the UI while retaining underlying metadata for governance? | @Mayte Eme |  |  |  |  | Pending
How does AEM handle deduplication when querying overlapping CF paths? | @Mayte Eme |  |  |  |  | Pending
How does AEM validate Promotion ID uniqueness at repository level? | @Mayte Eme |  |  |  |  | Pending
How does Promotion status impact Query Builder results and direct ID rendering? | @Mayte Eme |  |  |  |  | Pending
How is focal point behavior managed across responsive breakpoints? | @Mayte Eme |  |  |  |  | Pending
How is http://Schema.org structured data applied to Promotion Detail pages for SEO compliance? | @Mayte Eme |  |  |  |  | Pending
How is lazy loading implemented to support Core Web Vitals performance? | @Mayte Eme |  |  |  |  | Pending
How is Promotion ID uniqueness scoped — globally across AEM or per site root? | @Mayte Eme |  |  |  |  | Pending
How is responsive video behavior governed across breakpoints? | @Mayte Eme |  |  |  |  | Pending
If a CF Model is modified (field added/removed), What happens to existing fragments? | @Mayte Eme |  |  |  |  | Pending
If cards wrap unevenly across breakpoints, how is visual balance handled? | @Mayte Eme |  |  |  |  | Pending
if DPLT updates, does that update cascade to all components referencing it automatically? | @Mayte Eme |  |  |  |  | Pending
If we schedule a content fragment to go live in the future, but make edits to the content fragment on the back-end, will it impact the scheduling? | @Lisa Cardia |  |  |  |  | Pending
Is it possible to add same control configurations for Video Card for External that exist for Third Party? | @Lisa Cardia |  |  |  |  | Pending
Is there a formal pattern for “Evergreen Content Parking” (reusable hidden components that are not rendered in HTML)? | @Lisa Cardia |  |  |  |  | Pending
Is there a global grid system policy that can enforce consistent column behavior across components? | @Mayte Eme |  |  |  |  | Pending
Is there a library of icons? | @Mayte Eme |  |  |  |  | Pending
Is there a Promotion Detail Page template planned, or are all promotion detail pages expected to be manually created using the Open Page template? | @Mayte Eme |  |  |  |  | Pending
Is there an easier way for authors to select individual Promotion card instead of needing the unique ID? i.e. source of card through folder path of assets | @Lisa Cardia |  |  |  |  | Pending
Is there version control / rollback for CF Model edits? | @Mayte Eme |  |  |  |  | Pending
Please provide best practices for all fields if Third Party is selected for both Fixed and Responsive Layouts. | @Lisa Cardia |  |  |  |  | Pending
Should Hiring Events truly be modeled as Promotions long-term, or should Events CF be enhanced instead? Seems promotions requires even more manual steps than events CF. | @Mayte Eme |  |  |  |  | Pending
What architectural difference causes carousel cards to auto-adjust while standalone cards do not? | @Mayte Eme |  |  |  |  | Pending
What architecture prevents ongoing 1:1 maintenance overhead for Promotion references? | @Mayte Eme |  |  |  |  | Pending
What are the enforced DAM specifications (aspect ratio, resolution, weight) for Promotion card and banner assets? | @Lisa Cardia ; @Don Middlebrook , @Mayte Eme |  |  |  |  | Pending
What formats are accepted for icons? | @Mayte Eme |  |  |  |  | Pending
What global responsive grid policies exist at template level? | @Mayte Eme |  |  |  |  | Pending
What is required to reuse the Casino Integration Promotion Detail template across additional site themes? | @Lisa Cardia |  |  |  |  | Pending
What is the architectural limitation of External URL mode versus structured 3rd Party integration? | @Mayte Eme |  |  |  |  | Pending
What is the architectural reason for requiring a manually entered Promotion ID, and how do we eliminate manual dependency? | @Mayte Eme |  |  |  |  | Pending
What is the caching strategy (Dispatcher/CDN) for Promotion listing queries? | @Mayte Eme |  |  |  |  | Pending
What is the dependency impact if a referenced Promotion ID is modified? | @Mayte Eme |  |  |  |  | Pending
What is the performance impact of broad path-based CF queries at enterprise scale? | @Mayte Eme |  |  |  |  | Pending
What is the recommended architecture to manage Promotion filter options without requiring CF Model changes and code deployments? | @Lisa Cardia | 2026-02-12 |  |  |  | Pending
What is the recommended pattern for recurring Promotion visibility? | @Mayte Eme |  |  |  |  | Pending
What is the scalable pattern for dynamically surfacing Promotions across grids and carousels without manual ID references? | @Mayte Eme |  |  |  |  | Pending
What is the standardized template architecture for Promotion Detail Pages? | @Mayte Eme |  |  |  |  | Pending
What is the underlying logic that drives filter values — dynamic metadata/tag queries or hard-coded dialog configuration? | @Mayte Eme |  |  |  |  | Pending
What lifecycle controls exist beyond basic publish/unpublish? | @Mayte Eme |  |  |  |  | Pending
What performance thresholds should we consider for filter volume in Query Builder–driven listings? | @Mayte Eme |  |  |  |  | Pending
What provider constraints exist when using External URL configuration? | @Mayte Eme |  |  |  |  | Pending
What providers and playback capabilities are supported under 3rd Party mode? | @Mayte Eme, @Lisa Cardia |  |  |  |  | Pending
What styling logic is applied when Default theme is selected? | @Lisa Cardia |  |  |  |  | Pending
What styling or layering conflict prevented white background rendering during KT? | @Lisa Cardia , @Mayte Eme |  |  |  |  | Pending
What thumbnail specifications ensure consistent responsive rendering for Video Cards? | @Lisa Cardia @Don Middlebrook |  |  |  |  | Pending
What validation or fallback logic protects layout integrity when asset specs are incorrect? | @Mayte Eme |  |  |  |  | Pending
Where is focal point controlled — DAM Smart Crop, Image Position tab, or component configuration? | @Don Middlebrook |  |  |  |  | Pending
Where is layout behavior governed — Editable Template Policy or component dialog? | @Mayte Eme |  |  |  |  | Pending
Why do standalone card components Icon and video cards) not inherit responsive grid policies automatically? | @Mayte Eme |  |  |  |  | Pending

## 6_Tagging_Taxonomy_Metadata_Gov
Question | Date Asked | Asked By | Answer | Answered On | Answered By | Status
How are Path and Tags Mapping leveraged in SHRSS implementation? |  | @Don Middlebrook |  |  |  | Pending
What are the implications of consolidating tags? (Consolidate or rename Categories, Event Categories, Category and Properties) |  | @Don Middlebrook |  |  |  | Pending
What are the generic list and how are they being used? |  | @Don Middlebrook |  |  |  | Pending
How can we restrict specified assets from the Sites search rail? (there may be assets that we do not want to be authored on sites) |  | @Don Middlebrook |  |  |  | Pending
What is the current intended taxonomy architecture under the SHRSS namespace (Categories, Category, Event Categories, Properties, Property Names, etc.)? |  | @Mayte Eme |  |  |  | Pending
What are the functional differences between: Categories, Category, Event Categories, etc? |  | @Mayte Eme |  |  |  | Pending
Which components or services currently reference each of these tag branches? |  | @Mayte Eme |  |  |  | Pending
What is the safest approach to consolidating or renaming tag branches without breaking? |  | @Mayte Eme |  |  |  | Pending
Are any tag paths hardcoded in backend services or environment variables? |  | @Don Middlebrook |  |  |  | Pending
If we move or rename tags using the Tag Console, will all JCR references automatically update? |  | @Don Middlebrook |  |  |  | Pending
What validation steps should be completed before restructuring the taxonomy? |  | @Mayte Eme |  |  |  | Pending
Which site components rely on ACS Commons Path/Tag mapping? |  | @Mayte Eme |  |  |  | Pending
Where are Generic Lists currently configured and what functional dependencies do they drive? |  | @Mayte Eme |  |  |  | Pending
Are Generic Lists governing allowed tag values in specific components? |  | @Mayte Eme |  |  |  | Pending
s there documentation mapping each Generic List to its consuming component? |  | @Mayte Eme |  |  |  | Pending
Why are some Content Fragment Model fields driven by static enumerations instead of Tag taxonomy? |  | @Mayte Eme |  |  |  | Pending
Should Category fields inside CF Models be refactored to reference centralized Tags instead of hard-coded options? |  | @Mayte Eme |  |  |  | Pending
What is the difference in implementation between CQ:tags field, Category dropdown field, Metadata schema tag-driven dropdowns? |  | @Mayte Eme |  |  |  | Pending
Is Category a required field on Content Fragments? |  | @Mayte Eme |  |  |  | Pending
What components currently query Content Fragments by Category tag? |  | @Mayte Eme |  |  |  | Pending
How does tag selection in a Content Fragment affect dynamic listings (e.g., News card lists)? |  | @Mayte Eme |  |  |  | Pending
If taxonomy is consolidated, how will this impact existing Content Fragments? |  | @Mayte Eme |  |  |  | Pending
Which asset metadata fields are currently tag-driven? |  | @Mayte Eme |  |  |  | Pending
Are asset metadata tag fields governed differently than page-level tagging? |  | @Mayte Eme |  |  |  | Pending
What is the process to audit tag usage? What is the recommended process for exporting asset metadata for audit (without selecting “All Properties”)? |  | @Mayte Eme |  |  |  | Pending
Is there a recommended naming convention for tag namespaces and branches? |  | @Mayte Eme |  |  |  | Pending
What happens if a tag in use is deleted? |  | @Mayte Eme |  |  |  | Pending
Does AEM provide dependency warnings before tag deletion? |  | @Mayte Eme |  |  |  | Pending
What functionality in SHRSS implementation is currently not supported in Universal Editor? |  | @Mayte Eme |  |  |  | Pending
What is the roadmap for migrating back to Universal Editor (Experience Cloud editor)? |  | @Mayte Eme |  |  |  | Pending
Are any tag-related features incompatible with Universal Editor? |  | @Mayte Eme |  |  |  | Pending
How do we validate that no dynamic components break after tag consolidation? |  | @Mayte Eme |  |  |  | Pending
Can “field presets” for Metadata Export selections be customized? (rather than manual selection of each field) |  | @Don Middlebrook |  |  |  | Pending
Re: Importing Metadata, what are best practices for large imports (e.g., 50k rows): batching, error handling, and rollback? |  | @Don Middlebrook |  |  |  | Pending
Will search facets and filters adapt if we consolidate tag trees? |  | @Don Middlebrook |  |  |  | Pending
Are Events, News, and other CFs using inconsistent metadata patterns? |  | @Lisa Cardia @Don Middlebrook |  |  |  | Pending

## 7_DAM_Training_Usage_Admin
Question | Date Asked | Asked By | Answer | Answered On | Answered By | Status
Why are Careers assets named incorrectly? These weren’t the names in Sitecore. Was this caused by the migration tool? |  | @Lisa Cardia @Don Middlebrook |  |  |  | Pending
Is there a built‑in bulk update tool for sites? |  | @Don Middlebrook |  |  |  | Pending
Should DM sync be limited to specific top‑level folders? |  | @Don Middlebrook |  |  |  | Pending
What are recommended image rendition sizes for SHRSS components? |  | @Don Middlebrook |  |  |  | Pending
When Dynamic Media is implemented, will presets replace static renditions?” |  | @Don Middlebrook |  |  |  | Pending
Is there a built‑in bulk update tool for sites? |  | @Don Middlebrook |  |  |  | Pending
Other than folder level access, how can we restrict specific assets from the search rail that may also live in the same folder as other assets? |  | @Don Middlebrook |  |  |  | Pending
When using the asset picker on sites, or when using the search rail, we are unable to see the full name of many of the assets. Can we adjust the way the filenames are displayed so the user can know they are picking the correct asset? |  | @Don Middlebrook |  |  |  | Pending
Can a report be set up that will identify duplicate assets based on the image specs and not the filename? |  | @Don Middlebrook |  |  |  | Pending
Should static renditions be disabled entirely once DM launches? |  | @Don Middlebrook |  |  |  | Pending
Why were Careers assets renamed incorrectly during migration? Was the migration tool responsible for the naming changes? |  | @Mayte Eme |  |  |  | Pending
What metadata fields should be mandatory upon upload? |  | @Mayte Eme |  |  |  | Pending
Should we rely on metadata (not folder location) for identifying asset languages (EN/ES/FR)? |  | @Mayte Eme |  |  |  | Pending
Can we adjust how asset filenames display in the asset picker and in the Sites rail so authors can see more of the filename (avoid truncation)? |  | @Mayte Eme |  |  |  | Pending
How do static renditions get automatically chosen by out‑of‑the‑box components? |  | @Mayte Eme |  |  |  | Pending
How can we prevent components from accidentally pulling old or duplicate assets? |  | @Mayte Eme |  |  |  | Pending
What are the recommended image rendition sizes for SHRSS components (cards, banners, hero, gallery, tiles, etc.)? |  | @Mayte Eme |  |  |  | Pending
When an author uploads a new asset, how do we ensure the correct rendition is chosen automatically? |  | @Mayte Eme |  |  |  | Pending
Should static renditions be fully disabled once Dynamic Media is launched? |  | @Mayte Eme |  |  |  | Pending
What is the plan for transitioning from static renditions → Dynamic Media presets? |  | @Mayte Eme |  |  |  | Pending
When Dynamic Media is implemented, will image presets replace all static renditions? |  | @Mayte Eme |  |  |  | Pending
Do we need dedicated language folders in DAM to support future localization automation? |  | @Mayte Eme |  |  |  | Pending
Can metadata alone be used to identify language-specific versions of assets? |  | @Mayte Eme |  |  |  | Pending

## 8_Shared_Data
Question | Date Asked | Asked By | Answer | Answered On | Answered By | Status
Can CF Card List center cards when only one or two cards are present? |  | From Transcript |  |  |  | Pending
If an event has no details page, can the CTA be removed entirely? |  | From Transcript
Can root path only reference internal DAM content, or can it reference external locations? |  | From Transcript
How does the component handle secondary CTAs when the CF has no secondary link? |  | From Transcript
What happens if the event model was designed expecting all events to have additional details? |  | From Transcript
What is the purpose of the styling options? Example: setting background color to "Transparent" does nothing. |  | @Edwin Aquino
What do we do if we need to show a card with no CTA? |  | @Edwin Aquino
Some events do not have details and showing “More Info” creates a bad UX.
Can we break inheritance in a variation and use it independently? |  | From Transcript
Can we reorder components in a variation without affecting the master? |  | From Transcript
Can we copy components out of an XF and use them standalone on a page? |  | From Transcript
When should an XF be used inside another XF (e.g., footer disclaimers)? |  | From Transcript
Can we create XF variations for site‑specific changes? |  | From Transcript
How does the language selector determine which items appear? |  | @Edwin Aquino
How do drop‑down CTA / modal / map marker behaviors differ? |  | @Edwin Aquino
Can we change the alignment of the dropdown so it can appear centered? |  | @Edwin Aquino
(Current workaround uses a container + alignment style.)
Is it possible to change the icon, or is the globe the only option? |  | @Edwin Aquino
What does the “Is Reverb” toggle change? |  | From Transcript
Can child pages use a different header than the inherited site header? |  | From Transcript
Would a new page template be required to break header/footer inheritance? |  | From Transcript
How do primary, secondary, and tertiary navigation levels work? |  | From Transcript
What is the expected behavior of the “Hide Links” option? |  | @Edwin Aquino
Are hidden links still visible in Inspect?
Why does the dropdown still appear when all links are hidden?
Can we create an additional column in the secondary navigation? |  | @Edwin Aquino
Can we create a new column for tertiary navigation? |  | @Edwin Aquino
There is no option to change the font color. |  | @Edwin Aquino
If background color is changed to a light color, how do we ensure text is readable?
How do modal types behave (modal, modal small, link, sign-in)? |  | From Transcript
How does the modal reference an XF? |  | From Transcript
How is the “pipe” separator used when there is more than one nav item? |  | From Transcript
Are there restrictions on using multiple utility links? |  | From Transcript
Why does the footer template offer fewer components than standard XFs? |  | From Transcript
How do we decouple the footer? mote very page needs the pre footer. |  | @Mayte Eme
How should disclaimers be handled across sites? |  | From Transcript
Need a new page template that allows breaking header/footer inheritance. |  | @Edwin Aquino
Current child pages always inherit the parent header/footer.
What are the recommended image specs for footer award images for each component? |  | From Transcript
What determines the image max height for each component? |  | From Transcript
How many award images can be added to carousel? |  | From Transcript
How do two-column vs inline layouts get chosen? |  | From Transcript
Why are some footer social icons styled differently? |  | From Transcript
Is there an option to use light/dark icon versions depending on background color? |  | @Edwin Aquino
Can CF models include default images? |  | From Transcript
Do CFs inherit global typography styles? |  | From Transcript
Can CFs be copied to create similar content (events)? |  | From Transcript
When should a CF model be created vs. an XF used instead? |  | From Transcript
Can we create a new template to break header/footer inheritance? |  | From Transcript
How should templates be structured to allow unique headers/footers? |  | From Transcript
How can we validate which components are allowed on which templates? |  | @Mayte Eme
How do we enforce component‑level governance so property teams don’t misuse components? |  | @Mayte Eme
Can we enable/disable components at the template level without making new templates? |  | @Mayte Eme
Are there any components that should never be used inside containers? |  | @Mayte Eme
How can we force authors into structured content (CFs) instead of free‑form page edits? |  | @Mayte Eme
Which components support personalization (Target / ContextHub)? |  | @Mayte Eme
Which components support responsive behavior automatically, and which require specific authoring steps? |  | @Mayte Eme
Is there a component audit available showing which components rely on clientlibs, HTML templates, Sling models, etc.? |  | @Mayte Eme
Which components support drag‑and‑drop DAM assets natively? |  | @Mayte Eme
Which components support variants / styles, and how do we expose more styles? |  | @Mayte Eme
Which CF models support translation and which do not? |  | @Mayte Eme
Do CF references break if CFs are moved into new folders? |  | @Mayte Eme
Can CF models be versioned, and how do we migrate existing CFs to a new version? |  | @Mayte Eme
What is the recommended governance for creating new CF models? Who approves them? |  | @Mayte Eme
How do validation rules in CF models affect existing fragments when rules change? |  | @Mayte Eme
How do authors locate CFs when the number of fragments becomes very large? |  | @Mayte Eme
Can CFs support conditional fields or business rules (e.g., show this field only when…)? |  | @Mayte Eme
How do XF variations handle caching across sites? |  | @Mayte Eme
When should an XF NOT be used because of performance implications? |  | @Mayte Eme
Can XF inheritance be partial? (e.g., inherit CTA but not image?) |  | @Mayte Eme
How do we prevent authors from editing a variation that should be locked? |  | @Mayte Eme
What is the versioning strategy for XFs used on multiple sites with different publish cycles? |  | @Mayte Eme
How does AEM’s site search index XFs, CFs, and DAM assets? |  | @Mayte Eme
Can we exclude certain XF variations or CF fields from search indexing? |  | @Mayte Eme
How are navigation links cached and invalidated globally (important for corporate → property consistency)? |  | @Mayte Eme
Can we define navigation hierarchies outside the Experience Fragment (e.g., via CFs)? |  | @Mayte Eme
How do we properly use “policy inheritance” to avoid accidental template override? |  | @Mayte Eme
How do we create a template that allows flexible component-level permissions but retains design rules? |  | @Mayte Eme
Can we restrict certain components on certain templates for governance? |  | @Mayte Eme
Can we create a template with two optional headers or footers |  | @Mayte Eme
When authors choose an image from the DAM, can we warn them if the image is too large (e.g., 12MB)? |  | @Mayte Eme
Can components auto‑select the correct rendition based on container width? |  | @Mayte Eme
Does the component detect WebP, AVIF, or DM renditions automatically? |  | @Mayte Eme
When Dynamic Media launches, do any current components need refactoring? |  | @Mayte Eme
How do CFs work with AEM translation frameworks? |  | @Mayte Eme
Can XFs be translated automatically, or must they be duplicated per language? |  | @Mayte Eme
How do we ensure shared CF models work across EN/ES/FR without breaking? |  | @Mayte Eme
Do localized assets need folder-level locale structure if we rely on metadata only? |  | @Mayte Eme
Which components automatically contain http://schema.org markup? |  | @Mayte Eme
Should we add structured data fields to CF models for SEO? |  | @Mayte Eme
How do we ensure canonical URLs work when XF content is shared across pages? |  | @Mayte Eme
To what extent do CF‑ or XF‑driven pages get indexed differently? |  | @Mayte Eme
How does AEM handle caching and invalidation when CFs are updated but used on 30+ pages? |  | @Mayte Eme
What is the recommended publishing workflow when shared content exists across multiple sites? |  | @Mayte Eme
Do we need a “Content Freeze” rule when updating shared XFs or CFs? |  | @Mayte Eme
Is there an audit log showing which components are used on which pages (to avoid accidental side effects)? |  | @Mayte Eme
How do we troubleshoot page performance if components load large images or too many CF references? |  | @Mayte Eme
What are some use cases for “Logo Image” Image Type style? |  | @Edwin Aquino

## 9_News
Question | Date Asked | Asked By | Answer | Answered On | Answered By | Status
What is the purpose of Name when creating a News Page? Is it to override the URL? |  | @Edwin Aquino |  |  |  | Pending
For the Search Results Page path, can we investigate using logic to pre-populate this field based on the path the News Page is created. |  | @Edwin Aquino |  |  |  | Pending
What path do we choose for CF List Path? This was a bit confusing in the enablement session. Can we maybe explore updating the ⓘ tool tip to be more informative as it isn’t intuitive on what the path should be. |  | @Edwin Aquino |  |  |  | Pending
For Default Image, can we explore using logic to have default images based on Tags. This is a gap in functionality as current CMS allow us to supply and automatically use a default image if no image is supplied based on the first Category tag associated. |  | @Edwin Aquino |  |  |  | Pending