## Cursor_Generated
Session # | Session | Asked By | Question/Comment
1 | Jobs | Cursor | Governance: Who owns ongoing maintenance of job property–to–image mapping (Adobe, IT, or SHRSS)? What process for new properties or Workday name changes?
1 | Jobs | Cursor | Authoring: Can we get a short checklist or decision tree for authors (which component when; what authors can edit vs what sync overwrites)?
1 | Jobs | Cursor | Tagging/metadata: Besides Hot Job and image, what other author-controlled metadata affects display or filtering? Who governs allowed values for categories (Workday vs author-created)?
1 | Jobs | Cursor | Gap analysis: Which of today's gaps are in scope for careers go-live (e.g. job ID, deep links, hot jobs empty state, image specs) vs deferred to post–gap analysis?
1 | Jobs | Cursor | Permissions: Who can access Job Image configuration (ACS AEM Commons)? Admin-only or can we assign a careers/DAM role?
2 | Events | Cursor | Governance: Who owns Event Categories tags and DPLT location list? Process when property/venue added or renamed?
2 | Events | Cursor | Authoring: One-page checklist for event authoring (what to create, publish, order) and when to use events CF vs promotions CF?
2 | Events | Cursor | Tagging: Event categories vs tags for filtering vs 'dinner and a show' query—who governs?
2 | Events | Cursor | Gap analysis: Decision criteria for events CF vs promotions CF; which gaps apply to which model?
2 | Events | Cursor | Permissions: Who can create/edit Event Categories tags and DPLT location reference options?
3 | Careers | Cursor | Governance: Who owns promotion ID list and filter options? Process to add/change?
3 | Careers | Cursor | Authoring: Single checklist for hiring events (CF → card vs search → detail page → publish order) and when events vs promotions?
3 | Careers | Cursor | Tagging: Do promotions use tags for filtering? If card list adds promotions, tag-based selection?
3 | Careers | Cursor | Gap priorities: Which items (ID vs path, filter removal, card list promotions, video carousel, thumbnail specs, hide vs disable) for careers vs platform expansion?
3 | Careers | Cursor | Permissions: Who can edit promotions model (promo types) and promotion search config (filter labels)?
4 | Tagging_Taxonomy_Metadata_Gov | Cursor | Governance: Who owns SHRSS tag vocabulary and consolidation decision? Process to add namespace?
4 | Tagging_Taxonomy_Metadata_Gov | Cursor | Authoring: Where do authors see tag-driven vs fixed list? One-pager by model/asset type?
4 | Tagging_Taxonomy_Metadata_Gov | Cursor | Permissions: Which groups have create/update/delete on SHRSS tags?
5 | DAM_Training_Usage_Admin | Cursor | Governance: Who approves DAM folder structure and bulk renames?
5 | DAM_Training_Usage_Admin | Cursor | Rendition profiles not applying—root cause and fix in scope?
6 | Shared_Data | Cursor | Governance: Who creates CF models for shared data? Who creates EF variations and rolls out?
7 | News | Cursor | Governance: Who can add news categories (tags) and change news CF model?
8 | Locations | Cursor | Governance: Who maintains location/venue CF when DPLT updates? Who can add new sort/filter fields?
9 | Locations_Day_2 | Cursor | Who owns DPLT classification (line of business) and SHRSS contact for misclassification?
9 | Locations_Day_2 | Cursor | Which groups need read/write on generic list 'regions' for Google Map?
10 | Media | Cursor | Who can add/edit generic list values (e.g. regions)? Which groups get read vs write?
10 | Media | Cursor | Image gallery grid: hide title or show description—enhancement?

## All
Session # | Session | Status | Date Asked | Answered On | Answered By | Asked By | Question/Comment | Answer | Notes
2 | Events | Pending | 2026-02-11 | 2026-02-11 | Daniela Tea | Rick Lyon (Director of Digital Experience) | Preview link for unpublished page to share for approval before republish? | Unpublished CF not on calendar or detail. If publish CF, visible in author; page must be published for end user. Daniela to report back on detail-page behavior. | Preview before publish = gap.
6 | Shared_Data | Answered | 2026-02-19 | 2026-02-19 | Daniela Tea | Rick Lyon | Multiple vanity URLs per page—all link to same page? | Yes. Useful for print (short URL) vs long.
8 | Locations | Answered | 2026-02-23 | 2026-02-23 | Daniela Tea | Rick Lyon | Delivery/venue links: open in new window? | Yes; baked in (external links).
9 | Locations_Day_2 | Deferred | 2026-02-24 | 2026-02-24 | Daniela Tea | Rick Lyon | Booking modal: black border; can we make booking widget same size/background as modal? | Note as gap—configurable color/size for modal.
9 | Locations_Day_2 | Deferred | 2026-02-24 | 2026-02-24 | Daniela Tea | Rick Lyon | Booking offers: can we hide the booking window section completely? | Tried; window still present, fields blank. Hide label too = potential gap. No option to hide completely today.
10 | Media | Pending | 2026-02-25 | 2026-02-25 | Daniela Tea | Rick Lyon | Media gallery: carousel dots not centered (left of center). | Daniela noted; capture for update to center align carousel dots.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Ramona Harris | What is the standard size for the logo image that should be uploaded? | Still need to get back—used whatever was in DAM for Sage site; don't have exact measurements yet.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Ramona Harris | Select locations in job search—are those pulling from AEM? New property—is author responsible for adding so it appears in filter? | Locations come from content fragment (country, state, city). New property/jobs from Workday create folder structure automatically; author does not add. | Ramona had not seen Ottawa in AEM—clarified it's from CF data.
1 | Jobs | Pending | 2026-02-10 |  |  | Product Director | Governance: Who owns ongoing maintenance of job property–to–image mapping (Adobe, IT, or SHRSS)? What process for new properties or Workday name changes? |  | Governance and roles.
1 | Jobs | Pending | 2026-02-10 |  |  | Product Director | Authoring: Can we get a short checklist or decision tree for authors (which component when; what authors can edit vs what sync overwrites)? |  | Authoring clarity.
1 | Jobs | Pending | 2026-02-10 |  |  | Product Director | Tagging/metadata: Besides Hot Job and image, what other author-controlled metadata affects display or filtering? Who governs allowed values for categories (Workday vs author-created)? |  | Tagging and governance.
1 | Jobs | Pending | 2026-02-10 |  |  | Product Director | Gap analysis: Which of today's gaps are in scope for careers go-live (e.g. job ID, deep links, hot jobs empty state, image specs) vs deferred to post–gap analysis? |  | Priorities for go-live.
1 | Jobs | Pending | 2026-02-10 |  |  | Product Director | Permissions: Who can access Job Image configuration (ACS AEM Commons)? Admin-only or can we assign a careers/DAM role? |  | Governance and permissions.
2 | Events | Pending | 2026-02-11 |  |  | Product Director | Governance: Who owns Event Categories tags and DPLT location list? Process when property/venue added or renamed?
2 | Events | Pending | 2026-02-11 |  |  | Product Director | Authoring: One-page checklist for event authoring (what to create, publish, order) and when to use events CF vs promotions CF?
2 | Events | Pending | 2026-02-11 |  |  | Product Director | Tagging: Event categories vs tags for filtering vs 'dinner and a show' query—who governs? |  | Categories = filter; tags = internal; tag for query possible.
2 | Events | Pending | 2026-02-11 |  |  | Product Director | Gap analysis: Decision criteria for events CF vs promotions CF; which gaps apply to which model?
2 | Events | Pending | 2026-02-11 |  |  | Product Director | Permissions: Who can create/edit Event Categories tags and DPLT location reference options?
3 | Careers | Pending | 2026-02-12 |  |  | Product Director | Governance: Who owns promotion ID list and filter options? Process to add/change?
3 | Careers | Pending | 2026-02-12 |  |  | Product Director | Authoring: Single checklist for hiring events (CF → card vs search → detail page → publish order) and when events vs promotions?
3 | Careers | Pending | 2026-02-12 |  |  | Product Director | Tagging: Do promotions use tags for filtering? If card list adds promotions, tag-based selection?
3 | Careers | Pending | 2026-02-12 |  |  | Product Director | Gap priorities: Which items (ID vs path, filter removal, card list promotions, video carousel, thumbnail specs, hide vs disable) for careers vs platform expansion?
3 | Careers | Pending | 2026-02-12 |  |  | Product Director | Permissions: Who can edit promotions model (promo types) and promotion search config (filter labels)?
4 | Tagging_Taxonomy_Metadata_Gov | Pending | 2026-02-17 |  |  | Product Director | Governance: Who owns SHRSS tag vocabulary and consolidation decision? Process to add namespace?
4 | Tagging_Taxonomy_Metadata_Gov | Pending | 2026-02-17 |  |  | Product Director | Authoring: Where do authors see tag-driven vs fixed list? One-pager by model/asset type?
4 | Tagging_Taxonomy_Metadata_Gov | Pending | 2026-02-17 |  |  | Product Director | Permissions: Which groups have create/update/delete on SHRSS tags?
5 | DAM_Training_Usage_Admin | Pending | 2026-02-18 |  |  | Product Director | Governance: Who approves DAM folder structure and bulk renames?
5 | DAM_Training_Usage_Admin | Pending | 2026-02-18 |  |  | Product Director | Rendition profiles not applying—root cause and fix in scope?
6 | Shared_Data | Pending | 2026-02-19 |  |  | Product Director | Governance: Who creates CF models for shared data? Who creates EF variations and rolls out?
7 | News | Pending | 2026-02-20 |  |  | Product Director | Governance: Who can add news categories (tags) and change news CF model?
8 | Locations | Pending | 2026-02-23 |  |  | Product Director | Governance: Who maintains location/venue CF when DPLT updates? Who can add new sort/filter fields?
9 | Locations_Day_2 | Pending | 2026-02-24 |  |  | Product Director | Who owns DPLT classification (line of business) and SHRSS contact for misclassification? | Not answered in session.
9 | Locations_Day_2 | Pending | 2026-02-24 |  |  | Product Director | Which groups need read/write on generic list 'regions' for Google Map? | Not answered in session. Andy covering permissions in KT next week.
10 | Media | Pending | 2026-02-25 |  |  | Product Director | Who can add/edit generic list values (e.g. regions)? Which groups get read vs write?
10 | Media | Pending | 2026-02-25 |  |  | Product Director | Image gallery grid: hide title or show description—enhancement?
2 | Events | Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Mayte Eme / Gonzalo | Hiring events—using promotions not events? What can events CF do vs promotions? | Hiring events section uses promotions content fragment (date/location override). Events CF + calendar/detail = what we covered. Tomorrow: hiring events component. | Careers not using events CF for that section.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | You have two IDs—job unique ID and job ID. Which one are you using? (Displayed one is wrong.) | Right now both come from Workday; what's displayed to end user is job ID. Ticket exists for this; dev team looking at it. | Mayte said 'that's the wrong one'—job ID vs job unique ID; fix via ticket.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Image field—not mapped to pick up automatically the right image like we currently have? | Image is author-input; image configuration page allows setting images per property; author can overwrite or remove.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | If we override something in the CF, does the sync overwrite it or do we keep the override? | Only Workday fields get overwritten. Image, is hot job, and LD JSON are author-only and do not get overwritten by sync.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | How do you create a new job as an author (not from Workday)? | Create → Content Fragment → select Jobs; fill out all fields. Categories are not dropdowns—must match exact value (e.g. casino sales).
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Is there scheduling when adding a job—as soon as you publish it goes live? | Content fragments can be scheduled; Workday jobs get published automatically on sync without author intervention.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Manual jobs—they drop off based on Workday; if manual, we have to manually delete? | Correct.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Do we have an option to immediately hide a job from the website without Workday removing it? (e.g. weekend, can't get hold of anyone.) | Author could delete but sync would republish. No current way to just hide. Daniela to check with dev team if turning off 'is API data' could freeze sync for that job. | Edge case but has happened; need business continuity.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | When clicking a job card—what data do we send to Tealium data layer? Do we have unique IDs per card for tracking? | Daniela to check with tech team. Content fragments have unique IDs; need to confirm what is passed to data layer. | Mayte: need unique IDs per card, not just friendly link.
1 | Jobs | Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | If sync goes wrong and can't display data—do we have an error message or just blank? | No jobs in AEM shows 'no jobs found.' Separate error message for sync failure (vs no results) is a gap—note for gap analysis. | Mayte: had blank page when testing iSense; want custom message for business continuity.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | When you select filters, do they update each other (conditional/dependent filters)? | Yes—e.g. selecting property updates other filter options; unchecking brings categories back.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Job listings—does it only go by state (e.g. Florida) or can we select properties? Can we do multiple properties? | Can select one folder (e.g. Orlando or Florida). You can only select ONE root path, not multiple properties. To show Coco + Classic + Hollywood would require multiple components one after another; can't sort across them. | Mayte: our use case is three South Florida properties; noted as gap.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | For hot jobs can we have the root path higher so it's all hot jobs, not specific to one location? | Yes—set root path higher in hierarchy to get all hot jobs across locations.
1 | Jobs | Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | If there are no hot jobs—does the component hide, or show blank with a message? | Currently shows section title with no cards and no message. Does not hide. Angelika confirmed; Mayte/Lisa want hide or message—gap. | JIRA ticket exists for this.
1 | Jobs | Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Why do we have to configure the search page in Job Filters? We only have one search page. Can it be defaulted? | Currently pointing to correct page. If component used elsewhere, author can change. Defaulting is possible; Mayte wants one step less for authors. Log as gap.
1 | Jobs | Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Job category cards—how do we change/pick which categories to display? (e.g. don't want food and beverage, want to promote others.) | Currently cannot pick and choose categories; shows all or by sort (most jobs / alphabetical). Not in component. | Mayte: we had ability in past; this component may be deprecated.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | What is 'job property' in the image config? Is it a specific name we need to match (e.g. Workday name)? | It's the value from the job property field in the content fragment. Config matches that value to assign the image. Must match exactly.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea / Lucas Nelson | Mayte Eme | Are all locations in the image config? We have over 500 locations; the list doesn't seem long. | Initial setup by Adobe tech team; list may not be complete. Need full list—Lucas to follow up with Vinay; Scott to task IT to get list from Workday and map ahead of time. | Lisa: mapping has to be manually added in AEM; Workday doesn't push it.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | If Workday changes internal name (e.g. HRC Washington DC to Hard Rock Cafe Washington DC), does that break the mapping? | New entry would need to be added in config with the new property value and desired logo. Old name would no longer match. | Mayte: mapping is very manual; concern for 500+ locations.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Who does the mapping and who gets every location name when we go to production? | Adobe did initial setup. Who adds new properties or changes logos unclear; need to understand source of full list. | Scott to ask Vinay; Lisa: whoever handed off first time.
1 | Jobs | Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | On the hot jobs page—where is the filtering and searching? | Filtering is not currently part of the component; open ticket, gap in JIRA.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Queries for bringing in different content by property (like Sitecore scopes)—will we go through that? | Daniela asked for examples. Angelika showed brands/cafes/casinos—same cards on multiple pages. Experience Fragment approach can give single update; exclusion logic (e.g. don't show current page's card) would need custom logic. | Lisa: need logic so on Casinos page we don't show Casinos card (show children excluding current).
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea / Lucas Nelson | Mayte Eme | Did we ask for specs for the job/logo images so we don't have corrupt or huge logos? Who fixes those before go-live? | Spec sheet not yet detailed. Lucas: Daniela to talk with Vinay and authoring support.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Lucas Nelson / Scott Sorel | Mayte Eme | Pagination—recommendation for max number of jobs per page? We have ~800 jobs; have you tested performance? | Lucas: Adobe doesn't have performance testing resource. Scott: take back to TJ/Mohsin. Mayte: had issues before with 50; want an answer.
2 | Events | Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Mayte Eme | Event detail page—why does it look like a card? Are we on careers? Hard Rock Live—can we use for careers? | This is the event detail page (one template). Same for all sites. Daniela created new page to show from scratch. | Mayte: digital page not working for careers events.
2 | Events | Deferred | 2026-02-11 | 2026-02-11 | Daniela Tea | Mayte Eme | Event statuses: all manual or can we schedule (presale, announcement, rescheduled)? Do they drive/hide content? | Currently manual. Gap to have date range per status. Presale/sold out etc. change label/flag; event status message is separate. Doesn't hide CTA or content.
2 | Events | Answered | 2026-02-11 | 2026-02-11 | Mayte Eme / Daniela Tea | Mayte Eme | Recap: unpublish works; schedule not local to property; end date auto drop-off; all statuses manual; no date/location override; three times instead of one (vs Sitecore). | Daniela acknowledged. Hiring events use promotions model (has overrides); events model does not.
2 | Events | Deferred | 2026-02-11 | 2026-02-11 | Daniela Tea | Mayte Eme | Can we choose mix-and-match locations for one calendar (e.g. six properties, or hotel+casinos, or by venue)? | No. One content fragment folder path only; cannot select multiple folders. Big gap for multi-venue/entertainment sites.
2 | Events | Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Mayte Eme | Pull events into other pages (venue page, homepage by category, e.g. dinner and a show)? | Content Fragment card list component can show events (or news); by root path or by tag (e.g. dinner and a show). Not locked to calendar component.
2 | Events | Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Mayte Eme | Can we pull jobs (hot jobs/hiring events) to property page (e.g. Reverb) by tag or location? | Yes—select root path (e.g. Tampa folder); all jobs under that path. Cannot select multiple locations in one component. Exclude category under Tampa? Not in component.
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | When pasting ID elsewhere (e.g. component), is there a dropdown to select from existing or must we remember/paste? | Component field is plain text; no dropdown. Must copy from CF. Gonzalo: gap = source field to navigate DAM and pick CF.
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea / Lucas Nelson | Mayte Eme | Promotion ID for casino or careers? We're not using for casinos; we need to fix for casinos (many users, can't remember IDs). | Initially for casinos. Careers using it for hiring events. Lucas: capture what it doesn't have; disposition in platform expansion; modify/change is part of it.
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Promotion search: can we remove the search field and keep only filters? | Search cannot be removed currently. With filters, search bar always shows. To display as list without filter/search = gap.
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | If we use promotions for hiring events we can't have promotion cards in grid/carousel elsewhere without filter+search—only one-by-one by ID. | Correct. Content fragment card list currently events/news only; gap = add promotions so list/carousel without filter+search.
3 | Careers | Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Transperfect: manual translations for some languages; not always Transperfect. OK? | Noted. Daniela will address in Transperfect KT.
3 | Careers | Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Promotion start/end date and time—is that for scheduling or display only? | Display only. Schedule = Manage Publication > Now or Later (activation date). Not for 'display this event on Saturday but publish tomorrow.'
3 | Careers | Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Job listings on another site (e.g. hotel)—same component, theme changes styling? Can we choose multiple locations? | Yes—component is global; theme drives look. Still one root path only (gap). Use case: Tampa/Hollywood dedicated job pages.
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Events template allows link to another page (event detail). Promotions can't do that—we have hot jobs/dealer university with detail pages. | Promotions: can link to any page from CF. Events: one detail page + ID. Override in events = gap; then could use events for hiring events. Workaround: link to existing page from promotion CF.
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Video card: if we add a fourth, does it become carousel automatically (like Sitecore)? | No. Video card not in allowed components for card carousel or hero carousel. Gap: allow video cards in carousel.
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Card (icon variation): with 6 or 9 cards, does it go 3 to 1 columns automatically or manual per breakpoint? | Manual per viewport for standalone card. Some components (e.g. carousel) have breakpoint config. Mayte: add to gap list.
3 | Careers | Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Executives/diversity page (careers) same as hardrock.com—shared so one update? | Currently separate cards. Can move to experience fragment: update once, same styling both sites. Content fragment = same content, different styling per site. | Rick: corporate page hardrock.com.
3 | Careers | Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Experience fragment: same content, different styling per site possible? | Experience fragment = same content + same look. For same content, different look = content fragment.
3 | Careers | Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Careers locations page same as brand—pulling from DPLT? Can we copy accordion/component so one source? | Careers = accordion/text (migrated); brand = map component + DPLT. Can copy map component to careers. Intent: all location listings from DPLT, one maintenance. | Daniela to post test page with copied component.
2 | Events | Pending | 2026-02-11 | 2026-02-11 | Andy Lambert | Lucas Nelson | Publish delays on stage—investigating? | Andy: seen failed publish entries in cloud services log; raising support ticket; will keep team posted.
9 | Locations_Day_2 | Pending | 2026-02-24 | 2026-02-24 | Daniela Tea | Lisa Cardia / Rick Lyon | Google Map: carousel dots not centered under images. | Daniela noted; would need to be updated to center align carousel dots.
2 | Events | Deferred | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia / Mayte Eme | Clean/friendly URL for event detail (property.com/artist-name not numbers)? | Event ID is read-only to prevent duplicates. Enhancement = make editable for friendly URL. Mayte: need real names; like WordPress/Sitecore—pick up page name. Gap. | Labor intensive; add to gap list.
2 | Events | Pending | 2026-02-11 | 2026-02-11 | Daniela Tea / Andy Lambert | Lisa Cardia / Mayte Eme | Do we have to publish to see changes? How to preview before publish for approval? | View as published doesn't show CF changes until CF is published. Andy: preview tier exists, not configured; will check export. Mayte: need browser preview to screenshot for approval. | Preview server / preview links = gap analysis.
2 | Events | Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia / Mayte Eme | Unpublish event (take down without delete) to repurpose later? | Unpublish CF removes from calendar. Daniela to check if detail URL still accessible. Later: unpublished = detail URL shows configured 'no events' message; content not visible. | Mayte: add as gap—not expected behavior but at least user doesn't see it.
3 | Careers | Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia / Mayte Eme | Promotion ID—where from? What do we put? Is it made up? Required for targeting/analytics we had for casino, not unique ID for display. | Author-entered unique identifier to display one promotion (e.g. content fragment card). No format requirement. Uniqueness validated on save. Same value in another CF blocks save. | Mayte: gap—we don't want this; need to remember/copy; not smart (dropdown of existing IDs).
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia / Mayte Eme | Video card: third party (YouTube) gives fixed/responsive, aspect ratio; external URL doesn't. Same config for external? | External URL = no those options. Third party = full config. Gap—external should have same controls; else only use YouTube/Vimeo. Mayte: don't use external until fixed.
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia / Mayte Eme | Store component on page but not displayed (like Sitecore disable)—reuse later without recreating? Hide = still in DOM? | Hide component (layout > eye) = still in tree, still in DOM/crawled. Not like Sitecore where disabled = not in HTML. Gap: store without rendering for evergreen swap. | Content refresh initiative; rotate temp vs evergreen.
8 | Locations | Answered | 2026-02-23 | 2026-02-23 | Lucas Nelson | Lisa Cardia / Mayte Eme | Gap list: Adobe building it or SHRSS? Confluence questions = gap list? | Lucas: SHRSS documents gaps; Confluence questions feed funnel. Adobe shows framework; SHRSS comes to platform expansion with use cases and gaps. | Scott: questions/needs on Confluence.
5 | DAM_Training_Usage_Admin | Answered | 2026-02-18 | 2026-02-18 | Chris Lewis | Lisa Cardia / Don Middlebrook | Careers asset names odd (C2D5 etc.)—not from Sitecore. Bulk rename? | Chris: migration tool internal ref. Bulk rename via export metadata to Excel, edit names, re-upload.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | Does the image override replace the image on the card and the listing or just the card? | Override updates image in both job listings component (cards) and job search component (horizontal cards). | Lisa noted they typically use logo on listings, property shot on homepage/hiring events.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | Which fields do not get overridden when sync happens? (You said three.) | Image, is hot job, and LD JSON. Only those three are author-only.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | For a new careers page—what template should we use? | Open page template for all these pages (header/footer + content area).
1 | Jobs | Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | If we have fewer than three cards (e.g. one or two), is there a way to center them instead of left align? | Not currently. Would need to discuss in gap portion—centered vs same width vs full width. | Lisa: hot jobs vs hiring events cards all display differently; consistency concern.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | Apply Now button—what is its purpose if the URL always comes from the content fragment? | Button text is configurable in component; the URL/destination is from the content fragment.
1 | Jobs | Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | Hot jobs we use property image; in listings we use logo. Same job in hot jobs vs listing—we want different images. | Noted. Daniela confirmed understanding—hot job might have property image, same job in search shows logo. Gap for implementation.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | Hot jobs page and hiring events page—do we have to add hot jobs manually to every location or does it pull from same feed? | Same component (job listings, hot jobs). Toggle hot job in CF once; appears on homepage and hot jobs page. Hiring events = different content fragment (events session).
1 | Jobs | Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | Hiring events cards vs hot jobs—different widths/heights; not consistent. | Different content fragments; will cover events tomorrow. Noted inconsistency.
1 | Jobs | Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | Shared cards—when on casino page, don't show casino card (show all children excluding current page). Experience fragment gets us reuse; we need that exclusion logic. | Experience fragment = update once. Current implementation is local per page so exclusion was possible. To get both reuse and exclusion would need custom component. Decision for Hard Rock. | Mayte: should have been set up properly; task for Mohsin.
2 | Events | Deferred | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia | Override for date field (e.g. 'every Wednesday through February') instead of actual date/time? | Not in event content fragment. Promotions has date override; can confirm if same behavior wanted for events—gap. | Same question for location override.
2 | Events | Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia | What happens if we add an additional image in the event image field (multi)? | Believes it defaults to first one; can test. Migration used only one image.
2 | Events | Deferred | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia | Event status: logic so presale dates show presale disclaimer then auto-revert to 'on sale'? | Not currently. Gap: associate status with date/time so it changes without author republish. Presale can be outside business hours.
2 | Events | Deferred | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia | Hide CTA (more info) when there's no landing page / no extra info for user? | Default links to event detail page. Toggle to hide CTA entirely would be gap. | Use case: weekly free entertainment; no detail page.
2 | Events | Deferred | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia | Location reference: limit by user so cafe only adds their location? Avoid choosing wrong location (e.g. Amsterdam for Mexico event). | Location reference drives filter roll-up; root path limits which events show. Wrong location in CF still adds to this site's filter. Restrict by user = gap. | Folder path = organization; location reference = required for display/filter.
2 | Events | Deferred | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia | Default image for event card so author doesn't have to select every time (generic default)? | CF cannot be saved without image. Component-level default (like jobs listing) could be gap. Author can use default from DAM in meantime.
2 | Events | Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia | When adding new event: publish fragment, detail page, and calendar every time? | One event detail page per calendar—publish once. New event: publish CF; calendar page must be published for event to show on publisher (can take a few minutes). | Gonzalo's delay = calendar page publish.
2 | Events | Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia | Why did we lose the filter for events (careers hiring events landing page)? | Careers uses content fragment card (no filter on purpose for homepage). Promotions component has filter; can swap on landing page if desired.
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | Without promotions filter (careers homepage): steps to get card on page = know ID, copy from fragment, paste in component. No other way? | Yes. Content fragment card expects promotion ID for promotions/events. No folder path picker. Gap: enhance card list to include promotions or add path/source picker.
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | Who manages filter options (category, venue, date range)? Author or dev? Can we add different options? | In component code; hardcoded from promotions requirements. New filter = dev. Potential to move to generic list (author-managed) but not available today. Mayte: we manage every filter—gap.
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | Promotion search: same as events—can't select two category folders (e.g. casino + hotel promotions)? | Single path only. Can choose promotions root or e.g. casinos; cannot pick two of four folders. Mayte: another gap.
3 | Careers | Pending | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | Promotions: are filter options (e.g. select category) translatable / overridable for language? | Daniela to check with tech team. Components have language strings; need to confirm what's translatable. At minimum override all areas. Gonzalo: include Transperfect + developer labels. | Technical topic; Scott/technical enablement.
3 | Careers | Pending | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | If we schedule for later and then edit the fragment (e.g. change venue), does it maintain schedule or push live? | Daniela to test (save, manage publication, save); will confirm.
3 | Careers | Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | Promo types (loyalty, slot)—hardcoded? How do we add extra promo types? | In content fragment model (not component). Model editor = more flexibility; permissions apply. Adding dropdown to component = dev. Model edit vs component = different.
3 | Careers | Pending | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | How do we see the promotion card's detail page? Is there a promotion detail template? | No promotion detail template. Create open page, add content, link from CF. Daniela to show casino example from integration env. | Banner image in CF = for when promotion has its own page.
3 | Careers | Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | Video card: external URL—recommended width? Pixel required? What does width affect? | Width affects modal size. Number only, no 'px.' 846 was to match live site. Can change.
3 | Careers | Pending | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | Video card styling (none/black/white): is 'none' transparent? White description not showing. | Daniela to check white; none = default. Black works. Screenshot of three when fixed.
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | Asset specs for video card thumbnail, promotion card/banner—recommended dimensions? Focal point for video thumbnail? | Document on component basis; video thumbnail aspect/specs; no image tab on video card. Gap.
4 | Tagging_Taxonomy_Metadata_Gov | Pending | 2026-02-17 | 2026-02-17 | Andy Lambert | Lisa Cardia | If we restructure tags, does that break anything currently? | Assess first; goal is no hard-coded paths, config where possible. Then SHRSS can make changes. Move tool updates reference paths.
8 | Locations | Answered | 2026-02-23 | 2026-02-23 | Daniela Tea | Lisa Cardia | New location from DPLT: is delivery only—author manually checks? | Yes.
8 | Locations | Answered | 2026-02-23 | 2026-02-23 | Daniela Tea | Lisa Cardia | Image in location CF—where does it populate? Hotels? | Destinations and venues component (e.g. Hard Rock Hotel Cancun). Image specs to Confluence.
8 | Locations | Deferred | 2026-02-23 | 2026-02-23 | Daniela Tea | Lisa Cardia | Add new sort-by or filter field (e.g. meeting room view)? Process? | Update venue CF model, add to component dialog, front-end component update. Mayte: gap—overcomplicated; need optimized way. Lucas: mark as gap.
8 | Locations | Deferred | 2026-02-23 | 2026-02-23 | Daniela Tea | Lisa Cardia | Filters (e.g. type of destination) also hard-coded? Can we add (e.g. Unity participating hotel)? | Same concept—model + component.
9 | Locations_Day_2 | Answered | 2026-02-24 | 2026-02-24 | Kerry Holyoak (SHRSS) / Daniela Tea | Lisa Cardia | Delivery widget: Hard Rock Casino Rockford showing—casino classified as cafe. Who do we contact to fix? | DPLT team (Vipul Patel). Classifications come from DPLT; if misclassified, take to Vipul's team. Lisa to reach out. | Line of business = Cafe in DPLT drives delivery list.
9 | Locations_Day_2 | Answered | 2026-02-24 | 2026-02-24 | Rick Lyon / Daniela Tea | Lisa Cardia | Where do we get destination value (e.g. 59391) for booking widget? Do authors need to know it? | Rick: Senex/Vizergy; in booking links. Migrated; values don't change. Authors may need for restore if someone changes. Daniela: casino booking not finalized (pre-pause).
9 | Locations_Day_2 | Answered | 2026-02-24 | 2026-02-24 | Daniela Tea | Lisa Cardia | Booking widget: adding a different field (e.g. balcony) beyond rooms/adults/children—development? | Yes—new field type, UI, parameter passing, booking engine side. Development for sure.
9 | Locations_Day_2 | Deferred | 2026-02-24 | 2026-02-24 | Daniela Tea | Lisa Cardia | Find a location: can we change the background color? | Currently fixed in code. Change would require code update to allow author-configurable background.
9 | Locations_Day_2 | Answered | 2026-02-24 | 2026-02-24 | Daniela Tea | Lisa Cardia | Google Map: filter map not in config but filters showing—why? No results vs no locations? | Filter map adds filters on map. Different messages for no results vs no locations. Daniela made copy to demo filter map.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Joseph Brondolo (SHRSS) | Job filters (homepage)—where are the four labels (job category label, properties label, etc.) located in configuration? I had a story and couldn't find them. | Daniela to get back—might be in markup not visible to user. Add to list for beginning of tomorrow's session.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Gonzalo Calasich (SHRSS) | When sync runs from Workday, do we delete all job postings from AEM each time? Job no longer active in Workday—removed on next sync? | Folder structure stays; job postings come and go based on Workday. When job removed in Workday, next sync removes it from AEM.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Gonzalo Calasich (SHRSS) | When you select a filter it doesn't append to URL. Can we have deep links so copying URL lands on filtered view? (We need friendly deep links, not weird numbers.) | Daniela to talk to tech team. Use case: property sites link to careers filtered by property/category/region. | Mayte: we don't want every filter combo creating new URL (analytics); we want ability to deep link.
2 | Events | Pending | 2026-02-11 | 2026-02-11 | Daniela Tea / Andy Lambert | Gonzalo Calasich (SHRSS) | View as published shows changes fast but publisher takes too long; new job (CF) not showing on publisher. Can we expedite? | Need more info (cache, etc.). Daniela will monitor during call. Andy investigating failed publish logs; will raise support ticket. | Gonzalo: not showing at all on publisher; likely cache.
3 | Careers | Pending | 2026-02-12 | 2026-02-12 | Andy Lambert / Daniela Tea | Gonzalo Calasich (SHRSS) | Manual job content fragment: create, publish, not showing on jobs page. Other CFs show. Workday sync deletes manual jobs (is not API data) in ~30 min. | Andy: investigating; support ticket. Get all job IDs not excluding manual; email with recommendation coming; tech sync to drill in. | Gonzalo to send example URLs for logs.
8 | Locations | Pending | 2026-02-23 | 2026-02-23 | Daniela Tea | Gonzalo Calasich (SHRSS) | Regions filter on hardrock.com prod not working—Google Map component? | Different component (Google Map). Destination search and filter = this one. Cover Google Map when we get to it.
9 | Locations_Day_2 | Answered | 2026-02-24 | 2026-02-24 | Daniela Tea / Lucas Nelson | Gonzalo Calasich (SHRSS) | Google Map: regions dropdown blank in prod—why? North America first in config but showing last. | Permissions: groups didn't have read on generic list 'regions.' Template Authors given read. Order: ensure regions authored in dialog (first = top); republish page. | ACS Commons on prod. Media session confirmed fix.
10 | Media | Answered | 2026-02-25 | 2026-02-25 | Daniela Tea | Gonzalo Calasich (SHRSS) | Google Map regions dropdown not visible yesterday—resolution? | Generic list 'regions' populates dropdown. User groups lacked read access. Template Authors given read; Gonzalo and Lisa confirmed can see. Permissions topic with Andy next week. | Locations Day 2 follow-up.
10 | Media | Answered | 2026-02-25 | 2026-02-25 | Daniela Tea | Gonzalo Calasich (SHRSS) | North America showing last on prod—publish page again? | View as published to confirm order; then publish. Andy to take a look at prod page.
2 | Events | Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Edwin Aquino | Event detail page hero—standard across all or customizable per page? | Default hero on event detail page; banner image + alt in CF overrides.
2 | Events | Pending | 2026-02-11 | 2026-02-11 | Daniela Tea | Edwin Aquino | Display tag on event cards (21+, free event, phone-free)? | Daniela asked for example; will discuss with technical team. | Edwin to send example.
6 | Shared_Data | Pending | 2026-02-19 | 2026-02-19 | Daniela Tea | Edwin Aquino | Redirect vanity URL checkbox—what does it do? When to use? | Daniela to get back. In this case not needed.
6 | Shared_Data | Answered | 2026-02-19 | 2026-02-19 | Daniela Tea | Edwin Aquino | Content fragment model: default image for new CF? Override by author? | Yes—default value on model; new CFs get it; author can replace. Custom component (e.g. card) would show it.
6 | Shared_Data | Pending | 2026-02-19 | 2026-02-19 | Daniela Tea | Edwin Aquino | Experience fragment variation: break connection to reorder or use as regular component? | Daniela to confirm.
7 | News | Pending | 2026-02-20 | 2026-02-20 | Daniela Tea | Edwin Aquino | List component: exclude certain tags (e.g. do not use) from list? | Not OOTB; matching only. Daniela to take use case back (e.g. promotion page not on landing).
7 | News | Answered | 2026-02-20 | 2026-02-20 | Daniela Tea | Edwin Aquino | List: what dictates which items appear in which column? Order? | Order by title or last modified. Column count in config; fills in order.
7 | News | Pending | 2026-02-20 | 2026-02-20 | Daniela Tea | Edwin Aquino | Logo styling (image icon in footer)—what is it? Use case? | Daniela to check JIRA; not footer-specific; image component in general (e.g. height/width for multi-logo pages).
7 | News | Deferred | 2026-02-20 | 2026-02-20 | Daniela Tea | Edwin Aquino | News: default image by category/tag (e.g. casino vs hotel)? | Not currently. Gap; need requirements (multiple tags = which default?).
9 | Locations_Day_2 | Answered | 2026-02-24 | 2026-02-24 | Daniela Tea | Edwin Aquino | What path do we choose for CF list path (category listing)? Not intuitive; can we update info tools? | Path = parent; component shows children of that parent. E.g. path to EN under news → year folders. Daniela demonstrated; Edwin confirmed. | News session follow-up.
10 | Media | Deferred | 2026-02-25 | 2026-02-25 | Daniela Tea | Edwin Aquino | Image gallery grid: option to show/hide title or inherit from asset like alt text? | Not for this component. Title pulled from DAM metadata. If no title in metadata, 'no title' shows. Enhancement to capture if team wants option to not display title.
10 | Media | Deferred | 2026-02-25 | 2026-02-25 | Daniela Tea | Edwin Aquino | Image gallery grid: different titles for same image per property/site? | Not currently. Control via metadata per asset; no variation/title override in component.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Don Middlebrook | For the image in the component—where does it come from? If we move the asset in DAM, do we lose the reference? | Image comes from DAM. If asset moved or renamed, reference should update; if deleted, would break. Daniela to confirm.
3 | Careers | Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Don Middlebrook | Card/promotion image: 16:9 asset—how to control focal point (e.g. center guitar)? Image position? | Image position tab on image components (desktop/tablet/mobile). List (promotion search) has no per-row position; crop outside or use rendition—DAM/gap. | Don: one source image across placements; figure out with DAM/renditions.
4 | Tagging_Taxonomy_Metadata_Gov | Pending | 2026-02-17 | 2026-02-17 | Andy Lambert | Don Middlebrook | Why multiple category directories (categories, category, news categories, events categories)? Consolidate under one? | Different purposes; naming could be clearer. Andy to assess functional implications of consolidation, then green-light. Add as to-do for cleanup. | Don: same for property/hotel/casino/cafe under locations.
4 | Tagging_Taxonomy_Metadata_Gov | Pending | 2026-02-17 | 2026-02-17 | Andy Lambert | Don Middlebrook | How do we use generic lists (ACS Commons path-to-tag mapping)? What are they used for? | Governs tags for a section. Andy to add to Confluence Q&A; Vinay for deeper answer. Not used for corporate/careers today.
4 | Tagging_Taxonomy_Metadata_Gov | Deferred | 2026-02-17 | 2026-02-17 | Andy Lambert | Don Middlebrook | Content fragment model category field—tag-driven or defined in model? Where do these lists come from? | Can be tag-driven or enumeration. Locations example = not all from tags. Depends on use case; gap to align. Check model.
4 | Tagging_Taxonomy_Metadata_Gov | Pending | 2026-02-17 | 2026-02-17 | Andy Lambert | Don Middlebrook | Asset categories vs content fragment categories—different? Event categories on asset vs events. | Yes—asset metadata vs CF categories; confusing. Asset event categories ≠ CF event categories. Action: cleanup, rename for clarity. | Lisa: location reference ID same issue (events session).
4 | Tagging_Taxonomy_Metadata_Gov | Deferred | 2026-02-17 | 2026-02-17 | Andy Lambert | Don Middlebrook | Pre-populated metadata set for export (so we don't add 15 properties every time)? | Not OOTB. Andy: pain; keep text file with property names, copy/paste. Chris may say same tomorrow.
5 | DAM_Training_Usage_Admin | Answered | 2026-02-18 | 2026-02-18 | Andy Lambert | Don Middlebrook | SHRSS primary: consolidate into SHRSS, deprecate primary? Path forward. | Yes. Don to move primary content into SHRSS; deprecate primary. Content fragment behavior may need back-end look. | Don: 13 months ago didn't know move wouldn't break refs.
5 | DAM_Training_Usage_Admin | Pending | 2026-02-18 | 2026-02-18 | Andy Lambert | Don Middlebrook | Renditions: Don tried to create, they're not applying. | Andy: renditions in agenda; will cover. Hot topic.
8 | Locations | Answered | 2026-02-23 | 2026-02-23 | Daniela Tea | Don Middlebrook | Location CF title = location ID; how to bulk update to property legal name? | Bulk metadata update: take value from property legal name (or chosen field), replace title. Daniela: tech KT if help needed. | Read-only fields from DPLT; title editable.
6 | Shared_Data | Deferred | 2026-02-19 | 2026-02-19 | Daniela Tea | Daniela Tea (update) | Card carousel tablet field removed—why? Can we have tablet-specific again? | Requirement: desktop/tablet same, mobile separate. Tablet always 2 for non–full width; field had no effect. Removed. Gap if tablet config needed.
7 | News | Answered | 2026-02-20 | 2026-02-20 | Daniela Tea | Daniela Tea (update) | Redirect vanity URL checkbox: 302 redirect; when to use? | Documentation: 302 when checkbox. Daniela to share link; technical enablement for redirect management.
10 | Media | Answered | 2026-02-25 | 2026-02-25 | Don Middlebrook / Daniela Tea | Daniela Tea (to Don) | Image gallery grid: are we adding titles/descriptions to assets? | Don: planning to add as much metadata as possible—titles, description. Daniela: if titles not always desired, capture enhancement to not display or use description.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Charles Baugh (SHRSS) | How is the sequence/order of job results determined? How would we reorder? | Sort filter on component: most recent (default), job title, location. Hot jobs always stay at top; rest sort among themselves.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Charles Baugh (SHRSS) | Best way to take down 3 jobs and reschedule for later—resubmit through Workday with 10 and purge, or purge in AEM, or reschedule manually in AEM? | Workday is source of truth; AEM changes get overwritten by sync. Daniela to check with tech team if there's an author-side way to handle; answer tomorrow.
7 | News | Answered | 2026-02-20 | 2026-02-20 | Daniela Tea | Carlos Aldana | News CF: default image in model? Carlos: all articles have image. | Default image at component level (news search results) for items without image. Model default can be added.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Angelika Akopyan (SHRSS) | Is there an option to run the Workday sync on demand? | Daniela to check. May be running more frequently than 30 min (e.g. 5 min); will confirm and ask about on-demand.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Angelika Akopyan (SHRSS) | Production sync—how long will the period be (5 min or 30)? With ~800 jobs, how long does full sync take? | Daniela to check with team.
5 | DAM_Training_Usage_Admin | Answered | 2026-02-18 | 2026-02-18 | Andy Lambert / Chris Lewis | Andy Lambert | Legacy/migrated assets folder—option to move old content there, new structure for new? | Yes—e.g. legacy-assets; new content in new structure; cleanup/scripting later. Chris agreed.
5 | DAM_Training_Usage_Admin | Answered | 2026-02-18 | 2026-02-18 | Chris Lewis | Andy Lambert | Language folders for assets—required for translation automation? | Chris: language at top level for AM Guide etc. If no language-swap use case, metadata for language is fine. Don: single asset, metadata.

## Jobs
Session # | Session | Status | Date Asked | Answered On | Answered By | Asked By | Question/Comment | Answer | Notes
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | You have two IDs—job unique ID and job ID. Which one are you using? (Displayed one is wrong.) | Right now both come from Workday; what's displayed to end user is job ID. Ticket exists for this; dev team looking at it. | Mayte said 'that's the wrong one'—job ID vs job unique ID; fix via ticket.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Image field—not mapped to pick up automatically the right image like we currently have? | Image is author-input; image configuration page allows setting images per property; author can overwrite or remove.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | Does the image override replace the image on the card and the listing or just the card? | Override updates image in both job listings component (cards) and job search component (horizontal cards). | Lisa noted they typically use logo on listings, property shot on homepage/hiring events.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | If we override something in the CF, does the sync overwrite it or do we keep the override? | Only Workday fields get overwritten. Image, is hot job, and LD JSON are author-only and do not get overwritten by sync.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Ramona Harris | What is the standard size for the logo image that should be uploaded? | Still need to get back—used whatever was in DAM for Sage site; don't have exact measurements yet.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | How do you create a new job as an author (not from Workday)? | Create → Content Fragment → select Jobs; fill out all fields. Categories are not dropdowns—must match exact value (e.g. casino sales).
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Is there scheduling when adding a job—as soon as you publish it goes live? | Content fragments can be scheduled; Workday jobs get published automatically on sync without author intervention.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Manual jobs—they drop off based on Workday; if manual, we have to manually delete? | Correct.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Gonzalo Calasich (SHRSS) | When sync runs from Workday, do we delete all job postings from AEM each time? Job no longer active in Workday—removed on next sync? | Folder structure stays; job postings come and go based on Workday. When job removed in Workday, next sync removes it from AEM.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Do we have an option to immediately hide a job from the website without Workday removing it? (e.g. weekend, can't get hold of anyone.) | Author could delete but sync would republish. No current way to just hide. Daniela to check with dev team if turning off 'is API data' could freeze sync for that job. | Edge case but has happened; need business continuity.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | Which fields do not get overridden when sync happens? (You said three.) | Image, is hot job, and LD JSON. Only those three are author-only.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Ramona Harris | Select locations in job search—are those pulling from AEM? New property—is author responsible for adding so it appears in filter? | Locations come from content fragment (country, state, city). New property/jobs from Workday create folder structure automatically; author does not add. | Ramona had not seen Ottawa in AEM—clarified it's from CF data.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Don Middlebrook | For the image in the component—where does it come from? If we move the asset in DAM, do we lose the reference? | Image comes from DAM. If asset moved or renamed, reference should update; if deleted, would break. Daniela to confirm.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Charles Baugh (SHRSS) | How is the sequence/order of job results determined? How would we reorder? | Sort filter on component: most recent (default), job title, location. Hot jobs always stay at top; rest sort among themselves.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | When clicking a job card—what data do we send to Tealium data layer? Do we have unique IDs per card for tracking? | Daniela to check with tech team. Content fragments have unique IDs; need to confirm what is passed to data layer. | Mayte: need unique IDs per card, not just friendly link.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Angelika Akopyan (SHRSS) | Is there an option to run the Workday sync on demand? | Daniela to check. May be running more frequently than 30 min (e.g. 5 min); will confirm and ask about on-demand.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Angelika Akopyan (SHRSS) | Production sync—how long will the period be (5 min or 30)? With ~800 jobs, how long does full sync take? | Daniela to check with team.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Gonzalo Calasich (SHRSS) | When you select a filter it doesn't append to URL. Can we have deep links so copying URL lands on filtered view? (We need friendly deep links, not weird numbers.) | Daniela to talk to tech team. Use case: property sites link to careers filtered by property/category/region. | Mayte: we don't want every filter combo creating new URL (analytics); we want ability to deep link.
1 | Jobs | Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | If sync goes wrong and can't display data—do we have an error message or just blank? | No jobs in AEM shows 'no jobs found.' Separate error message for sync failure (vs no results) is a gap—note for gap analysis. | Mayte: had blank page when testing iSense; want custom message for business continuity.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | For a new careers page—what template should we use? | Open page template for all these pages (header/footer + content area).
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | When you select filters, do they update each other (conditional/dependent filters)? | Yes—e.g. selecting property updates other filter options; unchecking brings categories back.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Job listings—does it only go by state (e.g. Florida) or can we select properties? Can we do multiple properties? | Can select one folder (e.g. Orlando or Florida). You can only select ONE root path, not multiple properties. To show Coco + Classic + Hollywood would require multiple components one after another; can't sort across them. | Mayte: our use case is three South Florida properties; noted as gap.
1 | Jobs | Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | If we have fewer than three cards (e.g. one or two), is there a way to center them instead of left align? | Not currently. Would need to discuss in gap portion—centered vs same width vs full width. | Lisa: hot jobs vs hiring events cards all display differently; consistency concern.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | Apply Now button—what is its purpose if the URL always comes from the content fragment? | Button text is configurable in component; the URL/destination is from the content fragment.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | For hot jobs can we have the root path higher so it's all hot jobs, not specific to one location? | Yes—set root path higher in hierarchy to get all hot jobs across locations.
1 | Jobs | Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | If there are no hot jobs—does the component hide, or show blank with a message? | Currently shows section title with no cards and no message. Does not hide. Angelika confirmed; Mayte/Lisa want hide or message—gap. | JIRA ticket exists for this.
1 | Jobs | Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | Hot jobs we use property image; in listings we use logo. Same job in hot jobs vs listing—we want different images. | Noted. Daniela confirmed understanding—hot job might have property image, same job in search shows logo. Gap for implementation.
1 | Jobs | Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Why do we have to configure the search page in Job Filters? We only have one search page. Can it be defaulted? | Currently pointing to correct page. If component used elsewhere, author can change. Defaulting is possible; Mayte wants one step less for authors. Log as gap.
1 | Jobs | Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Job category cards—how do we change/pick which categories to display? (e.g. don't want food and beverage, want to promote others.) | Currently cannot pick and choose categories; shows all or by sort (most jobs / alphabetical). Not in component. | Mayte: we had ability in past; this component may be deprecated.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | What is 'job property' in the image config? Is it a specific name we need to match (e.g. Workday name)? | It's the value from the job property field in the content fragment. Config matches that value to assign the image. Must match exactly.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea / Lucas Nelson | Mayte Eme | Are all locations in the image config? We have over 500 locations; the list doesn't seem long. | Initial setup by Adobe tech team; list may not be complete. Need full list—Lucas to follow up with Vinay; Scott to task IT to get list from Workday and map ahead of time. | Lisa: mapping has to be manually added in AEM; Workday doesn't push it.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | If Workday changes internal name (e.g. HRC Washington DC to Hard Rock Cafe Washington DC), does that break the mapping? | New entry would need to be added in config with the new property value and desired logo. Old name would no longer match. | Mayte: mapping is very manual; concern for 500+ locations.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Who does the mapping and who gets every location name when we go to production? | Adobe did initial setup. Who adds new properties or changes logos unclear; need to understand source of full list. | Scott to ask Vinay; Lisa: whoever handed off first time.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | Hot jobs page and hiring events page—do we have to add hot jobs manually to every location or does it pull from same feed? | Same component (job listings, hot jobs). Toggle hot job in CF once; appears on homepage and hot jobs page. Hiring events = different content fragment (events session).
1 | Jobs | Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | On the hot jobs page—where is the filtering and searching? | Filtering is not currently part of the component; open ticket, gap in JIRA.
1 | Jobs | Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | Hiring events cards vs hot jobs—different widths/heights; not consistent. | Different content fragments; will cover events tomorrow. Noted inconsistency.
1 | Jobs | Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Queries for bringing in different content by property (like Sitecore scopes)—will we go through that? | Daniela asked for examples. Angelika showed brands/cafes/casinos—same cards on multiple pages. Experience Fragment approach can give single update; exclusion logic (e.g. don't show current page's card) would need custom logic. | Lisa: need logic so on Casinos page we don't show Casinos card (show children excluding current).
1 | Jobs | Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | Shared cards—when on casino page, don't show casino card (show all children excluding current page). Experience fragment gets us reuse; we need that exclusion logic. | Experience fragment = update once. Current implementation is local per page so exclusion was possible. To get both reuse and exclusion would need custom component. Decision for Hard Rock. | Mayte: should have been set up properly; task for Mohsin.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Charles Baugh (SHRSS) | Best way to take down 3 jobs and reschedule for later—resubmit through Workday with 10 and purge, or purge in AEM, or reschedule manually in AEM? | Workday is source of truth; AEM changes get overwritten by sync. Daniela to check with tech team if there's an author-side way to handle; answer tomorrow.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Joseph Brondolo (SHRSS) | Job filters (homepage)—where are the four labels (job category label, properties label, etc.) located in configuration? I had a story and couldn't find them. | Daniela to get back—might be in markup not visible to user. Add to list for beginning of tomorrow's session.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Daniela Tea / Lucas Nelson | Mayte Eme | Did we ask for specs for the job/logo images so we don't have corrupt or huge logos? Who fixes those before go-live? | Spec sheet not yet detailed. Lucas: Daniela to talk with Vinay and authoring support.
1 | Jobs | Pending | 2026-02-10 | 2026-02-10 | Lucas Nelson / Scott Sorel | Mayte Eme | Pagination—recommendation for max number of jobs per page? We have ~800 jobs; have you tested performance? | Lucas: Adobe doesn't have performance testing resource. Scott: take back to TJ/Mohsin. Mayte: had issues before with 50; want an answer.
1 | Jobs | Pending | 2026-02-10 |  |  | Product Director | Governance: Who owns ongoing maintenance of job property–to–image mapping (Adobe, IT, or SHRSS)? What process for new properties or Workday name changes? |  | Governance and roles.
1 | Jobs | Pending | 2026-02-10 |  |  | Product Director | Authoring: Can we get a short checklist or decision tree for authors (which component when; what authors can edit vs what sync overwrites)? |  | Authoring clarity.
1 | Jobs | Pending | 2026-02-10 |  |  | Product Director | Tagging/metadata: Besides Hot Job and image, what other author-controlled metadata affects display or filtering? Who governs allowed values for categories (Workday vs author-created)? |  | Tagging and governance.
1 | Jobs | Pending | 2026-02-10 |  |  | Product Director | Gap analysis: Which of today's gaps are in scope for careers go-live (e.g. job ID, deep links, hot jobs empty state, image specs) vs deferred to post–gap analysis? |  | Priorities for go-live.
1 | Jobs | Pending | 2026-02-10 |  |  | Product Director | Permissions: Who can access Job Image configuration (ACS AEM Commons)? Admin-only or can we assign a careers/DAM role? |  | Governance and permissions.

## Events
Session # | Session | Status | Date Asked | Answered On | Answered By | Asked By | Question/Comment | Answer | Notes
2 | Events | Pending | 2026-02-11 | 2026-02-11 | Daniela Tea / Andy Lambert | Gonzalo Calasich (SHRSS) | View as published shows changes fast but publisher takes too long; new job (CF) not showing on publisher. Can we expedite? | Need more info (cache, etc.). Daniela will monitor during call. Andy investigating failed publish logs; will raise support ticket. | Gonzalo: not showing at all on publisher; likely cache.
2 | Events | Deferred | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia | Override for date field (e.g. 'every Wednesday through February') instead of actual date/time? | Not in event content fragment. Promotions has date override; can confirm if same behavior wanted for events—gap. | Same question for location override.
2 | Events | Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia | What happens if we add an additional image in the event image field (multi)? | Believes it defaults to first one; can test. Migration used only one image.
2 | Events | Deferred | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia | Event status: logic so presale dates show presale disclaimer then auto-revert to 'on sale'? | Not currently. Gap: associate status with date/time so it changes without author republish. Presale can be outside business hours.
2 | Events | Deferred | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia | Hide CTA (more info) when there's no landing page / no extra info for user? | Default links to event detail page. Toggle to hide CTA entirely would be gap. | Use case: weekly free entertainment; no detail page.
2 | Events | Deferred | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia | Location reference: limit by user so cafe only adds their location? Avoid choosing wrong location (e.g. Amsterdam for Mexico event). | Location reference drives filter roll-up; root path limits which events show. Wrong location in CF still adds to this site's filter. Restrict by user = gap. | Folder path = organization; location reference = required for display/filter.
2 | Events | Deferred | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia | Default image for event card so author doesn't have to select every time (generic default)? | CF cannot be saved without image. Component-level default (like jobs listing) could be gap. Author can use default from DAM in meantime.
2 | Events | Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Mayte Eme | Event detail page—why does it look like a card? Are we on careers? Hard Rock Live—can we use for careers? | This is the event detail page (one template). Same for all sites. Daniela created new page to show from scratch. | Mayte: digital page not working for careers events.
2 | Events | Deferred | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia / Mayte Eme | Clean/friendly URL for event detail (property.com/artist-name not numbers)? | Event ID is read-only to prevent duplicates. Enhancement = make editable for friendly URL. Mayte: need real names; like WordPress/Sitecore—pick up page name. Gap. | Labor intensive; add to gap list.
2 | Events | Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Edwin Aquino | Event detail page hero—standard across all or customizable per page? | Default hero on event detail page; banner image + alt in CF overrides.
2 | Events | Deferred | 2026-02-11 | 2026-02-11 | Daniela Tea | Mayte Eme | Event statuses: all manual or can we schedule (presale, announcement, rescheduled)? Do they drive/hide content? | Currently manual. Gap to have date range per status. Presale/sold out etc. change label/flag; event status message is separate. Doesn't hide CTA or content.
2 | Events | Pending | 2026-02-11 | 2026-02-11 | Daniela Tea / Andy Lambert | Lisa Cardia / Mayte Eme | Do we have to publish to see changes? How to preview before publish for approval? | View as published doesn't show CF changes until CF is published. Andy: preview tier exists, not configured; will check export. Mayte: need browser preview to screenshot for approval. | Preview server / preview links = gap analysis.
2 | Events | Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia | When adding new event: publish fragment, detail page, and calendar every time? | One event detail page per calendar—publish once. New event: publish CF; calendar page must be published for event to show on publisher (can take a few minutes). | Gonzalo's delay = calendar page publish.
2 | Events | Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia / Mayte Eme | Unpublish event (take down without delete) to repurpose later? | Unpublish CF removes from calendar. Daniela to check if detail URL still accessible. Later: unpublished = detail URL shows configured 'no events' message; content not visible. | Mayte: add as gap—not expected behavior but at least user doesn't see it.
2 | Events | Answered | 2026-02-11 | 2026-02-11 | Mayte Eme / Daniela Tea | Mayte Eme | Recap: unpublish works; schedule not local to property; end date auto drop-off; all statuses manual; no date/location override; three times instead of one (vs Sitecore). | Daniela acknowledged. Hiring events use promotions model (has overrides); events model does not.
2 | Events | Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Mayte Eme / Gonzalo | Hiring events—using promotions not events? What can events CF do vs promotions? | Hiring events section uses promotions content fragment (date/location override). Events CF + calendar/detail = what we covered. Tomorrow: hiring events component. | Careers not using events CF for that section.
2 | Events | Deferred | 2026-02-11 | 2026-02-11 | Daniela Tea | Mayte Eme | Can we choose mix-and-match locations for one calendar (e.g. six properties, or hotel+casinos, or by venue)? | No. One content fragment folder path only; cannot select multiple folders. Big gap for multi-venue/entertainment sites.
2 | Events | Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Mayte Eme | Pull events into other pages (venue page, homepage by category, e.g. dinner and a show)? | Content Fragment card list component can show events (or news); by root path or by tag (e.g. dinner and a show). Not locked to calendar component.
2 | Events | Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia | Why did we lose the filter for events (careers hiring events landing page)? | Careers uses content fragment card (no filter on purpose for homepage). Promotions component has filter; can swap on landing page if desired.
2 | Events | Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Mayte Eme | Can we pull jobs (hot jobs/hiring events) to property page (e.g. Reverb) by tag or location? | Yes—select root path (e.g. Tampa folder); all jobs under that path. Cannot select multiple locations in one component. Exclude category under Tampa? Not in component.
2 | Events | Pending | 2026-02-11 | 2026-02-11 | Daniela Tea | Edwin Aquino | Display tag on event cards (21+, free event, phone-free)? | Daniela asked for example; will discuss with technical team. | Edwin to send example.
2 | Events | Pending | 2026-02-11 | 2026-02-11 | Daniela Tea | Rick Lyon (Director of Digital Experience) | Preview link for unpublished page to share for approval before republish? | Unpublished CF not on calendar or detail. If publish CF, visible in author; page must be published for end user. Daniela to report back on detail-page behavior. | Preview before publish = gap.
2 | Events | Pending | 2026-02-11 | 2026-02-11 | Andy Lambert | Lucas Nelson | Publish delays on stage—investigating? | Andy: seen failed publish entries in cloud services log; raising support ticket; will keep team posted.
2 | Events | Pending | 2026-02-11 |  |  | Product Director | Governance: Who owns Event Categories tags and DPLT location list? Process when property/venue added or renamed?
2 | Events | Pending | 2026-02-11 |  |  | Product Director | Authoring: One-page checklist for event authoring (what to create, publish, order) and when to use events CF vs promotions CF?
2 | Events | Pending | 2026-02-11 |  |  | Product Director | Tagging: Event categories vs tags for filtering vs 'dinner and a show' query—who governs? |  | Categories = filter; tags = internal; tag for query possible.
2 | Events | Pending | 2026-02-11 |  |  | Product Director | Gap analysis: Decision criteria for events CF vs promotions CF; which gaps apply to which model?
2 | Events | Pending | 2026-02-11 |  |  | Product Director | Permissions: Who can create/edit Event Categories tags and DPLT location reference options?

## Careers
Session # | Session | Status | Date Asked | Answered On | Answered By | Asked By | Question/Comment | Answer | Notes
3 | Careers | Pending | 2026-02-12 | 2026-02-12 | Andy Lambert / Daniela Tea | Gonzalo Calasich (SHRSS) | Manual job content fragment: create, publish, not showing on jobs page. Other CFs show. Workday sync deletes manual jobs (is not API data) in ~30 min. | Andy: investigating; support ticket. Get all job IDs not excluding manual; email with recommendation coming; tech sync to drill in. | Gonzalo to send example URLs for logs.
3 | Careers | Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia / Mayte Eme | Promotion ID—where from? What do we put? Is it made up? Required for targeting/analytics we had for casino, not unique ID for display. | Author-entered unique identifier to display one promotion (e.g. content fragment card). No format requirement. Uniqueness validated on save. Same value in another CF blocks save. | Mayte: gap—we don't want this; need to remember/copy; not smart (dropdown of existing IDs).
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | When pasting ID elsewhere (e.g. component), is there a dropdown to select from existing or must we remember/paste? | Component field is plain text; no dropdown. Must copy from CF. Gonzalo: gap = source field to navigate DAM and pick CF.
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | Without promotions filter (careers homepage): steps to get card on page = know ID, copy from fragment, paste in component. No other way? | Yes. Content fragment card expects promotion ID for promotions/events. No folder path picker. Gap: enhance card list to include promotions or add path/source picker.
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea / Lucas Nelson | Mayte Eme | Promotion ID for casino or careers? We're not using for casinos; we need to fix for casinos (many users, can't remember IDs). | Initially for casinos. Careers using it for hiring events. Lucas: capture what it doesn't have; disposition in platform expansion; modify/change is part of it.
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Promotion search: can we remove the search field and keep only filters? | Search cannot be removed currently. With filters, search bar always shows. To display as list without filter/search = gap.
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | If we use promotions for hiring events we can't have promotion cards in grid/carousel elsewhere without filter+search—only one-by-one by ID. | Correct. Content fragment card list currently events/news only; gap = add promotions so list/carousel without filter+search.
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | Who manages filter options (category, venue, date range)? Author or dev? Can we add different options? | In component code; hardcoded from promotions requirements. New filter = dev. Potential to move to generic list (author-managed) but not available today. Mayte: we manage every filter—gap.
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | Promotion search: same as events—can't select two category folders (e.g. casino + hotel promotions)? | Single path only. Can choose promotions root or e.g. casinos; cannot pick two of four folders. Mayte: another gap.
3 | Careers | Pending | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | Promotions: are filter options (e.g. select category) translatable / overridable for language? | Daniela to check with tech team. Components have language strings; need to confirm what's translatable. At minimum override all areas. Gonzalo: include Transperfect + developer labels. | Technical topic; Scott/technical enablement.
3 | Careers | Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Transperfect: manual translations for some languages; not always Transperfect. OK? | Noted. Daniela will address in Transperfect KT.
3 | Careers | Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Promotion start/end date and time—is that for scheduling or display only? | Display only. Schedule = Manage Publication > Now or Later (activation date). Not for 'display this event on Saturday but publish tomorrow.'
3 | Careers | Pending | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | If we schedule for later and then edit the fragment (e.g. change venue), does it maintain schedule or push live? | Daniela to test (save, manage publication, save); will confirm.
3 | Careers | Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | Promo types (loyalty, slot)—hardcoded? How do we add extra promo types? | In content fragment model (not component). Model editor = more flexibility; permissions apply. Adding dropdown to component = dev. Model edit vs component = different.
3 | Careers | Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Don Middlebrook | Card/promotion image: 16:9 asset—how to control focal point (e.g. center guitar)? Image position? | Image position tab on image components (desktop/tablet/mobile). List (promotion search) has no per-row position; crop outside or use rendition—DAM/gap. | Don: one source image across placements; figure out with DAM/renditions.
3 | Careers | Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Job listings on another site (e.g. hotel)—same component, theme changes styling? Can we choose multiple locations? | Yes—component is global; theme drives look. Still one root path only (gap). Use case: Tampa/Hollywood dedicated job pages.
3 | Careers | Pending | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | How do we see the promotion card's detail page? Is there a promotion detail template? | No promotion detail template. Create open page, add content, link from CF. Daniela to show casino example from integration env. | Banner image in CF = for when promotion has its own page.
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Events template allows link to another page (event detail). Promotions can't do that—we have hot jobs/dealer university with detail pages. | Promotions: can link to any page from CF. Events: one detail page + ID. Override in events = gap; then could use events for hiring events. Workaround: link to existing page from promotion CF.
3 | Careers | Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | Video card: external URL—recommended width? Pixel required? What does width affect? | Width affects modal size. Number only, no 'px.' 846 was to match live site. Can change.
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia / Mayte Eme | Video card: third party (YouTube) gives fixed/responsive, aspect ratio; external URL doesn't. Same config for external? | External URL = no those options. Third party = full config. Gap—external should have same controls; else only use YouTube/Vimeo. Mayte: don't use external until fixed.
3 | Careers | Pending | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | Video card styling (none/black/white): is 'none' transparent? White description not showing. | Daniela to check white; none = default. Black works. Screenshot of three when fixed.
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Video card: if we add a fourth, does it become carousel automatically (like Sitecore)? | No. Video card not in allowed components for card carousel or hero carousel. Gap: allow video cards in carousel.
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Card (icon variation): with 6 or 9 cards, does it go 3 to 1 columns automatically or manual per breakpoint? | Manual per viewport for standalone card. Some components (e.g. carousel) have breakpoint config. Mayte: add to gap list.
3 | Careers | Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Executives/diversity page (careers) same as hardrock.com—shared so one update? | Currently separate cards. Can move to experience fragment: update once, same styling both sites. Content fragment = same content, different styling per site. | Rick: corporate page hardrock.com.
3 | Careers | Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Experience fragment: same content, different styling per site possible? | Experience fragment = same content + same look. For same content, different look = content fragment.
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | Asset specs for video card thumbnail, promotion card/banner—recommended dimensions? Focal point for video thumbnail? | Document on component basis; video thumbnail aspect/specs; no image tab on video card. Gap.
3 | Careers | Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia / Mayte Eme | Store component on page but not displayed (like Sitecore disable)—reuse later without recreating? Hide = still in DOM? | Hide component (layout > eye) = still in tree, still in DOM/crawled. Not like Sitecore where disabled = not in HTML. Gap: store without rendering for evergreen swap. | Content refresh initiative; rotate temp vs evergreen.
3 | Careers | Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Careers locations page same as brand—pulling from DPLT? Can we copy accordion/component so one source? | Careers = accordion/text (migrated); brand = map component + DPLT. Can copy map component to careers. Intent: all location listings from DPLT, one maintenance. | Daniela to post test page with copied component.
3 | Careers | Pending | 2026-02-12 |  |  | Product Director | Governance: Who owns promotion ID list and filter options? Process to add/change?
3 | Careers | Pending | 2026-02-12 |  |  | Product Director | Authoring: Single checklist for hiring events (CF → card vs search → detail page → publish order) and when events vs promotions?
3 | Careers | Pending | 2026-02-12 |  |  | Product Director | Tagging: Do promotions use tags for filtering? If card list adds promotions, tag-based selection?
3 | Careers | Pending | 2026-02-12 |  |  | Product Director | Gap priorities: Which items (ID vs path, filter removal, card list promotions, video carousel, thumbnail specs, hide vs disable) for careers vs platform expansion?
3 | Careers | Pending | 2026-02-12 |  |  | Product Director | Permissions: Who can edit promotions model (promo types) and promotion search config (filter labels)?

## Tagging_Taxonomy_Metadata_Gov
Session # | Session | Status | Date Asked | Answered On | Answered By | Asked By | Question/Comment | Answer | Notes
4 | Tagging_Taxonomy_Metadata_Gov | Pending | 2026-02-17 | 2026-02-17 | Andy Lambert | Don Middlebrook | Why multiple category directories (categories, category, news categories, events categories)? Consolidate under one? | Different purposes; naming could be clearer. Andy to assess functional implications of consolidation, then green-light. Add as to-do for cleanup. | Don: same for property/hotel/casino/cafe under locations.
4 | Tagging_Taxonomy_Metadata_Gov | Pending | 2026-02-17 | 2026-02-17 | Andy Lambert | Lisa Cardia | If we restructure tags, does that break anything currently? | Assess first; goal is no hard-coded paths, config where possible. Then SHRSS can make changes. Move tool updates reference paths.
4 | Tagging_Taxonomy_Metadata_Gov | Pending | 2026-02-17 | 2026-02-17 | Andy Lambert | Don Middlebrook | How do we use generic lists (ACS Commons path-to-tag mapping)? What are they used for? | Governs tags for a section. Andy to add to Confluence Q&A; Vinay for deeper answer. Not used for corporate/careers today.
4 | Tagging_Taxonomy_Metadata_Gov | Deferred | 2026-02-17 | 2026-02-17 | Andy Lambert | Don Middlebrook | Content fragment model category field—tag-driven or defined in model? Where do these lists come from? | Can be tag-driven or enumeration. Locations example = not all from tags. Depends on use case; gap to align. Check model.
4 | Tagging_Taxonomy_Metadata_Gov | Pending | 2026-02-17 | 2026-02-17 | Andy Lambert | Don Middlebrook | Asset categories vs content fragment categories—different? Event categories on asset vs events. | Yes—asset metadata vs CF categories; confusing. Asset event categories ≠ CF event categories. Action: cleanup, rename for clarity. | Lisa: location reference ID same issue (events session).
4 | Tagging_Taxonomy_Metadata_Gov | Deferred | 2026-02-17 | 2026-02-17 | Andy Lambert | Don Middlebrook | Pre-populated metadata set for export (so we don't add 15 properties every time)? | Not OOTB. Andy: pain; keep text file with property names, copy/paste. Chris may say same tomorrow.
4 | Tagging_Taxonomy_Metadata_Gov | Pending | 2026-02-17 |  |  | Product Director | Governance: Who owns SHRSS tag vocabulary and consolidation decision? Process to add namespace?
4 | Tagging_Taxonomy_Metadata_Gov | Pending | 2026-02-17 |  |  | Product Director | Authoring: Where do authors see tag-driven vs fixed list? One-pager by model/asset type?
4 | Tagging_Taxonomy_Metadata_Gov | Pending | 2026-02-17 |  |  | Product Director | Permissions: Which groups have create/update/delete on SHRSS tags?

## DAM_Training_Usage_Admin
Session # | Session | Status | Date Asked | Answered On | Answered By | Asked By | Question/Comment | Answer | Notes
5 | DAM_Training_Usage_Admin | Answered | 2026-02-18 | 2026-02-18 | Andy Lambert | Don Middlebrook | SHRSS primary: consolidate into SHRSS, deprecate primary? Path forward. | Yes. Don to move primary content into SHRSS; deprecate primary. Content fragment behavior may need back-end look. | Don: 13 months ago didn't know move wouldn't break refs.
5 | DAM_Training_Usage_Admin | Answered | 2026-02-18 | 2026-02-18 | Andy Lambert / Chris Lewis | Andy Lambert | Legacy/migrated assets folder—option to move old content there, new structure for new? | Yes—e.g. legacy-assets; new content in new structure; cleanup/scripting later. Chris agreed.
5 | DAM_Training_Usage_Admin | Answered | 2026-02-18 | 2026-02-18 | Chris Lewis | Andy Lambert | Language folders for assets—required for translation automation? | Chris: language at top level for AM Guide etc. If no language-swap use case, metadata for language is fine. Don: single asset, metadata.
5 | DAM_Training_Usage_Admin | Pending | 2026-02-18 | 2026-02-18 | Andy Lambert | Don Middlebrook | Renditions: Don tried to create, they're not applying. | Andy: renditions in agenda; will cover. Hot topic.
5 | DAM_Training_Usage_Admin | Answered | 2026-02-18 | 2026-02-18 | Chris Lewis | Lisa Cardia / Don Middlebrook | Careers asset names odd (C2D5 etc.)—not from Sitecore. Bulk rename? | Chris: migration tool internal ref. Bulk rename via export metadata to Excel, edit names, re-upload.
5 | DAM_Training_Usage_Admin | Pending | 2026-02-18 |  |  | Product Director | Governance: Who approves DAM folder structure and bulk renames?
5 | DAM_Training_Usage_Admin | Pending | 2026-02-18 |  |  | Product Director | Rendition profiles not applying—root cause and fix in scope?

## Shared_Data
Session # | Session | Status | Date Asked | Answered On | Answered By | Asked By | Question/Comment | Answer | Notes
6 | Shared_Data | Pending | 2026-02-19 | 2026-02-19 | Daniela Tea | Edwin Aquino | Redirect vanity URL checkbox—what does it do? When to use? | Daniela to get back. In this case not needed.
6 | Shared_Data | Answered | 2026-02-19 | 2026-02-19 | Daniela Tea | Rick Lyon | Multiple vanity URLs per page—all link to same page? | Yes. Useful for print (short URL) vs long.
6 | Shared_Data | Deferred | 2026-02-19 | 2026-02-19 | Daniela Tea | Daniela Tea (update) | Card carousel tablet field removed—why? Can we have tablet-specific again? | Requirement: desktop/tablet same, mobile separate. Tablet always 2 for non–full width; field had no effect. Removed. Gap if tablet config needed.
6 | Shared_Data | Answered | 2026-02-19 | 2026-02-19 | Daniela Tea | Edwin Aquino | Content fragment model: default image for new CF? Override by author? | Yes—default value on model; new CFs get it; author can replace. Custom component (e.g. card) would show it.
6 | Shared_Data | Pending | 2026-02-19 | 2026-02-19 | Daniela Tea | Edwin Aquino | Experience fragment variation: break connection to reorder or use as regular component? | Daniela to confirm.
6 | Shared_Data | Pending | 2026-02-19 |  |  | Product Director | Governance: Who creates CF models for shared data? Who creates EF variations and rolls out?

## News
Session # | Session | Status | Date Asked | Answered On | Answered By | Asked By | Question/Comment | Answer | Notes
7 | News | Pending | 2026-02-20 | 2026-02-20 | Daniela Tea | Edwin Aquino | List component: exclude certain tags (e.g. do not use) from list? | Not OOTB; matching only. Daniela to take use case back (e.g. promotion page not on landing).
7 | News | Answered | 2026-02-20 | 2026-02-20 | Daniela Tea | Edwin Aquino | List: what dictates which items appear in which column? Order? | Order by title or last modified. Column count in config; fills in order.
7 | News | Pending | 2026-02-20 | 2026-02-20 | Daniela Tea | Edwin Aquino | Logo styling (image icon in footer)—what is it? Use case? | Daniela to check JIRA; not footer-specific; image component in general (e.g. height/width for multi-logo pages).
7 | News | Answered | 2026-02-20 | 2026-02-20 | Daniela Tea | Daniela Tea (update) | Redirect vanity URL checkbox: 302 redirect; when to use? | Documentation: 302 when checkbox. Daniela to share link; technical enablement for redirect management.
7 | News | Deferred | 2026-02-20 | 2026-02-20 | Daniela Tea | Edwin Aquino | News: default image by category/tag (e.g. casino vs hotel)? | Not currently. Gap; need requirements (multiple tags = which default?).
7 | News | Answered | 2026-02-20 | 2026-02-20 | Daniela Tea | Carlos Aldana | News CF: default image in model? Carlos: all articles have image. | Default image at component level (news search results) for items without image. Model default can be added.
7 | News | Pending | 2026-02-20 |  |  | Product Director | Governance: Who can add news categories (tags) and change news CF model?

## Locations
Session # | Session | Status | Date Asked | Answered On | Answered By | Asked By | Question/Comment | Answer | Notes
8 | Locations | Answered | 2026-02-23 | 2026-02-23 | Daniela Tea | Don Middlebrook | Location CF title = location ID; how to bulk update to property legal name? | Bulk metadata update: take value from property legal name (or chosen field), replace title. Daniela: tech KT if help needed. | Read-only fields from DPLT; title editable.
8 | Locations | Answered | 2026-02-23 | 2026-02-23 | Daniela Tea | Lisa Cardia | New location from DPLT: is delivery only—author manually checks? | Yes.
8 | Locations | Answered | 2026-02-23 | 2026-02-23 | Daniela Tea | Lisa Cardia | Image in location CF—where does it populate? Hotels? | Destinations and venues component (e.g. Hard Rock Hotel Cancun). Image specs to Confluence.
8 | Locations | Answered | 2026-02-23 | 2026-02-23 | Daniela Tea | Rick Lyon | Delivery/venue links: open in new window? | Yes; baked in (external links).
8 | Locations | Deferred | 2026-02-23 | 2026-02-23 | Daniela Tea | Lisa Cardia | Add new sort-by or filter field (e.g. meeting room view)? Process? | Update venue CF model, add to component dialog, front-end component update. Mayte: gap—overcomplicated; need optimized way. Lucas: mark as gap.
8 | Locations | Deferred | 2026-02-23 | 2026-02-23 | Daniela Tea | Lisa Cardia | Filters (e.g. type of destination) also hard-coded? Can we add (e.g. Unity participating hotel)? | Same concept—model + component.
8 | Locations | Pending | 2026-02-23 | 2026-02-23 | Daniela Tea | Gonzalo Calasich (SHRSS) | Regions filter on hardrock.com prod not working—Google Map component? | Different component (Google Map). Destination search and filter = this one. Cover Google Map when we get to it.
8 | Locations | Answered | 2026-02-23 | 2026-02-23 | Lucas Nelson | Lisa Cardia / Mayte Eme | Gap list: Adobe building it or SHRSS? Confluence questions = gap list? | Lucas: SHRSS documents gaps; Confluence questions feed funnel. Adobe shows framework; SHRSS comes to platform expansion with use cases and gaps. | Scott: questions/needs on Confluence.
8 | Locations | Pending | 2026-02-23 |  |  | Product Director | Governance: Who maintains location/venue CF when DPLT updates? Who can add new sort/filter fields?

## Locations_Day_2
Session # | Session | Status | Date Asked | Answered On | Answered By | Asked By | Question/Comment | Answer | Notes
9 | Locations_Day_2 | Answered | 2026-02-24 | 2026-02-24 | Daniela Tea | Edwin Aquino | What path do we choose for CF list path (category listing)? Not intuitive; can we update info tools? | Path = parent; component shows children of that parent. E.g. path to EN under news → year folders. Daniela demonstrated; Edwin confirmed. | News session follow-up.
9 | Locations_Day_2 | Answered | 2026-02-24 | 2026-02-24 | Kerry Holyoak (SHRSS) / Daniela Tea | Lisa Cardia | Delivery widget: Hard Rock Casino Rockford showing—casino classified as cafe. Who do we contact to fix? | DPLT team (Vipul Patel). Classifications come from DPLT; if misclassified, take to Vipul's team. Lisa to reach out. | Line of business = Cafe in DPLT drives delivery list.
9 | Locations_Day_2 | Deferred | 2026-02-24 | 2026-02-24 | Daniela Tea | Rick Lyon | Booking modal: black border; can we make booking widget same size/background as modal? | Note as gap—configurable color/size for modal.
9 | Locations_Day_2 | Answered | 2026-02-24 | 2026-02-24 | Rick Lyon / Daniela Tea | Lisa Cardia | Where do we get destination value (e.g. 59391) for booking widget? Do authors need to know it? | Rick: Senex/Vizergy; in booking links. Migrated; values don't change. Authors may need for restore if someone changes. Daniela: casino booking not finalized (pre-pause).
9 | Locations_Day_2 | Answered | 2026-02-24 | 2026-02-24 | Daniela Tea | Lisa Cardia | Booking widget: adding a different field (e.g. balcony) beyond rooms/adults/children—development? | Yes—new field type, UI, parameter passing, booking engine side. Development for sure.
9 | Locations_Day_2 | Deferred | 2026-02-24 | 2026-02-24 | Daniela Tea | Rick Lyon | Booking offers: can we hide the booking window section completely? | Tried; window still present, fields blank. Hide label too = potential gap. No option to hide completely today.
9 | Locations_Day_2 | Deferred | 2026-02-24 | 2026-02-24 | Daniela Tea | Lisa Cardia | Find a location: can we change the background color? | Currently fixed in code. Change would require code update to allow author-configurable background.
9 | Locations_Day_2 | Answered | 2026-02-24 | 2026-02-24 | Daniela Tea / Lucas Nelson | Gonzalo Calasich (SHRSS) | Google Map: regions dropdown blank in prod—why? North America first in config but showing last. | Permissions: groups didn't have read on generic list 'regions.' Template Authors given read. Order: ensure regions authored in dialog (first = top); republish page. | ACS Commons on prod. Media session confirmed fix.
9 | Locations_Day_2 | Answered | 2026-02-24 | 2026-02-24 | Daniela Tea | Lisa Cardia | Google Map: filter map not in config but filters showing—why? No results vs no locations? | Filter map adds filters on map. Different messages for no results vs no locations. Daniela made copy to demo filter map.
9 | Locations_Day_2 | Pending | 2026-02-24 | 2026-02-24 | Daniela Tea | Lisa Cardia / Rick Lyon | Google Map: carousel dots not centered under images. | Daniela noted; would need to be updated to center align carousel dots.
9 | Locations_Day_2 | Pending | 2026-02-24 |  |  | Product Director | Who owns DPLT classification (line of business) and SHRSS contact for misclassification? | Not answered in session.
9 | Locations_Day_2 | Pending | 2026-02-24 |  |  | Product Director | Which groups need read/write on generic list 'regions' for Google Map? | Not answered in session. Andy covering permissions in KT next week.

## Media
Session # | Session | Status | Date Asked | Answered On | Answered By | Asked By | Question/Comment | Answer | Notes
10 | Media | Answered | 2026-02-25 | 2026-02-25 | Daniela Tea | Gonzalo Calasich (SHRSS) | Google Map regions dropdown not visible yesterday—resolution? | Generic list 'regions' populates dropdown. User groups lacked read access. Template Authors given read; Gonzalo and Lisa confirmed can see. Permissions topic with Andy next week. | Locations Day 2 follow-up.
10 | Media | Answered | 2026-02-25 | 2026-02-25 | Daniela Tea | Gonzalo Calasich (SHRSS) | North America showing last on prod—publish page again? | View as published to confirm order; then publish. Andy to take a look at prod page.
10 | Media | Pending | 2026-02-25 | 2026-02-25 | Daniela Tea | Rick Lyon | Media gallery: carousel dots not centered (left of center). | Daniela noted; capture for update to center align carousel dots.
10 | Media | Deferred | 2026-02-25 | 2026-02-25 | Daniela Tea | Edwin Aquino | Image gallery grid: option to show/hide title or inherit from asset like alt text? | Not for this component. Title pulled from DAM metadata. If no title in metadata, 'no title' shows. Enhancement to capture if team wants option to not display title.
10 | Media | Deferred | 2026-02-25 | 2026-02-25 | Daniela Tea | Edwin Aquino | Image gallery grid: different titles for same image per property/site? | Not currently. Control via metadata per asset; no variation/title override in component.
10 | Media | Answered | 2026-02-25 | 2026-02-25 | Don Middlebrook / Daniela Tea | Daniela Tea (to Don) | Image gallery grid: are we adding titles/descriptions to assets? | Don: planning to add as much metadata as possible—titles, description. Daniela: if titles not always desired, capture enhancement to not display or use description.
10 | Media | Pending | 2026-02-25 |  |  | Product Director | Who can add/edit generic list values (e.g. regions)? Which groups get read vs write?
10 | Media | Pending | 2026-02-25 |  |  | Product Director | Image gallery grid: hide title or show description—enhancement?