## Jobs
Status | Date Asked | Answered On | Answered By | Asked By | Question/Comment | Answer | Notes
Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | You have two IDs—job unique ID and job ID. Which one are you using? (Displayed one is wrong.) | Right now both come from Workday; what's displayed to end user is job ID. Ticket exists for this; dev team looking at it. | Mayte said 'that's the wrong one'—job ID vs job unique ID; fix via ticket.
Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Image field—not mapped to pick up automatically the right image like we currently have? | Image is author-input; image configuration page allows setting images per property; author can overwrite or remove.
Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | Does the image override replace the image on the card and the listing or just the card? | Override updates image in both job listings component (cards) and job search component (horizontal cards). | Lisa noted they typically use logo on listings, property shot on homepage/hiring events.
Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | If we override something in the CF, does the sync overwrite it or do we keep the override? | Only Workday fields get overwritten. Image, is hot job, and LD JSON are author-only and do not get overwritten by sync.
Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Ramona Harris | What is the standard size for the logo image that should be uploaded? | Still need to get back—used whatever was in DAM for Sage site; don't have exact measurements yet.
Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | How do you create a new job as an author (not from Workday)? | Create → Content Fragment → select Jobs; fill out all fields. Categories are not dropdowns—must match exact value (e.g. casino sales).
Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Is there scheduling when adding a job—as soon as you publish it goes live? | Content fragments can be scheduled; Workday jobs get published automatically on sync without author intervention.
Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Manual jobs—they drop off based on Workday; if manual, we have to manually delete? | Correct.
Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Gonzalo Calasich (SHRSS) | When sync runs from Workday, do we delete all job postings from AEM each time? Job no longer active in Workday—removed on next sync? | Folder structure stays; job postings come and go based on Workday. When job removed in Workday, next sync removes it from AEM.
Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Do we have an option to immediately hide a job from the website without Workday removing it? (e.g. weekend, can't get hold of anyone.) | Author could delete but sync would republish. No current way to just hide. Daniela to check with dev team if turning off 'is API data' could freeze sync for that job. | Edge case but has happened; need business continuity.
Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | Which fields do not get overridden when sync happens? (You said three.) | Image, is hot job, and LD JSON. Only those three are author-only.
Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Ramona Harris | Select locations in job search—are those pulling from AEM? New property—is author responsible for adding so it appears in filter? | Locations come from content fragment (country, state, city). New property/jobs from Workday create folder structure automatically; author does not add. | Ramona had not seen Ottawa in AEM—clarified it's from CF data.
Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Don Middlebrook | For the image in the component—where does it come from? If we move the asset in DAM, do we lose the reference? | Image comes from DAM. If asset moved or renamed, reference should update; if deleted, would break. Daniela to confirm.
Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Charles Baugh (SHRSS) | How is the sequence/order of job results determined? How would we reorder? | Sort filter on component: most recent (default), job title, location. Hot jobs always stay at top; rest sort among themselves.
Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | When clicking a job card—what data do we send to Tealium data layer? Do we have unique IDs per card for tracking? | Daniela to check with tech team. Content fragments have unique IDs; need to confirm what is passed to data layer. | Mayte: need unique IDs per card, not just friendly link.
Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Angelika Akopyan (SHRSS) | Is there an option to run the Workday sync on demand? | Daniela to check. May be running more frequently than 30 min (e.g. 5 min); will confirm and ask about on-demand.
Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Angelika Akopyan (SHRSS) | Production sync—how long will the period be (5 min or 30)? With ~800 jobs, how long does full sync take? | Daniela to check with team.
Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Gonzalo Calasich (SHRSS) | When you select a filter it doesn't append to URL. Can we have deep links so copying URL lands on filtered view? (We need friendly deep links, not weird numbers.) | Daniela to talk to tech team. Use case: property sites link to careers filtered by property/category/region. | Mayte: we don't want every filter combo creating new URL (analytics); we want ability to deep link.
Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | If sync goes wrong and can't display data—do we have an error message or just blank? | No jobs in AEM shows 'no jobs found.' Separate error message for sync failure (vs no results) is a gap—note for gap analysis. | Mayte: had blank page when testing iSense; want custom message for business continuity.
Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | For a new careers page—what template should we use? | Open page template for all these pages (header/footer + content area).
Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | When you select filters, do they update each other (conditional/dependent filters)? | Yes—e.g. selecting property updates other filter options; unchecking brings categories back.
Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Job listings—does it only go by state (e.g. Florida) or can we select properties? Can we do multiple properties? | Can select one folder (e.g. Orlando or Florida). You can only select ONE root path, not multiple properties. To show Coco + Classic + Hollywood would require multiple components one after another; can't sort across them. | Mayte: our use case is three South Florida properties; noted as gap.
Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | If we have fewer than three cards (e.g. one or two), is there a way to center them instead of left align? | Not currently. Would need to discuss in gap portion—centered vs same width vs full width. | Lisa: hot jobs vs hiring events cards all display differently; consistency concern.
Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | Apply Now button—what is its purpose if the URL always comes from the content fragment? | Button text is configurable in component; the URL/destination is from the content fragment.
Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | For hot jobs can we have the root path higher so it's all hot jobs, not specific to one location? | Yes—set root path higher in hierarchy to get all hot jobs across locations.
Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | If there are no hot jobs—does the component hide, or show blank with a message? | Currently shows section title with no cards and no message. Does not hide. Angelika confirmed; Mayte/Lisa want hide or message—gap. | JIRA ticket exists for this.
Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | Hot jobs we use property image; in listings we use logo. Same job in hot jobs vs listing—we want different images. | Noted. Daniela confirmed understanding—hot job might have property image, same job in search shows logo. Gap for implementation.
Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Why do we have to configure the search page in Job Filters? We only have one search page. Can it be defaulted? | Currently pointing to correct page. If component used elsewhere, author can change. Defaulting is possible; Mayte wants one step less for authors. Log as gap.
Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Job category cards—how do we change/pick which categories to display? (e.g. don't want food and beverage, want to promote others.) | Currently cannot pick and choose categories; shows all or by sort (most jobs / alphabetical). Not in component. | Mayte: we had ability in past; this component may be deprecated.
Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | What is 'job property' in the image config? Is it a specific name we need to match (e.g. Workday name)? | It's the value from the job property field in the content fragment. Config matches that value to assign the image. Must match exactly.
Pending | 2026-02-10 | 2026-02-10 | Daniela Tea / Lucas Nelson | Mayte Eme | Are all locations in the image config? We have over 500 locations; the list doesn't seem long. | Initial setup by Adobe tech team; list may not be complete. Need full list—Lucas to follow up with Vinay; Scott to task IT to get list from Workday and map ahead of time. | Lisa: mapping has to be manually added in AEM; Workday doesn't push it.
Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | If Workday changes internal name (e.g. HRC Washington DC to Hard Rock Cafe Washington DC), does that break the mapping? | New entry would need to be added in config with the new property value and desired logo. Old name would no longer match. | Mayte: mapping is very manual; concern for 500+ locations.
Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Who does the mapping and who gets every location name when we go to production? | Adobe did initial setup. Who adds new properties or changes logos unclear; need to understand source of full list. | Scott to ask Vinay; Lisa: whoever handed off first time.
Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | Hot jobs page and hiring events page—do we have to add hot jobs manually to every location or does it pull from same feed? | Same component (job listings, hot jobs). Toggle hot job in CF once; appears on homepage and hot jobs page. Hiring events = different content fragment (events session).
Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | On the hot jobs page—where is the filtering and searching? | Filtering is not currently part of the component; open ticket, gap in JIRA.
Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | Hiring events cards vs hot jobs—different widths/heights; not consistent. | Different content fragments; will cover events tomorrow. Noted inconsistency.
Answered | 2026-02-10 | 2026-02-10 | Daniela Tea | Mayte Eme | Queries for bringing in different content by property (like Sitecore scopes)—will we go through that? | Daniela asked for examples. Angelika showed brands/cafes/casinos—same cards on multiple pages. Experience Fragment approach can give single update; exclusion logic (e.g. don't show current page's card) would need custom logic. | Lisa: need logic so on Casinos page we don't show Casinos card (show children excluding current).
Deferred | 2026-02-10 | 2026-02-10 | Daniela Tea | Lisa Cardia | Shared cards—when on casino page, don't show casino card (show all children excluding current page). Experience fragment gets us reuse; we need that exclusion logic. | Experience fragment = update once. Current implementation is local per page so exclusion was possible. To get both reuse and exclusion would need custom component. Decision for Hard Rock. | Mayte: should have been set up properly; task for Mohsin.
Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Charles Baugh (SHRSS) | Best way to take down 3 jobs and reschedule for later—resubmit through Workday with 10 and purge, or purge in AEM, or reschedule manually in AEM? | Workday is source of truth; AEM changes get overwritten by sync. Daniela to check with tech team if there's an author-side way to handle; answer tomorrow.
Pending | 2026-02-10 | 2026-02-10 | Daniela Tea | Joseph Brondolo (SHRSS) | Job filters (homepage)—where are the four labels (job category label, properties label, etc.) located in configuration? I had a story and couldn't find them. | Daniela to get back—might be in markup not visible to user. Add to list for beginning of tomorrow's session.
Pending | 2026-02-10 | 2026-02-10 | Daniela Tea / Lucas Nelson | Mayte Eme | Did we ask for specs for the job/logo images so we don't have corrupt or huge logos? Who fixes those before go-live? | Spec sheet not yet detailed. Lucas: Daniela to talk with Vinay and authoring support.
Pending | 2026-02-10 | 2026-02-10 | Lucas Nelson / Scott Sorel | Mayte Eme | Pagination—recommendation for max number of jobs per page? We have ~800 jobs; have you tested performance? | Lucas: Adobe doesn't have performance testing resource. Scott: take back to TJ/Mohsin. Mayte: had issues before with 50; want an answer.
Pending | 2026-02-10 |  |  | Product Director | Governance: Who owns ongoing maintenance of job property–to–image mapping (Adobe, IT, or SHRSS)? What process for new properties or Workday name changes? |  | Governance and roles.
Pending | 2026-02-10 |  |  | Product Director | Authoring: Can we get a short checklist or decision tree for authors (which component when; what authors can edit vs what sync overwrites)? |  | Authoring clarity.
Pending | 2026-02-10 |  |  | Product Director | Tagging/metadata: Besides Hot Job and image, what other author-controlled metadata affects display or filtering? Who governs allowed values for categories (Workday vs author-created)? |  | Tagging and governance.
Pending | 2026-02-10 |  |  | Product Director | Gap analysis: Which of today's gaps are in scope for careers go-live (e.g. job ID, deep links, hot jobs empty state, image specs) vs deferred to post–gap analysis? |  | Priorities for go-live.
Pending | 2026-02-10 |  |  | Product Director | Permissions: Who can access Job Image configuration (ACS AEM Commons)? Admin-only or can we assign a careers/DAM role? |  | Governance and permissions.

## Events
Status | Date Asked | Answered On | Answered By | Asked By | Question/Comment | Answer | Notes
Pending | 2026-02-11 | 2026-02-11 | Daniela Tea / Andy Lambert | Gonzalo Calasich (SHRSS) | View as published shows changes fast but publisher takes too long; new job (CF) not showing on publisher. Can we expedite? | Need more info (cache, etc.). Daniela will monitor during call. Andy investigating failed publish logs; will raise support ticket. | Gonzalo: not showing at all on publisher; likely cache.
Deferred | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia | Override for date field (e.g. 'every Wednesday through February') instead of actual date/time? | Not in event content fragment. Promotions has date override; can confirm if same behavior wanted for events—gap. | Same question for location override.
Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia | What happens if we add an additional image in the event image field (multi)? | Believes it defaults to first one; can test. Migration used only one image.
Deferred | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia | Event status: logic so presale dates show presale disclaimer then auto-revert to 'on sale'? | Not currently. Gap: associate status with date/time so it changes without author republish. Presale can be outside business hours.
Deferred | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia | Hide CTA (more info) when there's no landing page / no extra info for user? | Default links to event detail page. Toggle to hide CTA entirely would be gap. | Use case: weekly free entertainment; no detail page.
Deferred | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia | Location reference: limit by user so cafe only adds their location? Avoid choosing wrong location (e.g. Amsterdam for Mexico event). | Location reference drives filter roll-up; root path limits which events show. Wrong location in CF still adds to this site's filter. Restrict by user = gap. | Folder path = organization; location reference = required for display/filter.
Deferred | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia | Default image for event card so author doesn't have to select every time (generic default)? | CF cannot be saved without image. Component-level default (like jobs listing) could be gap. Author can use default from DAM in meantime.
Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Mayte Eme | Event detail page—why does it look like a card? Are we on careers? Hard Rock Live—can we use for careers? | This is the event detail page (one template). Same for all sites. Daniela created new page to show from scratch. | Mayte: digital page not working for careers events.
Deferred | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia / Mayte Eme | Clean/friendly URL for event detail (property.com/artist-name not numbers)? | Event ID is read-only to prevent duplicates. Enhancement = make editable for friendly URL. Mayte: need real names; like WordPress/Sitecore—pick up page name. Gap. | Labor intensive; add to gap list.
Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Edwin Aquino | Event detail page hero—standard across all or customizable per page? | Default hero on event detail page; banner image + alt in CF overrides.
Deferred | 2026-02-11 | 2026-02-11 | Daniela Tea | Mayte Eme | Event statuses: all manual or can we schedule (presale, announcement, rescheduled)? Do they drive/hide content? | Currently manual. Gap to have date range per status. Presale/sold out etc. change label/flag; event status message is separate. Doesn't hide CTA or content.
Pending | 2026-02-11 | 2026-02-11 | Daniela Tea / Andy Lambert | Lisa Cardia / Mayte Eme | Do we have to publish to see changes? How to preview before publish for approval? | View as published doesn't show CF changes until CF is published. Andy: preview tier exists, not configured; will check export. Mayte: need browser preview to screenshot for approval. | Preview server / preview links = gap analysis.
Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia | When adding new event: publish fragment, detail page, and calendar every time? | One event detail page per calendar—publish once. New event: publish CF; calendar page must be published for event to show on publisher (can take a few minutes). | Gonzalo's delay = calendar page publish.
Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia / Mayte Eme | Unpublish event (take down without delete) to repurpose later? | Unpublish CF removes from calendar. Daniela to check if detail URL still accessible. Later: unpublished = detail URL shows configured 'no events' message; content not visible. | Mayte: add as gap—not expected behavior but at least user doesn't see it.
Answered | 2026-02-11 | 2026-02-11 | Mayte Eme / Daniela Tea | Mayte Eme | Recap: unpublish works; schedule not local to property; end date auto drop-off; all statuses manual; no date/location override; three times instead of one (vs Sitecore). | Daniela acknowledged. Hiring events use promotions model (has overrides); events model does not.
Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Mayte Eme / Gonzalo | Hiring events—using promotions not events? What can events CF do vs promotions? | Hiring events section uses promotions content fragment (date/location override). Events CF + calendar/detail = what we covered. Tomorrow: hiring events component. | Careers not using events CF for that section.
Deferred | 2026-02-11 | 2026-02-11 | Daniela Tea | Mayte Eme | Can we choose mix-and-match locations for one calendar (e.g. six properties, or hotel+casinos, or by venue)? | No. One content fragment folder path only; cannot select multiple folders. Big gap for multi-venue/entertainment sites.
Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Mayte Eme | Pull events into other pages (venue page, homepage by category, e.g. dinner and a show)? | Content Fragment card list component can show events (or news); by root path or by tag (e.g. dinner and a show). Not locked to calendar component.
Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Lisa Cardia | Why did we lose the filter for events (careers hiring events landing page)? | Careers uses content fragment card (no filter on purpose for homepage). Promotions component has filter; can swap on landing page if desired.
Answered | 2026-02-11 | 2026-02-11 | Daniela Tea | Mayte Eme | Can we pull jobs (hot jobs/hiring events) to property page (e.g. Reverb) by tag or location? | Yes—select root path (e.g. Tampa folder); all jobs under that path. Cannot select multiple locations in one component. Exclude category under Tampa? Not in component.
Pending | 2026-02-11 | 2026-02-11 | Daniela Tea | Edwin Aquino | Display tag on event cards (21+, free event, phone-free)? | Daniela asked for example; will discuss with technical team. | Edwin to send example.
Pending | 2026-02-11 | 2026-02-11 | Daniela Tea | Rick Lyon (Director of Digital Experience) | Preview link for unpublished page to share for approval before republish? | Unpublished CF not on calendar or detail. If publish CF, visible in author; page must be published for end user. Daniela to report back on detail-page behavior. | Preview before publish = gap.
Pending | 2026-02-11 | 2026-02-11 | Andy Lambert | Lucas Nelson | Publish delays on stage—investigating? | Andy: seen failed publish entries in cloud services log; raising support ticket; will keep team posted.
Pending | 2026-02-11 |  |  | Product Director | Governance: Who owns Event Categories tags and DPLT location list? Process when property/venue added or renamed?
Pending | 2026-02-11 |  |  | Product Director | Authoring: One-page checklist for event authoring (what to create, publish, order) and when to use events CF vs promotions CF?
Pending | 2026-02-11 |  |  | Product Director | Tagging: Event categories vs tags for filtering vs 'dinner and a show' query—who governs? |  | Categories = filter; tags = internal; tag for query possible.
Pending | 2026-02-11 |  |  | Product Director | Gap analysis: Decision criteria for events CF vs promotions CF; which gaps apply to which model?
Pending | 2026-02-11 |  |  | Product Director | Permissions: Who can create/edit Event Categories tags and DPLT location reference options?

## Careers
Status | Date Asked | Answered On | Answered By | Asked By | Question/Comment | Answer | Notes
Pending | 2026-02-12 | 2026-02-12 | Andy Lambert / Daniela Tea | Gonzalo Calasich (SHRSS) | Manual job content fragment: create, publish, not showing on jobs page. Other CFs show. Workday sync deletes manual jobs (is not API data) in ~30 min. | Andy: investigating; support ticket. Get all job IDs not excluding manual; email with recommendation coming; tech sync to drill in. | Gonzalo to send example URLs for logs.
Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia / Mayte Eme | Promotion ID—where from? What do we put? Is it made up? Required for targeting/analytics we had for casino, not unique ID for display. | Author-entered unique identifier to display one promotion (e.g. content fragment card). No format requirement. Uniqueness validated on save. Same value in another CF blocks save. | Mayte: gap—we don't want this; need to remember/copy; not smart (dropdown of existing IDs).
Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | When pasting ID elsewhere (e.g. component), is there a dropdown to select from existing or must we remember/paste? | Component field is plain text; no dropdown. Must copy from CF. Gonzalo: gap = source field to navigate DAM and pick CF.
Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | Without promotions filter (careers homepage): steps to get card on page = know ID, copy from fragment, paste in component. No other way? | Yes. Content fragment card expects promotion ID for promotions/events. No folder path picker. Gap: enhance card list to include promotions or add path/source picker.
Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea / Lucas Nelson | Mayte Eme | Promotion ID for casino or careers? We're not using for casinos; we need to fix for casinos (many users, can't remember IDs). | Initially for casinos. Careers using it for hiring events. Lucas: capture what it doesn't have; disposition in platform expansion; modify/change is part of it.
Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Promotion search: can we remove the search field and keep only filters? | Search cannot be removed currently. With filters, search bar always shows. To display as list without filter/search = gap.
Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | If we use promotions for hiring events we can't have promotion cards in grid/carousel elsewhere without filter+search—only one-by-one by ID. | Correct. Content fragment card list currently events/news only; gap = add promotions so list/carousel without filter+search.
Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | Who manages filter options (category, venue, date range)? Author or dev? Can we add different options? | In component code; hardcoded from promotions requirements. New filter = dev. Potential to move to generic list (author-managed) but not available today. Mayte: we manage every filter—gap.
Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | Promotion search: same as events—can't select two category folders (e.g. casino + hotel promotions)? | Single path only. Can choose promotions root or e.g. casinos; cannot pick two of four folders. Mayte: another gap.
Pending | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | Promotions: are filter options (e.g. select category) translatable / overridable for language? | Daniela to check with tech team. Components have language strings; need to confirm what's translatable. At minimum override all areas. Gonzalo: include Transperfect + developer labels. | Technical topic; Scott/technical enablement.
Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Transperfect: manual translations for some languages; not always Transperfect. OK? | Noted. Daniela will address in Transperfect KT.
Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Promotion start/end date and time—is that for scheduling or display only? | Display only. Schedule = Manage Publication > Now or Later (activation date). Not for 'display this event on Saturday but publish tomorrow.'
Pending | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | If we schedule for later and then edit the fragment (e.g. change venue), does it maintain schedule or push live? | Daniela to test (save, manage publication, save); will confirm.
Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | Promo types (loyalty, slot)—hardcoded? How do we add extra promo types? | In content fragment model (not component). Model editor = more flexibility; permissions apply. Adding dropdown to component = dev. Model edit vs component = different.
Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Don Middlebrook | Card/promotion image: 16:9 asset—how to control focal point (e.g. center guitar)? Image position? | Image position tab on image components (desktop/tablet/mobile). List (promotion search) has no per-row position; crop outside or use rendition—DAM/gap. | Don: one source image across placements; figure out with DAM/renditions.
Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Job listings on another site (e.g. hotel)—same component, theme changes styling? Can we choose multiple locations? | Yes—component is global; theme drives look. Still one root path only (gap). Use case: Tampa/Hollywood dedicated job pages.
Pending | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | How do we see the promotion card's detail page? Is there a promotion detail template? | No promotion detail template. Create open page, add content, link from CF. Daniela to show casino example from integration env. | Banner image in CF = for when promotion has its own page.
Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Events template allows link to another page (event detail). Promotions can't do that—we have hot jobs/dealer university with detail pages. | Promotions: can link to any page from CF. Events: one detail page + ID. Override in events = gap; then could use events for hiring events. Workaround: link to existing page from promotion CF.
Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | Video card: external URL—recommended width? Pixel required? What does width affect? | Width affects modal size. Number only, no 'px.' 846 was to match live site. Can change.
Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia / Mayte Eme | Video card: third party (YouTube) gives fixed/responsive, aspect ratio; external URL doesn't. Same config for external? | External URL = no those options. Third party = full config. Gap—external should have same controls; else only use YouTube/Vimeo. Mayte: don't use external until fixed.
Pending | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | Video card styling (none/black/white): is 'none' transparent? White description not showing. | Daniela to check white; none = default. Black works. Screenshot of three when fixed.
Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Video card: if we add a fourth, does it become carousel automatically (like Sitecore)? | No. Video card not in allowed components for card carousel or hero carousel. Gap: allow video cards in carousel.
Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Card (icon variation): with 6 or 9 cards, does it go 3 to 1 columns automatically or manual per breakpoint? | Manual per viewport for standalone card. Some components (e.g. carousel) have breakpoint config. Mayte: add to gap list.
Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Executives/diversity page (careers) same as hardrock.com—shared so one update? | Currently separate cards. Can move to experience fragment: update once, same styling both sites. Content fragment = same content, different styling per site. | Rick: corporate page hardrock.com.
Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Experience fragment: same content, different styling per site possible? | Experience fragment = same content + same look. For same content, different look = content fragment.
Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia | Asset specs for video card thumbnail, promotion card/banner—recommended dimensions? Focal point for video thumbnail? | Document on component basis; video thumbnail aspect/specs; no image tab on video card. Gap.
Deferred | 2026-02-12 | 2026-02-12 | Daniela Tea | Lisa Cardia / Mayte Eme | Store component on page but not displayed (like Sitecore disable)—reuse later without recreating? Hide = still in DOM? | Hide component (layout > eye) = still in tree, still in DOM/crawled. Not like Sitecore where disabled = not in HTML. Gap: store without rendering for evergreen swap. | Content refresh initiative; rotate temp vs evergreen.
Answered | 2026-02-12 | 2026-02-12 | Daniela Tea | Mayte Eme | Careers locations page same as brand—pulling from DPLT? Can we copy accordion/component so one source? | Careers = accordion/text (migrated); brand = map component + DPLT. Can copy map component to careers. Intent: all location listings from DPLT, one maintenance. | Daniela to post test page with copied component.
Pending | 2026-02-12 |  |  | Product Director | Governance: Who owns promotion ID list and filter options? Process to add/change?
Pending | 2026-02-12 |  |  | Product Director | Authoring: Single checklist for hiring events (CF → card vs search → detail page → publish order) and when events vs promotions?
Pending | 2026-02-12 |  |  | Product Director | Tagging: Do promotions use tags for filtering? If card list adds promotions, tag-based selection?
Pending | 2026-02-12 |  |  | Product Director | Gap priorities: Which items (ID vs path, filter removal, card list promotions, video carousel, thumbnail specs, hide vs disable) for careers vs platform expansion?
Pending | 2026-02-12 |  |  | Product Director | Permissions: Who can edit promotions model (promo types) and promotion search config (filter labels)?

## Tagging_Taxonomy_Metadata_Gov
Status | Date Asked | Answered On | Answered By | Asked By | Question/Comment | Answer | Notes
Pending | 2026-02-17 | 2026-02-17 | Andy Lambert | Don Middlebrook | Why multiple category directories (categories, category, news categories, events categories)? Consolidate under one? | Different purposes; naming could be clearer. Andy to assess functional implications of consolidation, then green-light. Add as to-do for cleanup. | Don: same for property/hotel/casino/cafe under locations.
Pending | 2026-02-17 | 2026-02-17 | Andy Lambert | Lisa Cardia | If we restructure tags, does that break anything currently? | Assess first; goal is no hard-coded paths, config where possible. Then SHRSS can make changes. Move tool updates reference paths.
Pending | 2026-02-17 | 2026-02-17 | Andy Lambert | Don Middlebrook | How do we use generic lists (ACS Commons path-to-tag mapping)? What are they used for? | Governs tags for a section. Andy to add to Confluence Q&A; Vinay for deeper answer. Not used for corporate/careers today.
Deferred | 2026-02-17 | 2026-02-17 | Andy Lambert | Don Middlebrook | Content fragment model category field—tag-driven or defined in model? Where do these lists come from? | Can be tag-driven or enumeration. Locations example = not all from tags. Depends on use case; gap to align. Check model.
Pending | 2026-02-17 | 2026-02-17 | Andy Lambert | Don Middlebrook | Asset categories vs content fragment categories—different? Event categories on asset vs events. | Yes—asset metadata vs CF categories; confusing. Asset event categories ≠ CF event categories. Action: cleanup, rename for clarity. | Lisa: location reference ID same issue (events session).
Deferred | 2026-02-17 | 2026-02-17 | Andy Lambert | Don Middlebrook | Pre-populated metadata set for export (so we don't add 15 properties every time)? | Not OOTB. Andy: pain; keep text file with property names, copy/paste. Chris may say same tomorrow.
Pending | 2026-02-17 |  |  | Product Director | Governance: Who owns SHRSS tag vocabulary and consolidation decision? Process to add namespace?
Pending | 2026-02-17 |  |  | Product Director | Authoring: Where do authors see tag-driven vs fixed list? One-pager by model/asset type?
Pending | 2026-02-17 |  |  | Product Director | Permissions: Which groups have create/update/delete on SHRSS tags?

## DAM_Training_Usage_Admin
Status | Date Asked | Answered On | Answered By | Asked By | Question/Comment | Answer | Notes
Answered | 2026-02-18 | 2026-02-18 | Andy Lambert | Don Middlebrook | SHRSS primary: consolidate into SHRSS, deprecate primary? Path forward. | Yes. Don to move primary content into SHRSS; deprecate primary. Content fragment behavior may need back-end look. | Don: 13 months ago didn't know move wouldn't break refs.
Answered | 2026-02-18 | 2026-02-18 | Andy Lambert / Chris Lewis | Andy Lambert | Legacy/migrated assets folder—option to move old content there, new structure for new? | Yes—e.g. legacy-assets; new content in new structure; cleanup/scripting later. Chris agreed.
Answered | 2026-02-18 | 2026-02-18 | Chris Lewis | Andy Lambert | Language folders for assets—required for translation automation? | Chris: language at top level for AM Guide etc. If no language-swap use case, metadata for language is fine. Don: single asset, metadata.
Pending | 2026-02-18 | 2026-02-18 | Andy Lambert | Don Middlebrook | Renditions: Don tried to create, they're not applying. | Andy: renditions in agenda; will cover. Hot topic.
Answered | 2026-02-18 | 2026-02-18 | Chris Lewis | Lisa Cardia / Don Middlebrook | Careers asset names odd (C2D5 etc.)—not from Sitecore. Bulk rename? | Chris: migration tool internal ref. Bulk rename via export metadata to Excel, edit names, re-upload.
Pending | 2026-02-18 |  |  | Product Director | Governance: Who approves DAM folder structure and bulk renames?
Pending | 2026-02-18 |  |  | Product Director | Rendition profiles not applying—root cause and fix in scope?

## Shared_Data
Status | Date Asked | Answered On | Answered By | Asked By | Question/Comment | Answer | Notes
Pending | 2026-02-19 | 2026-02-19 | Daniela Tea | Edwin Aquino | Redirect vanity URL checkbox—what does it do? When to use? | Daniela to get back. In this case not needed.
Answered | 2026-02-19 | 2026-02-19 | Daniela Tea | Rick Lyon | Multiple vanity URLs per page—all link to same page? | Yes. Useful for print (short URL) vs long.
Deferred | 2026-02-19 | 2026-02-19 | Daniela Tea | Daniela Tea (update) | Card carousel tablet field removed—why? Can we have tablet-specific again? | Requirement: desktop/tablet same, mobile separate. Tablet always 2 for non–full width; field had no effect. Removed. Gap if tablet config needed.
Answered | 2026-02-19 | 2026-02-19 | Daniela Tea | Edwin Aquino | Content fragment model: default image for new CF? Override by author? | Yes—default value on model; new CFs get it; author can replace. Custom component (e.g. card) would show it.
Pending | 2026-02-19 | 2026-02-19 | Daniela Tea | Edwin Aquino | Experience fragment variation: break connection to reorder or use as regular component? | Daniela to confirm.
Pending | 2026-02-19 |  |  | Product Director | Governance: Who creates CF models for shared data? Who creates EF variations and rolls out?

## News
Status | Date Asked | Answered On | Answered By | Asked By | Question/Comment | Answer | Notes
Pending | 2026-02-20 | 2026-02-20 | Daniela Tea | Edwin Aquino | List component: exclude certain tags (e.g. do not use) from list? | Not OOTB; matching only. Daniela to take use case back (e.g. promotion page not on landing).
Answered | 2026-02-20 | 2026-02-20 | Daniela Tea | Edwin Aquino | List: what dictates which items appear in which column? Order? | Order by title or last modified. Column count in config; fills in order.
Pending | 2026-02-20 | 2026-02-20 | Daniela Tea | Edwin Aquino | Logo styling (image icon in footer)—what is it? Use case? | Daniela to check JIRA; not footer-specific; image component in general (e.g. height/width for multi-logo pages).
Answered | 2026-02-20 | 2026-02-20 | Daniela Tea | Daniela Tea (update) | Redirect vanity URL checkbox: 302 redirect; when to use? | Documentation: 302 when checkbox. Daniela to share link; technical enablement for redirect management.
Deferred | 2026-02-20 | 2026-02-20 | Daniela Tea | Edwin Aquino | News: default image by category/tag (e.g. casino vs hotel)? | Not currently. Gap; need requirements (multiple tags = which default?).
Answered | 2026-02-20 | 2026-02-20 | Daniela Tea | Carlos Aldana | News CF: default image in model? Carlos: all articles have image. | Default image at component level (news search results) for items without image. Model default can be added.
Pending | 2026-02-20 |  |  | Product Director | Governance: Who can add news categories (tags) and change news CF model?

## Locations
Status | Date Asked | Answered On | Answered By | Asked By | Question/Comment | Answer | Notes
Answered | 2026-02-23 | 2026-02-23 | Daniela Tea | Don Middlebrook | Location CF title = location ID; how to bulk update to property legal name? | Bulk metadata update: take value from property legal name (or chosen field), replace title. Daniela: tech KT if help needed. | Read-only fields from DPLT; title editable.
Answered | 2026-02-23 | 2026-02-23 | Daniela Tea | Lisa Cardia | New location from DPLT: is delivery only—author manually checks? | Yes.
Answered | 2026-02-23 | 2026-02-23 | Daniela Tea | Lisa Cardia | Image in location CF—where does it populate? Hotels? | Destinations and venues component (e.g. Hard Rock Hotel Cancun). Image specs to Confluence.
Answered | 2026-02-23 | 2026-02-23 | Daniela Tea | Rick Lyon | Delivery/venue links: open in new window? | Yes; baked in (external links).
Deferred | 2026-02-23 | 2026-02-23 | Daniela Tea | Lisa Cardia | Add new sort-by or filter field (e.g. meeting room view)? Process? | Update venue CF model, add to component dialog, front-end component update. Mayte: gap—overcomplicated; need optimized way. Lucas: mark as gap.
Deferred | 2026-02-23 | 2026-02-23 | Daniela Tea | Lisa Cardia | Filters (e.g. type of destination) also hard-coded? Can we add (e.g. Unity participating hotel)? | Same concept—model + component.
Pending | 2026-02-23 | 2026-02-23 | Daniela Tea | Gonzalo Calasich (SHRSS) | Regions filter on hardrock.com prod not working—Google Map component? | Different component (Google Map). Destination search and filter = this one. Cover Google Map when we get to it.
Answered | 2026-02-23 | 2026-02-23 | Lucas Nelson | Lisa Cardia / Mayte Eme | Gap list: Adobe building it or SHRSS? Confluence questions = gap list? | Lucas: SHRSS documents gaps; Confluence questions feed funnel. Adobe shows framework; SHRSS comes to platform expansion with use cases and gaps. | Scott: questions/needs on Confluence.
Pending | 2026-02-23 |  |  | Product Director | Governance: Who maintains location/venue CF when DPLT updates? Who can add new sort/filter fields?

## Locations_Day_2
Status | Date Asked | Answered On | Answered By | Asked By | Question/Comment | Answer | Notes
Answered | 2026-02-24 | 2026-02-24 | Daniela Tea | Edwin Aquino | What path do we choose for CF list path (category listing)? Not intuitive; can we update info tools? | Path = parent; component shows children of that parent. E.g. path to EN under news → year folders. Daniela demonstrated; Edwin confirmed. | News session follow-up.
Answered | 2026-02-24 | 2026-02-24 | Kerry Holyoak (SHRSS) / Daniela Tea | Lisa Cardia | Delivery widget: Hard Rock Casino Rockford showing—casino classified as cafe. Who do we contact to fix? | DPLT team (Vipul Patel). Classifications come from DPLT; if misclassified, take to Vipul's team. Lisa to reach out. | Line of business = Cafe in DPLT drives delivery list.
Deferred | 2026-02-24 | 2026-02-24 | Daniela Tea | Rick Lyon | Booking modal: black border; can we make booking widget same size/background as modal? | Note as gap—configurable color/size for modal.
Answered | 2026-02-24 | 2026-02-24 | Rick Lyon / Daniela Tea | Lisa Cardia | Where do we get destination value (e.g. 59391) for booking widget? Do authors need to know it? | Rick: Senex/Vizergy; in booking links. Migrated; values don't change. Authors may need for restore if someone changes. Daniela: casino booking not finalized (pre-pause).
Answered | 2026-02-24 | 2026-02-24 | Daniela Tea | Lisa Cardia | Booking widget: adding a different field (e.g. balcony) beyond rooms/adults/children—development? | Yes—new field type, UI, parameter passing, booking engine side. Development for sure.
Deferred | 2026-02-24 | 2026-02-24 | Daniela Tea | Rick Lyon | Booking offers: can we hide the booking window section completely? | Tried; window still present, fields blank. Hide label too = potential gap. No option to hide completely today.
Deferred | 2026-02-24 | 2026-02-24 | Daniela Tea | Lisa Cardia | Find a location: can we change the background color? | Currently fixed in code. Change would require code update to allow author-configurable background.
Answered | 2026-02-24 | 2026-02-24 | Daniela Tea / Lucas Nelson | Gonzalo Calasich (SHRSS) | Google Map: regions dropdown blank in prod—why? North America first in config but showing last. | Permissions: groups didn't have read on generic list 'regions.' Template Authors given read. Order: ensure regions authored in dialog (first = top); republish page. | ACS Commons on prod. Media session confirmed fix.
Answered | 2026-02-24 | 2026-02-24 | Daniela Tea | Lisa Cardia | Google Map: filter map not in config but filters showing—why? No results vs no locations? | Filter map adds filters on map. Different messages for no results vs no locations. Daniela made copy to demo filter map.
Pending | 2026-02-24 | 2026-02-24 | Daniela Tea | Lisa Cardia / Rick Lyon | Google Map: carousel dots not centered under images. | Daniela noted; would need to be updated to center align carousel dots.
Pending | 2026-02-24 |  |  | Product Director | Who owns DPLT classification (line of business) and SHRSS contact for misclassification? | Not answered in session.
Pending | 2026-02-24 |  |  | Product Director | Which groups need read/write on generic list 'regions' for Google Map? | Not answered in session. Andy covering permissions in KT next week.

## Media
Status | Date Asked | Answered On | Answered By | Asked By | Question/Comment | Answer | Notes
Answered | 2026-02-25 | 2026-02-25 | Daniela Tea | Gonzalo Calasich (SHRSS) | Google Map regions dropdown not visible yesterday—resolution? | Generic list 'regions' populates dropdown. User groups lacked read access. Template Authors given read; Gonzalo and Lisa confirmed can see. Permissions topic with Andy next week. | Locations Day 2 follow-up.
Answered | 2026-02-25 | 2026-02-25 | Daniela Tea | Gonzalo Calasich (SHRSS) | North America showing last on prod—publish page again? | View as published to confirm order; then publish. Andy to take a look at prod page.
Pending | 2026-02-25 | 2026-02-25 | Daniela Tea | Rick Lyon | Media gallery: carousel dots not centered (left of center). | Daniela noted; capture for update to center align carousel dots.
Deferred | 2026-02-25 | 2026-02-25 | Daniela Tea | Edwin Aquino | Image gallery grid: option to show/hide title or inherit from asset like alt text? | Not for this component. Title pulled from DAM metadata. If no title in metadata, 'no title' shows. Enhancement to capture if team wants option to not display title.
Deferred | 2026-02-25 | 2026-02-25 | Daniela Tea | Edwin Aquino | Image gallery grid: different titles for same image per property/site? | Not currently. Control via metadata per asset; no variation/title override in component.
Answered | 2026-02-25 | 2026-02-25 | Don Middlebrook / Daniela Tea | Daniela Tea (to Don) | Image gallery grid: are we adding titles/descriptions to assets? | Don: planning to add as much metadata as possible—titles, description. Daniela: if titles not always desired, capture enhancement to not display or use description.
Pending | 2026-02-25 |  |  | Product Director | Who can add/edit generic list values (e.g. regions)? Which groups get read vs write?
Pending | 2026-02-25 |  |  | Product Director | Image gallery grid: hide title or show description—enhancement?

## Page_Templates
Question | Date Asked | Asked By | Answer | Answered On | Answered By | Status
How are booking parameters (e.g., destinationValue, rooms, adults, children) configured in the Booking Widget component dialog, and how are these values passed to the external booking engine via URL parameters? |  | From Transcript |  |  |  | Pending
What is the authoritative source for the Destination Value (SynXis hotel ID) used in the Booking Widget component, and where should content authors retrieve these IDs when configuring new destinations? |  | From Transcript |  |  |  | Pending
Since the current Booking Widget implementation appears to rely on SynXis hotel booking parameters, how should casino or non-hotel booking engines be integrated with this component? |  | From Transcript |  |  |  | Pending
What determines whether the Booking Widget renders inline on the page versus within a modal dialog, and is this controlled purely by component style variations or by different implementations? |  | From Transcript |  |  |  | Pending
If additional booking parameters are required (for example, additional guest options or filters), would adding new input fields to the Booking Widget require:changes to the component dialogupdates to the booking engine URL structurefront-end development for UI rendering? |  | From Transcript |  |  |  | Pending
What is the functional difference between:enabling arrival/departure date selection, andconfiguring a booking window start and end date within the Booking Offers component? |  | From Transcript |  |  |  | Pending
Is the Booking Window label and date range always rendered on the component even if arrival/departure selection is disabled, or can this label be hidden through configuration? |  | From Transcript |  |  |  | Pending
When configuring booking offers, how are offer parameters passed to the booking engine, and are these parameters configurable within the component dialog or handled externally? |  | From Transcript |  |  |  | Pending
When a user performs a search in the Find Location component, how is the search value passed to the destination page? |  | From Transcript |  |  |  | Pending
If a user enters invalid or unsupported search input (e.g., random text), does the component validate the input before passing it to the Locations page, or does it simply forward the raw value? |  | From Transcript |  |  |  | Pending
Is the functionality of both the Search button and View All button dependent on the same configured Page Path, and is it possible to configure separate destinations for each action? |  | From Transcript |  |  |  | Pending
Since most fields in the Google Map component (e.g., elementId, defaultCenterLatitude, styleJSON, zoomLevel) are not intuitive for content authors, is there a recommended approach for pre-configuring default values so authors only need to add locations? |  | From Transcript |  |  |  | Pending
Can the Google Map component be enhanced to provide default configuration templates so authors can reuse standard map configurations without manually entering technical fields? |  | From Transcript |  |  |  | Pending
Because the map does not render in the author environment unless the domain is whitelisted, what is the process for ensuring author environments are whitelisted so authors can preview the map during authoring? |  | From Transcript |  |  |  | Pending
Since the map styling (style JSON) currently relies on Google Map styling definitions, is there a plan to provide a user-friendly interface in AEM for selecting map styles rather than manually entering JSON? |  | From Transcript |  |  |  | Pending
When filter values are added in the Filter Map configuration, do these filters override the default Line of Business filters (Cafe, Hotel, Casino), or do they extend them? |  | From Transcript |  |  |  | Pending
If custom filter labels are defined in the component configuration, do they only affect the UI labels, or do they also influence the underlying filtering logic for locations retrieved from DPLT? |  | From Transcript |  |  |  | Pending
When regions are configured within the Map Data tab, does the display order on the front end follow the author-defined order in the dialog, or can other factors (such as caching or data ordering) override this? |  | From Transcript |  |  |  | Pending
When specifying Featured Countries within a region configuration, does this override the automatically generated list of countries from DPLT, or does it simply prioritize them in the display? |  | From Transcript |  |  |  | Pending
For Area Guide maps, are the points of interest entirely managed through the Location Addresses section of the component dialog, or can these locations also be sourced dynamically from DPLT? |  | From Transcript |  |  |  | Pending
For each point of interest in the Area Guide map:where are the Visit Site links configured?how are the Get Directions links generated (are they automatically created from latitude/longitude)? |  | From Transcript |  |  |  | Pending
Does the Location List component retrieve the same dataset as the Google Map component, or does it perform a separate query against DPLT? |  | From Transcript |  |  |  | Pending
Since the Location List component does not currently support the Featured Countries override field used in the Google Map component, is this a known limitation or a planned enhancement? |  | From Transcript |  |  |  | Pending
When location data is updated in DPLT, what triggers the synchronization with the Location Content Fragments in AEM:scheduled sync jobmanual ingestionevent-based update? |  | From Transcript |  |  |  | Pending
If optional fields from DPLT (such as Property Legal Name) are blank, how should AEM components handle this scenario to avoid displaying empty labels on the front end? |  | From Transcript |  |  |  | Pending
What is the recommended workflow for reusing complex components (like Google Maps) across pages when copy-paste between pages may not reliably retain configuration values? |  | From Transcript |  |  |  | Pending
Is it possible to define default component configurations at the template or policy level so that newly added components inherit baseline settings automatically? |  | From Transcript |  |  |  | Pending
Which fields in the Location Content Fragment are populated exclusively from DPLT?
Which fields in the Location Content Fragment are intended to be manually maintained by authors?
Are there any fields that can be edited in AEM but later overwritten by DPLT updates?
How does AEM determine whether a field value should come from DPLT data ingestion or author input? is there a configuration/setting somewhere?
Is there documentation listing all DPLT fields and their mapping to AEM Content Fragment fields?
What event triggers the creation of a new Location Content Fragment when a new property is added to DPLT? (i.e. status)
Does the ingestion process automatically publish new Location Content Fragments, or must authors publish them manually?
If a location is removed from DPLT, what happens to its corresponding Content Fragment in AEM?
Is there a process for archiving locations that are no longer active but should remain in historical records?
Can authors accidentally delete Location Content Fragments created by the integration? and if so, dies it show up after the sync?
Are there validation rules preventing authors from saving incomplete Location Content Fragments?
Are authors alerted if required data for a component is missing from a Location Content Fragment?
Is there any validation preventing authors from entering incorrect URLs for delivery partners?
Is there versioning available for Location Content Fragments so changes can be rolled back?
How can authors see which pages are currently using a specific Location Content Fragment?
Is there a way to track which components reference a specific location?
Can authors accidentally break pages by modifying a Location Content Fragment used by multiple pages?
Is there a recommended workflow for testing fragment updates before publishing them globally?
Can authors duplicate Location Content Fragments when creating new locations?
Can authors control the initial zoom level and center point of the map without editing technical fields?
Is there a limit to how many locations can appear on a map before performance is affected?
Are there caching rules applied to map data to improve performance?
What happens if the map API fails to load or returns an error?
Are filter values derived from Content Fragment fields or from tags?
Can authors define custom filter values without modifying the Content Fragment model?
What happens when a location contains multiple filter values for the same category?
Is there a priority rule determining which filter values appear first?
Are filters dynamically generated based on existing data or preconfigured in the component?
Are geographic regions controlled by DPLT or by AEM configuration?
Can a location belong to multiple regions?
How are country names derived for display under each region?
Is there any normalization process for country names coming from DPLT?
If multiple venues exist for a location, how are they displayed in components?
What happens if a venue Content Fragment is referenced by multiple locations?
Are there safeguards preventing incorrect venue associations?
Is there a way to validate that venue data matches the correct property?
s there a recommended maximum number of delivery partners that should be added to a location?
Is there a recommended maximum number of locations supported by the Destination Search component?
Does the system paginate or lazy-load large lists of locations?
How does the system handle high traffic on pages that query many location fragments?
Can the current location architecture support additional property types beyond hotels and cafes?
Would adding new location categories require structural changes to the Content Fragment model?
Can the location architecture support multiple brands within the same system?
Is the system flexible enough to support future expansions such as event venues or partner locations?

## Navigation_and_Data_Display
Question | Date Asked | Asked By | Answer | Answered On | Answered By | Status
Sub Nav - can we add an down facing arrow in the tablet/mobile version to match production so users know to click for more options? |  | @Lisa Cardia |  |  |  | Pending
Sub Nav - why is the alignment/spacing not the same for all links in this component? |  | @Lisa Cardia
Sub Nav - do we have the option to select a light background with dark text? |  | @Lisa Cardia
Content Carousel - The Select Panels feature does not work to change the image you are viewing. Is this a defect? The only option to view is changing to Preview and clicking arrow. |  | @Lisa Cardia
Dropdown - If you keep the dropdown open, it overlaps the content beneath it. Is this defect fixed? Reported for Cafes. |  | @Lisa Cardia
Dropdown - Can we have the option to change the alignment to Center or Right aligned like we do for Buttons? |  | @Lisa Cardia
Dropdown - Is it possible to change the icon? |  | @Lisa Cardia
Tabs - Button Styling does not do anything. Is this a defect? Or dependent on theme? |  | @Lisa Cardia
Tabs - Do content authors always need to add spacing below titles and buttons for appropriate padding? Can this be automatically added to the component to avoid inconsistency? |  | @Lisa Cardia
Tabs - Why is no title or description available on the Horizontal? |  | @Lisa Cardia
Tabs - Has this component been tested on all themes? Can we confirm it’s working? |  | @Lisa Cardia
Tabs - What are the image specs needed for this component? |  | @Lisa Cardia
Table - Why do we have a medium grey and light grey as options for border but no where else? |  | @Lisa Cardia
Table - Can you confirm if authors will use Parallax and GLightbox? If yes, how do they work? |  | @Lisa Cardia
How do authors determine the correct Navigation Start Level for breadcrumbs when building new pages?
How should authors decide when to enable “Show Hidden Navigation Items” in breadcrumbs?
How should authors handle breadcrumbs when a hidden page exists in the page hierarchy but should not appear to users?
How does the “Disable Shadowing” option affect breadcrumb behavior when a page is configured as a redirect?
How should authors determine when to hide the current page from the breadcrumb navigation?
How should breadcrumbs be configured when the page hierarchy becomes very deep and the breadcrumb wraps across multiple lines on mobile?
How does the sitemap determine which pages are included when a root path is selected?
How are hidden pages and their child pages handled within the sitemap component?
How does the sitemap treat special page types such as error pages or redirect pages?
How can authors control the depth of pages displayed in the sitemap if the hierarchy becomes very large?
How does the sitemap determine whether to display the Navigation Title or Page Title?
How should authors structure carousel cards when choosing between the two-column and three-column layout options?
How should authors manage multiple CTAs within the carousel when a location has several menus or actions?
How are new amenities or features added to the selectable list used in the carousel’s “Read More Details” section?
How should authors preview and validate carousel content when images and card content display differently in Author vs Published view?
How should authors manage image consistency when multiple images with different proportions are added to the carousel?
How should authors properly test components in isolation while ensuring the page behaves the same as production?
How should authors configure test pages so the correct theme, header, and footer are applied during component testing?
How should authors determine whether a component should be placed within the root container or a nested container?
How should component dialogs be structured so authors only see relevant configuration fields for that component?
How should consistent spacing and layout behavior be enforced across components to prevent authors from needing to manually insert spacers?
How do breadcrumbs behave if a page is moved to a different location in the site hierarchy after the component has already been configured?
How do breadcrumbs behave if a page has multiple redirect levels in its hierarchy?
How can authors quickly identify the hierarchy level number when deciding what value to use for the navigation start level?
How should authors troubleshoot breadcrumb issues when the structure in AEM does not match what appears on the page?
How does the breadcrumb behave if the Navigation Title field is blank for some pages but populated for others? |  |  | It will show the Title field value instead. |  | Daniela
How does the breadcrumb behave if the Navigation Title field is blank for some pages but populated for others? |  |  | Duplicate of above
How should authors handle sub-navigation when a page in the list is unpublished or deleted?
How does the sub-navigation behave if the current page is not included in the authored list?
How many links can be safely added to a sub-navigation before it impacts usability?
How should authors determine the correct grouping of pages when building sub-navigation for a section?
How should authors determine the correct root path when building a sitemap for a section?
How does the sitemap behave if pages within the hierarchy are unpublished?
How does the sitemap behave if a page is renamed after the sitemap has already been published?
How many cards are recommended within a carousel before usability becomes difficult for users?
How should authors manage carousel content when some cards require more content fields than others?
How does the carousel behave if authors add very long text in description or details fields?
How should authors structure carousel content when different locations require different CTAs?
How should authors manage dropdown content when additional options need to be added later?
How does the dropdown behave when multiple dropdown components are used on the same page?
How should authors structure dropdown links when linking to external vs internal pages?
How should authors handle dropdowns when link destinations change frequently?
How many tabs are recommended before the component becomes difficult to use on desktop or mobile?
How should authors manage tab content when one tab contains significantly more content than others?
How should authors structure content inside tabs to maintain consistent layout across all tabs?
How should authors reorganize tab content if the order of tabs needs to change later?
How should authors decide when to use the table component versus building a table within the text editor?
How should authors manage tables when the data needs to be updated frequently?
How should authors structure tables when content length varies significantly between columns?
How should authors handle tables that contain a large number of rows?
How should authors ensure tables remain readable on mobile devices?

## LOB_Specific
Question | Date Asked | Asked By | Answer | Answered On | Answered By | Status
Is the location that appears in the delivery widget coming from DPLT? | [5 empty] | Pending
Why does the disclaimer text look visually disconnected from the content when the widget is not placed in a container with the production background styling? |  | @Lisa Cardia
Can we control which locations appear in the “Reserve a Table” dropdown list (for example only US locations or only specific locations for a promotion)? |  | @Lisa Cardia
Is the “Reserve Table” experience fragment created inside every cafe folder? |  | @Lisa Cardia
Why is the button appearing purple in the example? |  | @Rick Lyon
Are there safeguards for third-party reservation widgets if the embed code is very large or poorly styled (too wide or too tall)? |  | @Rick Lyon
If a cafe uses a reservation widget other than OpenTable, will that same widget appear in the Reserve Table modal? |  | @Rick Lyon
For a location like Porto that uses a different reservation system, how would that embed be handled in AEM? |  | @Rick Lyon
How should phone numbers be entered so the tel: link works correctly while still displaying formatted characters like dashes? |  | @Lisa Cardia
If fields like phone number or email are blank, will the associated icons still display? |  | @Lisa Cardia
Where do we link the menu PDFs within the dining reservation component? |  | @Lisa Cardia
Do we have recommended image dimensions for the images used in the microsite card placements? |  | @Lisa Cardia @Don Middlebrook
Can the title color be changed in the Messi Experience component? |  | @Lisa Cardia
Why does Button 2 allow opening a modal but Button 1 does not? |  | @Lisa Cardia
On mobile, why are the titles and text left-aligned while the buttons appear centered? |  | @Lisa Cardia
How does the component behave if location services are disabled in the browser? |  | @Mayte Eme
How does the component behave if location services are disabled in the browser? |  | @Mayte Eme
How frequently does AEM refresh location data coming from DPLT content fragments? |  | @Mayte Eme
If a delivery partner URL is removed from a location content fragment, how quickly does it stop appearing in the widget? |  | @Mayte Eme
Is there any sorting logic applied to the delivery partner dropdown (priority order, alphabetical, etc.)?
What happens if a cafe does not have a Reserve Table experience fragment created?
Is there any validation to prevent duplicate experience fragment names across cafes?
Does the system require publishing both the experience fragment and the page for the modal to work?
Does the system require publishing both the experience fragment and the page for the modal to work?
Are there recommended styling constraints for embedded widgets inside the modal?
Are there recommended styling constraints for embedded widgets inside the modal?
Is there a maximum number of menus that should be added before usability becomes difficult?
Is there a maximum number of menus that should be added before usability becomes difficult?
If a social platform is deprecated or removed (like X/Twitter), how is the icon list updated across existing pages?
Are generic lists environment specific, or are they shared across dev, stage, and production?
Is there version control or auditing for changes made to generic lists?
Which of the components shown today are intended to be reusable across other sites (hotels, corporate, etc.)?
Are there components that were built specifically for one campaign or microsite and should not be reused? and why?
How should authors validate that newly added delivery partner links work correctly before publishing?
Can authors temporarily disable a social icon without deleting the configuration?
How should authors handle situations where a location does not have social media profiles?
How can authors verify that the Reserve Table experience fragment was configured correctly for a new location?
What troubleshooting steps should authors follow if the Reserve Table modal displays empty content?
Which components demonstrated in this session are considered core reusable components versus campaign-specific components?
Are delivery partner links marked with appropriate link attributes (nofollow, sponsored, etc.)?
Does the delivery widget generate crawlable links, or are they hidden behind JavaScript interactions?
Do reservation links include tracking parameters or canonical link considerations?
do menu links include structured data for restaurant menus?
Does the microsite template allow authors to configure meta titles, descriptions, and canonical tags?
Are anchor links in the microsite navigation considered SEO-friendly internal links?
Could parallax animations affect content indexing or accessibility for search engines?
Is the content within animated containers visible in the HTML DOM before animations trigger?
Are clicks on delivery partner links tracked as separate analytics events?
Can analytics distinguish between different delivery partners selected by users?
Can analytics identify which reservation platform generated the interaction?
Can analytics identify which reservation platform generated the interaction?
Can we track which cafe location users select within the modal dropdown?
Do we have recommended image dimensions for the images used in the Delivery widget? |  | @Lisa Cardia @Don Middlebrook
Why is the text not Rich Text for the Delivery Widget? |  | @Lisa Cardia
Can we update the Menu Asset Path folder to start with Assets instead of sites? Authors cannot add menus. |  | @Lisa Cardia @Don Middlebrook
Do we have recommended image dimensions for the images used in the Messi Experience? |  | @Lisa Cardia @Don Middlebrook
Do we have recommended image dimensions for the images used in the Microsite Banner? |  | @Lisa Cardia @Don Middlebrook
What does ‘Copy Link to’ do in Microsite Banner? |  | @Lisa Cardia
What size logo is necessary for Microsite Navigation? |  | @Lisa Cardia @Don Middlebrook

## Sheet4
Question | Date Asked | Asked By | Answer | Answered On | Answered By | Status
Button - Allows you to display an icon inside the button (availability depends on your CMS configuration). What is an example of this icon? Can we use fontawesome? |  | @Lisa Cardia |  |  |  | Pending
Accordion - Why does the containers for 1 & 2 automatically set to no width, but as soon as you add item 3, it’s set to content area and then an author has to adjust items 1, 2 and 3? |  | @Lisa Cardia
Tabs Cards Filter - What is paragraph system – HTL? |  | @Lisa Cardia
Card Carousel - Why does the Panel Selector not work for this component? Can we look at all components with Panel Selector option to make sure it is working as expected? |  | @Lisa Cardia
Card - What are the base asset dimensions necessary for consistency for all card style variations? |  | @Lisa Cardia
Alert and Alert Aggregator - We did not cover this in the KT. Can we have documentation on how these components work? |  | @Lisa Cardia
How can authors configure button width as a percentage (for example two buttons each taking 50% width on mobile)? |  | From Transcript
How can authors configure buttons to display side-by-side versus stacked, especially across different screen sizes? |  | From Transcript
How can authors override default button colors for campaign-specific designs such as Pinktober or Pride campaigns? |  | From Transcript
How can authors determine the recommended maximum button text length to prevent wrapping or layout issues? |  | From Transcript
How should authors handle long button text or long words so the layout remains consistent across breakpoints? |  | From Transcript
How can authors create responsive button groups without needing custom CSS? |  | From Transcript
How can authors configure a button to trigger a modal linked to an Experience Fragment so that it displays correctly? |  | From Transcript
What is the recommended layout structure for content inside a modal so it appears properly formatted and complete? |  | From Transcript
If modal styling is controlled elsewhere, where should authors configure or adjust modal styling to ensure it looks presentable? |  | From Transcript
What are the recommended guidelines or layout patterns authors should follow when building Experience Fragment content intended for modals? |  | From Transcript
How can authors trigger a modal from a text link instead of only from a button component? |  | From Transcript
How can authors adjust the heading level or visual size of accordion headers without editing HTML directly? |  | From Transcript
When using anchor links there’s no offset and users do NOT get to the right position on the page. when will that be fixed? |  | @Mayte Eme
How can authors determine or define the ID values used for accordion items when creating anchor links? |  | From Transcript
How can authors configure an accordion item to be expanded by default when the page loads, and how many items can be expanded by default? |  | From Transcript
How should accordions be configured when placed on dark background sections? |  | From Transcript
How can authors ensure text and link colors adjust correctly for accessibility when accordions are used on dark backgrounds? |  | From Transcript
What is the this “Simple” layout option for containers, and how should authors use it? |  | From Transcript
When should authors choose this “simple” layout versus a Grid layout for containers? |  | From Transcript
How should authors structure containers so that sections span full width while content remains aligned within the page grid? |  | From Transcript
What is the usage of this Hide Container option, and how should authors ensure hidden content is not indexed or crawled? |  | From Transcript
How can authors properly hide or remove page sections so they are not visible or discoverable by search engines? |  | From Transcript
how do we actually hide/unplubish any component/row/section so that does not get crawled and found? |  | From Transcript
How should authors assign and manage container IDs when they are needed for analytics tracking or personalization? |  | From Transcript
How can teams apply consistent naming conventions for container IDs to ensure they remain readable and standardized? |  | From Transcript
What safeguards or processes should be used to prevent duplicate container IDs across pages? |  | From Transcript
How can authors configure cards so they maintain consistent heights even when card text lengths vary? |  | From Transcript
What settings should authors apply so cards in the same container automatically match height? |  | From Transcript
How should authors configure text truncation for cards, and can it be managed globally instead of individually? |  | From Transcript
How can authors avoid conflicting card styling combinations when selecting card style options? |  | From Transcript
What is the recommended number of cards in a carousel to maintain good usability and performance? |  | From Transcript
How can authors configure a carousel to dynamically pull cards from content sources instead of adding them manually? |  | From Transcript
How should authors manage scheduled or expired cards within a carousel? manual? how do we handle off hours? |  | From Transcript
How can carousel content be shared across multiple layouts such as carousel, grid, or list views using the same data source? |  | From Transcript
How can authors configure the number of cards displayed per device (desktop, tablet, mobile) in a way that works well across screen sizes? |  | From Transcript
How should authors use or configure the Carousel ID, and what purpose does it serve? is it for personalization (Target) or analytics tracking only? |  | From Transcript
How can authors configure query-based content population so grids, lists, or carousels automatically display content based on defined criteria? |  | From Transcript
What criteria can be used in queries to dynamically pull content (tags, folders, templates, metadata, etc.)? |  | From Transcript
How can authors create pages that automatically populate card grids or lists using query rules instead of manual selection? |  | From Transcript
How can authors configure shared content sources so the same query populates multiple layouts such as grid, list, or carousel? |  | From Transcript
How should authors decide when to use the Tabs Cards Filter component versus standard Tabs or filter components? |  | From Transcript
How can authors configure the Tabs Cards Filter component to filter cards using metadata such as tags? |  | From Transcript
How can authors configure the component to pull cards automatically from Experience Fragments or Content Fragments without manually adding each item? |  | From Transcript
How can authors display Experience Fragments dynamically within components such as lists, grids, or carousels? |  | From Transcript
What methods are available to reuse Experience Fragment content across different page layouts? |  | From Transcript
How can authors confirm that the lightbox component supports keyboard navigation and accessibility requirements? |  | From Transcript
How should the lightbox behave for dark mode or accessibility display modes, and how can authors test this behavior? |  | From Transcript
How should authors configure spacer components so spacing displays consistently in author and published views? |  | From Transcript
What is the recommended approach for using spacers inside containers versus outside containers? |  | From Transcript
How should authors apply spacing so duplicate spacers are not required to achieve the intended layout? Or this bug fixed? |  | From Transcript
How can toolbar options within Rich Text Editor components be restricted or simplified for authors? |  | From Transcript
How can administrators restrict certain components (such as Advanced Embed) so they are only available to specific user groups? |  | From Transcript
What are the recommended image specifications (dimensions, aspect ratio, and file size) for container background images? |  | From Transcript
How should authors understand and use template-specific CSS classes, such as those applied in the News page template? |  | From Transcript
What is the recommended page structure for using containers as layout sections, and how should authors organize components within them? |  | From Transcript
In the News page template, what does the applied CSS class actually control and what functionality does it enable?
Why does the implementation require placing most components inside containers? Should page sections already act as structural containers by default?
What criteria can be used to dynamically pull content (e.g., Experience Fragments, pages, or cards) into components such as carousels, grids, or lists?
What query criteria are supported when pulling dynamic content (tags, folders, templates, metadata, etc.)?
Can components such as carousels, grids, or lists be configured to pull content dynamically using queries instead of requiring manual selection?
Can components such as carousels, grids, or lists be configured to pull content dynamically using queries instead of requiring manual selection?
How can authors build pages that automatically populate content using query-based lists or card grids rather than manually adding items one by one?
Why must authors manually configure the number of cards displayed per device (desktop, tablet, mobile) instead of the component automatically adapting to screen size?
Why does the carousel require a Carousel ID, and how is it used?
Why does the carousel require a Carousel ID, and how is it used?
Why are Experience Fragments restricted in how they can be displayed within certain components?
How can we use icons from our own icon library stored in DAM instead of being limited to Font Awesome?
If the icon we need is not available in Font Awesome, how should authors add and use custom icons?
Are there opportunities to create author presets or templates to reduce the risk of incorrect configuration?
What governance exists to ensure authors do not misuse advanced configuration options (CSS classes, embed components, etc.)?
How can the platform reduce the need for authors to manually configure responsive behavior?
Are components like modals, accordions, and lightboxes fully keyboard accessible?
can we add IDs for analytics and target to every component built by vendor?
For faq schema how is that enabled and disabled. not al accordions are faqs.
Can analytics distinguish between different content sources when the same component is reused across layouts?